## ControlParmeters
Application | NBNLOLO
Change Date | 2019-11-30
Change Number | CRQ000090100719
Change Desc | Application Schema (NBNLOLO) Database Object ReOrg
Host Name | LXDB0164/65
Database Name | LO1P
Environment | PROD

## Change#
CIP FOR APPLICATION DATABASE APPLN. SCHEMA OBJECTS RE-ORG - iTAM# CRQ000090100719
Task # | Task Name | Description | Start (Time) hh:mm AEST | End (Time) hh:mm AEST | Resource | TASK Details | iTAM Group | Planned Duration hh:mm | Actual Duration hh:mm | Remarks | Reviewed By | 2019-11-30
Pre-Change
0 | Ensure sudo access to server to access oracle binaries sqlplus , exp 1. credentials to login the server 2. read & write privilages on application area 3. Execute privilages on oralce binaries like sqlplus, exp on host | If doesn't have access, request access to security group with application approval | 2019-11-22 11:00 |  | AppDBA | TAS000090321467 | INFYDBA | 0:15 |  | We have enough privilege in server and Database | Jayanth
1 | Ensure application tablespaces have enough spare space for performing the database maintenance. Estimate TEMP & UNDO tablespace requirement If there is no enough space, add a task to IBMDSS to add space to respective tablespaces and update IBMSS task #8 | Ensure all application tablespaces have enough spare space for performing the database maintenance. Estimate TEMP & UNDO tablespace requirement If there is no enough space, add a task to IBMDSS to add space to the respective tablespaces. SQL>select a.tablespace_name,mxsize, free, free-mxsize required from ( select tablespace_name , max(bytes)/1024/1024 mxsize from dba_segments a where owner='NBNLOLO' group by tablespace_name ) a , (select tablespace_name , max(bytes)/1024/1024 free from dba_free_space group by tablespace_name ) b where a.tablespace_name=b.tablespace_name(+) | 2019-11-23 12:00 | 2019-11-23 12:30 | AppDBA | TAS000090321467 | INFYDBA | 0:30 |  | App Tablespace addition requirement has been submitted to IBMDSS . TEMP do not require any space | Jayanth
2 | Extract the metadata for tables & indexes for contingency purposes | Extract Metadata for Index and tables using tools like toad/sqldev | 2019-11-27 10:00 | 2019-11-27 10:30 | AppDBA | TAS000090321467 | INFYDBA | 0:30 |  | In progress
3 | Pre Change Artifacts (DB) 1. Collect NBNLOLO Schema segment size 2. Gather information about TableSpace Usage 3. Individual object status and summary | Execute below sripts one by one in sql prompt to gather segment size info and Tablesapce Usage info in the sql prompt SQL> select segment_name, bytes/1024/1024 from dba_segments where owner='NBNLOLO'; SQL> SELECT tablespace_name, TotalSize, TotalSize-Free Used, Free Available, ROUND((TotalSize-Free FROM ( SELECT df.tablespace_name, ROUND(SUM(df.bytes)/1024/1024,3) TotalSize, ROUND(sum(nvl(f.bytes,0))/1024/1024,3) Free from (select tablespace_name,sum(bytes) bytes from dba_data_files group by tablespace_name (select tablespace_name, sum(bytes) bytes from dba_free_space group by tablespace_name ) where df.tablespace_name=f.tablespace_name(+) group by df.tablespace_name ) union ( SELECT a.tablespace_name, ROUND(SUM (nvl(a.BYTES,0)) / (1024 * 1024),3) TotalSize, ROUND(SUM (nvl(b.bytes_cached,0)) / (1024 * 1024),3) used, ROUND(SUM (nvl(a.BYTES,0)) / (1024 * 1024),3) - ROUND(SUM (b.bytes_cached) / (1024 * 1024),3) ROUND((SUM (nvl(b.bytes_cached,0)) / SUM (a.BYTES) * 100),2 ) "Used%" FROM (select tablespace_name, sum(bytes) bytes from dba_temp_files group by tablespace_name ) (select tablespace_name, sum(bytes_cached) bytes_cached from v$temp_extent_pool group by t where a.tablespace_name=b.tablespace_name(+) group by a.tablespace_name ) SQL> select object_name,object_type,status from user_objects order by object_name,object_type; SQL > select object_name, object_type from user_objects where status <>'VALID' order by object_name; SQL> select object_name,object_type,status,count(*) from user_objects group by object_name,object_type,status order by object_name,object_type,status; SQL > select object_type , count(*) from user_objects where status <>'VALID' group by object_type ; SQL>select (case when constraint_type='P' then 'PK' when constraint_type='C' then 'CK' when constraint_type='R' then 'FK' when constraint_type='U' then 'UK' end ) constraint_type, status, count(*) from user_constraints group by constraint_type, status order by 1,2; | 2019-11-27 10:30 | 2019-11-27 11:00 | AppDBA | TAS000090321467 | INFYDBA | 0:30 |  |  | Jayanth
4 | Pre Change Artifacts (Apps) Collect Pre-Change Application Artifacts | Collect Pre-Change Application Artifacts | 2019-11-27 11:00 | 2019-11-27 12:00 | AppSupport | TAS000090321468 | INFYLOLO | 1:00
5 | EBR Level 0 Backup of LO1P on lxdb0164/5 Disable scheduled EBR backup of Sunday (24th Nov) | Take level 0 online backup of LO1P on lxdb0164/5 Disable scheduled EBR backup of LO1P Sunday (24th Nov) | 2019-11-30 17:30 | 2019-11-30 20:30 | IBM EBR Team | TAS000090321473 | IBM EBR Team | 3:00
Change Implementation
6 | Application Shutdown | Bring down application components (Please ensure that Cron scripts are comneted out Control M scripts are paused from execution | 2019-11-30 22:00 | 2019-11-30 23:00 | AppSupport | TAS000090321468 | INFYLOLO | 1:00
| Collect DB SCN and timestamp | Collect DB SCN and timestamp | 2019-11-30 23:00 | 2019-11-30 23:30 | IBM DSS | TAS000090322177 | Application DBA | 0:30
10 | Re-Org all Tables and Indexes | Execute attached scripts 1. lxdb0164 instance script 2. lxdb0165 instance script | 2019-11-30 23:30 | 2019-12-01 06:30 | AppDBA | TAS000090321467 | AppDBA | 7:00
12 | Check Validity of all Indexes & Status of all objects If any of the index is found to be INVALID or UNUSABLE, it needs to be rebuilt with the alter index <index_name> rebuild tablespace <tablespace_name> nologging | Check indexes are valid or not, if invalid rebuild. SQL> select object_name,object_type, status from user_objects; SQL>select index_name , status from user_indexes where status <>'VALID' | 2019-12-01 06:30 | 2019-12-01 07:00 | AppDBA | TAS000090321467 | Infosys APPDBA | 0:30
13 | Gather schema statistics for NBNLOLO schema. | execute below sript to gather object statistics SQL> EXEC DBMS_STATS.GATHER_DATABASE_STATS(ESTIMATE_PERCENT=>DBMS_STATS.AUTO_SAMPLE_SIZE,degree => 16,cascade=> True); | 2019-12-01 07:00 | 2019-12-01 08:30 | AppDBA | TAS000090321467 | Infosys APPDBA | 1:30
Post Change
18 | Post Change Artifacts (DB) 1. Collect NBNLOLO Schema segment size. 2. Gather information about TableSpace Usage 3. Individual object status and summary | Execute below sripts one by one in sql prompt to gather segment size info and Tablesapce Usage info in the sql prompt SQL> select segment_name, bytes/1024/1024 from dba_segments where owner='NBNLOLO'; SQL> SELECT tablespace_name, TotalSize, TotalSize-Free Used, Free Available, ROUND((TotalSize-Free FROM ( SELECT df.tablespace_name, ROUND(SUM(df.bytes)/1024/1024,3) TotalSize, ROUND(sum(nvl(f.bytes,0))/1024/1024,3) Free from (select tablespace_name,sum(bytes) bytes from dba_data_files group by tablespace_name (select tablespace_name, sum(bytes) bytes from dba_free_space group by tablespace_name ) where df.tablespace_name=f.tablespace_name(+) group by df.tablespace_name ) union ( SELECT a.tablespace_name, ROUND(SUM (nvl(a.BYTES,0)) / (1024 * 1024),3) TotalSize, ROUND(SUM (nvl(b.bytes_cached,0)) / (1024 * 1024),3) used, ROUND(SUM (nvl(a.BYTES,0)) / (1024 * 1024),3) - ROUND(SUM (b.bytes_cached) / (1024 * 1024),3) ROUND((SUM (nvl(b.bytes_cached,0)) / SUM (a.BYTES) * 100),2 ) "Used%" FROM (select tablespace_name, sum(bytes) bytes from dba_temp_files group by tablespace_name ) (select tablespace_name, sum(bytes_cached) bytes_cached from v$temp_extent_pool group by t where a.tablespace_name=b.tablespace_name(+) group by a.tablespace_name ) SQL> select object_name,object_type,status from user_objects order by object_name,object_type; SQL > select object_name, object_type from user_objects where status <>'VALID' order by object_name; SQL> select object_name,object_type,status,count(*) from user_objects group by object_name,object_type,status order by object_name,object_type,status; SQL > select object_type , count(*) from user_objects where status <>'VALID' group by object_type ; SQL>select (case when constraint_type='P' then 'PK' when constraint_type='C' then 'CK' when constraint_type='R' then 'FK' when constraint_type='U' then 'UK' end ) constraint_type, status, count(*) from user_constraints group by constraint_type, status order by 1,2; | 2019-12-01 08:30 | 2019-12-01 08:45 | AppDBA | TAS000090321467 | Infosys APPDBA | 0:15
19 | Application Startup | Bring up application components | 2019-12-01 08:45 | 2019-12-01 09:45 | AppSupport | TAS000090321468 | Infosys Application Support Team | 1:00
20 | 1. PVT 2. Post Change Artifacts (Apps) | Application PVT & Collect Post-Change Application Artifacts | 2019-12-01 09:45 | 2019-12-01 10:15 | AppSupport | TAS000090321468 | Infosys Application Support Team | 0:30
Based on PVT outcome if success Goto Instruction 21 Otherwise goto 22
21A | Enable Sunday EBR backup | Enable Sunday EBR backup | 2019-12-01 10:15 | 2019-12-01 10:45 | EBR Team | TAS000090321481 | IBM Midrange EBR Storage Support | 0:30
22 | Fix On Fail | Fix On Fail | 2019-12-01 10:15 | 2019-12-01 11:15 | AppDBA | TAS000090321467 | Infosys APPDBA | 1:00
Backout
23 | Application Sutdown | Bring down application components | 2019-12-01 11:15 | 2019-12-01 12:15 | AppSupport | TAS000090321468 | Infosys Application Support Team | 1:00
24 | Restore / Recover Database | Restore database using pre change backup | 2019-12-01 12:15 | 2019-12-01 16:15 | IBMDSS team | TAS000090321482 | IBMDSS | 4:00
20 | Recover Database | Recover database after the database is restored by IBM EBR team using pre change EBR backup | 2019-12-01 16:15 | 2019-12-01 16:45 | IBMDSS |  |  | 0:30
25 | DB PVT | PVT for Database health check | 2019-12-01 16:45 | 2019-12-01 17:05 | AppDBA | TAS000090321467 | Infosys Application Support Team | 0:20
26 | Application Startup | Bring up application components | 2019-12-01 17:05 | 2019-12-01 18:05 | AppSupport | TAS000090321468 | Infosys Application Support Team | 1:00
27 | PVT | Application PVT | 2019-12-01 18:05 | 2019-12-01 18:35 | AppSupport | TAS000090321468 | Infosys Application Support Team | 0:30
#REF!

## App Performance BenchMark (hidden)
P e r f o r m a n c e B e n c h M a r k S t a t i s t i c s
` | SQL Id | Elapsed Time | [5 empty] | Execution Cost | [6 empty] | Recursive Calls | [5 empty] | DB Block Gets | [5 empty] | Consistent Gets | [5 empty] | Physical reads | [5 empty] | Redo Size | [5 empty] | bytes sent via SQL*Net to client | [5 empty] | Bytes Received Via SQL*Net from client | [5 empty] | SQL*Net roundtrips to/from client | [5 empty] | Sorts (memory) | [5 empty] | Sorts (disk) | [5 empty] | Rows Processed
|  | Before Change |  |  | After Change |  |  | Before Change |  |  |  | After Change |  |  | Before Change |  |  | After Change |  |  | Before Change |  |  | After Change |  |  | Before Change |  |  | After Change |  |  | Before Change |  |  | After Change |  |  | Before Change |  |  | After Change |  |  | Before Change |  |  | After Change |  |  | Before Change |  |  | After Change |  |  | Before Change |  |  | After Change |  |  | Before Change |  |  | After Change |  |  | Before Change |  |  | After Change |  |  | Before Change |  |  | After Change
|  | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | AVG | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3 | Run1 | Run2 | Run3
| PM_Query_1.sql | 00:00:00.17 | 00:00:00.12 | 00:00:00.11 |  |  |  | 36 | 36 | 36 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 58 | 58 | 58 |  |  |  | 19 | 43 | 43 |  |  |  | 0 | 0 | 0 |  |  |  | 149969 | 149969 | 149969 |  |  |  | 3379 | 3379 | 3379 |  |  |  | 250 | 250 | 250 |  |  |  | 1 | 1 | 1 |  |  |  | 0 | 0 | 0 |  |  |  | 3723 | 3723 | 3723
| PM_Query_2.sql | 00:00:00.00 | 00:00:00.01 | 00:00:00.01 |  |  |  | 8 | 8 | 8 |  |  |  |  | 7 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 5 | 3 | 3 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 1170 | 1170 | 1170 |  |  |  | 651 | 651 | 651 |  |  |  | 2 | 2 | 2 |  |  |  | 1 | 1 | 1 |  |  |  | 0 | 0 | 0 |  |  |  | 9 | 9 | 9
| PM_Query_3.sql | 00:00:40.03 | 00:00:21.09 | 00:00:15.81 |  |  |  | 11916 | 11916 | 11916 |  |  |  |  | 23 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 123355 | 123352 | 123352 |  |  |  | 115357 | 119987 | 120290 |  |  |  | 0 | 0 | 0 |  |  |  | 2190 | 2190 | 2190 |  |  |  | 673 | 673 | 673 |  |  |  | 4 | 4 | 4 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 31 | 31 | 31
| PM_Query_4.sql | 00:00:00.03 | 00:00:00.00 | 00:00:00.01 |  |  |  | 8 | 8 | 8 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 4 | 4 | 4 |  |  |  | 3 | 3 | 3 |  |  |  | 0 | 0 | 0 |  |  |  | 501 | 501 | 501 |  |  |  | 456 | 456 | 456 |  |  |  | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| PM_Query_5.sql | 00:00:00.03 | 00:00:00.01 | 00:00:00.01 |  |  |  | 3 | 3 | 3 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 3 | 3 | 3 |  |  |  | 2 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 1154 | 1154 | 1154 |  |  |  | 651 | 651 | 651 |  |  |  | 2 | 2 | 2 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| PM_Query_6.sql | 00:00:00.02 | 00:00:00.01 | 00:00:00.01 |  |  |  | 1 | 1 | 1 |  |  |  |  | 41 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 10 | 3 | 3 |  |  |  | 3 | 2 | 2 |  |  |  | 0 | 0 | 0 |  |  |  | 436 | 436 | 436 |  |  |  | 456 | 456 | 456 |  |  |  | 1 | 1 | 1 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| PM_Query_7.sql | 00:00:00.00 | 00:00:00.00 | 00:00:00.00 |  |  |  | 1 | 1 | 1 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 3 | 3 | 3 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 718 | 718 | 718 |  |  |  | 456 | 456 | 456 |  |  |  | 1 | 1 | 1 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| PM_Query_8.sql | 00:01:35.25 | 00:00:52.77 | 00:00:47.03 |  |  |  | 29556 | 29556 | 29556 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 203541 | 196708 | 196708 |  |  |  | 216453 | 216952 | 170365 |  |  |  | 109460 | 0 | 0 |  |  |  | 660 | 660 | 660 |  |  |  | 651 | 651 | 651 |  |  |  | 2 | 2 | 2 |  |  |  | 1 | 1 | 1 |  |  |  | 0 | 0 | 0 |  |  |  | 2 | 2 | 2
| PM_Query_9.sql | 00:00:00.01 | 00:00:00.01 | 00:00:00.01 |  |  |  | 2 | 2 | 2 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 21 | 21 | 21 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 517 | 517 | 517 |  |  |  | 651 | 651 | 651 |  |  |  | 2 | 2 | 2 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 1 | 1 | 1
| PM_Query_10.sql | 00:00:00.01 | 00:00:00.01 | 00:00:00.00 |  |  |  | 9 | 9 | 9 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 3 | 3 | 3 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 432 | 432 | 432 |  |  |  | 456 | 456 | 456 |  |  |  | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| PM_Query_11.sql | 00:00:00.01 | 00:00:00.00 | 00:00:00.00 |  |  |  | 4 | 4 | 4 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 3 | 3 | 3 |  |  |  | 2 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 774 | 774 | 774 |  |  |  | 456 | 456 | 456 |  |  |  | 1 | 1 | 1 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| PM_Query_12.sql | 00:00:00.01 | 00:00:00.01 | 00:00:00.01 |  |  |  | 1 | 1 | 1 |  |  |  |  | 28 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 10 | 2 | 2 |  |  |  | 2 | 2 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 1517 | 1517 | 1517 |  |  |  | 651 | 651 | 651 |  |  |  | 2 | 2 | 2 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 1 | 1 | 1

## ChangeArtifacts Summary (hidden)
CRQ000001635634 - PRE AND POST CHANGE ARTIFACTS SUMAMRY REPORT
Task | Task Name | Artifacts /Remarks
O | Prechange Activity
A | Rename System Generated Constraints and Constraints with Non Standared Names
1 | Non Standard and Sys Generated Constraints | Refer A.1.NonStdNamedConstrains Sheet
2 | Application Table Constraint Status | Refer A.2.Appln Tbl Constraint Status Sheet
3 | Application Schema Object Status | Refer A.3.Appln Schema Object Status Sheet
B | Creating Partitions into ACTIVITY_HISTORY Table
1 | Activity History Table Partitions | Refer B.1.AH Table Partitions Sheet
2 | Application Table Constraint Status | Refer B.2.Appln TablConstraint Status Sheet
3 | Application Schema Object Status | Refer B.3.Appln Schema Object Status Sheet
4 | Activity History Table SQL Performance Metrics | Refer B.4.AH Table SQL Perfrm Metrics Sheet
C | Application Schema (NBNLOLO) Database Object ReOrg
1 | Tablespace Usage Report | Refer C.1.Tablespace Usage Report Sheet
2 | Schema Object Size Report | Refer C.2.ApSchema Object Size Report Sheet
3 | Application Schema Object Status | Refer C.3. ApplnSchema Object Status Sheet
4 | Application Table Constraint Status | Refer C.4.Appln.Table Constrai Status Sheet
5 | Application Query Performance Metrics | Refer C.5.PM Bench Mark Report Sheet
D | LOB Content MESSGE table Re-org
1 | LOB Content Tables | Refer D.1.LOB Content Table Sheet
2 | Application Schema Object Status | Refer D.2. ApplnSchema Object Status Sheet
3 | Application Table Constraint Status | Refer D.3.Appln.Table Constrai Status Sheet
SUMMARY OF OUTCOME FROM RE-ORG CHANGE - #CRQ000001283050
Benefits |  | Remarks
Storage | Overall 84GB of space can be reclaimed after the retention period of LOB content table and ACTIVITY_HISTORY_OLD table
1 | LOB Content Table MESSGE_20131230 can be dropped after 1 month of retention period
2 | Large objects are moved from GENUSER (common) tablespace to Application Tablespace
3 | LOB Content Table and LOB segment are moved to LOLO_DATA_LOB tablespace from LOLO_DATA_UL03 tablepace
Performance
| Application Query execution Time is significantly reduced | Refer C.5.PM Bench Mark Report Sheet
Recommendations
1 | Contact AppDBA to create any application obecject such as Table/Index/Constraints/etc to confirm the standards
2 | Every End of Year Necessary Partitions should be added to "ACTIVITY_HISTORY" Table as part of Application Maintanance Activty
3 | LOB Content table should be regularly Purged to Make room to grow with out any impact to application
4 | Tables in application schema without Primary key and indexes shoule be relooked.

## O. PrechangeActivity (hidden)
PRE CHANGE ACTIVITIES
Sl.No | Task | Status | Remark
0 | Envionment Setup and access privileages to DB, HOST | Done | No Access and setup issues
1 | Tablespace Space Avaialability Check | Done, , No More additional space required
2 | Extract the metadata for tables & indexes for contingency purposes | Done
3 | Pre Change Artifacts (DB) | Done | Presented in respective Sheets

## A.1.NonStdNamedConstrains (hidden)
NonStandard Named Constraints |  |  | Summary
NONStandard/System Generated Constraints | Forecasted | After Change/Standardizing | Constraints | Before Change | Forecasted | After Change
XPKACTIVITY | ACTIVITY_PK | ACTIVITY_PK | System Generated | 12 | 0 | 0
XPKACTIVITY_HISTORY | ACTIVITY_HISTORY_PK | ACTIVITY_HISTORY_PK | Tool Generated | 27 | 0 | 0
XPKATTRIBUTE | ATTRIBUTE_PK | ATTRIBUTE_PK | Non Standard | 48 | 0 | 0
XPKCUSTOMER_COURTESY_TITLE | CUSTOMER_COURTESY_TITLE_PK | CUSTOMER_COURTESY_TITLE_PK | Standard | 67 | 154 | 154
XPKCUSTOMER_TYPE | CUSTOMER_TYPE_PK | CUSTOMER_TYPE_PK
XPKEAST_ADDRESS_TYPE | EAST_ADDRESS_TYPE_PK | EAST_ADDRESS_TYPE_PK
XPKEAST_AXIS_ADDRESS_TYPE | EAST_AXIS_ADDRESS_TYPE_PK | EAST_AXIS_ADDRESS_TYPE_PK
XPKEAST_AXIS_STREET_TYPE | EAST_AXIS_STREET_TYPE_PK | EAST_AXIS_STREET_TYPE_PK
XPKEAST_AXIS_STREET_TYPE_SUFFI | EAST_AXIS_STREET_TYPE_SUFFIX_PK | EAST_AXIS_STREET_TYPE_SUFFIX_PK
XPKENTRY_MEDIUM | ENTRY_MEDIUM_PK | ENTRY_MEDIUM_PK
XPKFULLYCONFIGUREDSQRESPONSE | FULLY_CONFIG_SQ_RESPONSE_PK | FULLY_CONFIG_SQ_RESPONSE_PK
XPKFWOM_TIME_SLOT | FWOM_TIME_SLOT_PK | FWOM_TIME_SLOT_PK
XPKMOP_ORDER | MOP_ORDER_PK | MOP_ORDER_PK
XPKMOP_ORDER_ITEM_NOTIFICATION | MOP_ORDER_ITEM_NOTIFICATION_PK | MOP_ORDER_ITEM_NOTIFICATION_PK
XPKMOP_STATUS | MOP_STATUS_PK | MOP_STATUS_PK
XPKNOTES | NOTES_PK | NOTES_PK
XPKOFFERING_ATTRIBUTE | OFFERING_ATTRIBUTE_PK | OFFERING_ATTRIBUTE_PK
XPKPOSTCODE_LOCALITY | POSTCODE_LOCALITY_PK | POSTCODE_LOCALITY_PK
XPKREASON | REASON_PK | REASON_PK
XPKREQUEST_ITEM | REQUEST_ITEM_PK | REQUEST_ITEM_PK
XPKSDDB_ATTRIBUTE | SDDB_ATTRIBUTE_PK | SDDB_ATTRIBUTE_PK
XPKSERVICE_STATUS | SERVICE_STATUS_PK | SERVICE_STATUS_PK
XPKSP_SP_GROUP | SP_SP_GROUP_PK | SP_SP_GROUP_PK
XPKTARIFF | TARIFF_PK | TARIFF_PK
XPKWORK_TYPE_OFFERING | WORK_TYPE_OFFERING_PK | WORK_TYPE_OFFERING_PK
SYS_C0031561 | CCA_PK | CCA_PK
SYS_C0031565 | CHARACTERISTIC_PK | CHARACTERISTIC_PK
SYS_C0031567 | CHARAC_ASSOCIATION_PK | CHARAC_ASSOCIATION_PK
SYS_C0031569 | CHARAC_PARAMETER_PK | CHARAC_PARAMETER_PK
SYS_C0031571 | CHARAC_PARAM_ASSOCIATION_PK | CHARAC_PARAM_ASSOCIATION_PK
SYS_C0031579 | DIRECTORY_DETAILS_PK | DIRECTORY_DETAILS_PK
SYS_C0031611 | INSTANT_HOTLINE_PK | INSTANT_HOTLINE_PK
SYS_C0031615 | LOLO_MSQ_ATT_MAP_PK | LOLO_MSQ_ATT_MAP_PK
SYS_C0031617 | LOLO_MSQ_SRV_MAP_PK | LOLO_MSQ_SRV_MAP_PK
SYS_C0031639 | POP_LOCK_PK | POP_LOCK_PK
SYS_C0031694 | SERVICE_NK_NUMBER_INVENTORY_PK | SERVICE_NK_NUMBER_INVENTORY_PK
SYS_C0038738 | AMEND_LOCK_PK | AMEND_LOCK_PK
CC_ASTATE_CODE | AUST_STATE_CK | AUST_STATE_CK
CC_EQUIP_01 | EQUIPMENT_CK | EQUIPMENT_CK
CC_EQUIP_02 | EQUIPMENT_CK | EQUIPMENT_CK
POP_RULE_ACTION_ACTION_CHK | POP_RULE_ACTION_CK | POP_RULE_ACTION_CK
POP_RULE_CONDN_VALUE_TYPE_CHK | POP_RULE_CONDITION_CK | POP_RULE_CONDITION_CK
POP_RULE_CONDN_RULE_CONDN_CHK | POP_RULE_CONDITION_CK | POP_RULE_CONDITION_CK
CC_SN_01 | SP_SHORT_NAME_CK | SP_SHORT_NAME_CK
CC_WQ_01 | WORK_QUEUE_CK | WORK_QUEUE_CK
CC_WQ_02 | WORK_QUEUE_CK | WORK_QUEUE_CK
CC_WTCAT_01 | WORK_TYPE_CATEGORY_CK | WORK_TYPE_CATEGORY_CK
CC_WTCAT_02 | WORK_TYPE_CATEGORY_CK | WORK_TYPE_CATEGORY_CK
FK_EQUIP_ETYP_01 | EQUIPMENT_FK | EQUIPMENT_FK
FK_QA_WG_01 | QUEUE_ASSIGNMENT_FK | QUEUE_ASSIGNMENT_FK
FK_USERS_WG_01 | USERS_FK | USERS_FK
FK_ASSH_WQ_01 | ASSIGNMENT_HISTORY_FK | ASSIGNMENT_HISTORY_FK
FK_QA_WORK_QUEUE_1 | QUEUE_ASSIGNMENT_FK | QUEUE_ASSIGNMENT_FK
FK_REQ_WQ | REQUEST_FK | REQUEST_FK
R_49 | ACTIVITY_HISTORY_FK | ACTIVITY_HISTORY_FK
FK_CREQ_REAS_01 | CHANGE_REQUEST_FK | CHANGE_REQUEST_FK
FK_RITM_RIS_01 | REQUEST_ITEM_FK | REQUEST_ITEM_FK
FK_REQ_RSTAT_01 | REQUEST_FK | REQUEST_FK
R_53 | MOP_STATUS_FK | MOP_STATUS_FK
WORKTYPE_SP_WORKTYPE_AUTH | SP_WORK_TYPE_AUTH_FK | SP_WORK_TYPE_AUTH_FK
PK_ASSH | ASSIGNMENT_HISTORY_PK | ASSIGNMENT_HISTORY_PK
PK_ASTATE | AUST_STATE_PK | AUST_STATE_PK
PK_CIDN | SP_CIDN_PK | SP_CIDN_PK
PK_CREQ | CHANGE_REQUEST_PK | CHANGE_REQUEST_PK
PK_CRIT | COMPLEX_REQUEST_ITEM_PK | COMPLEX_REQUEST_ITEM_PK
XPKEAST_SUB_ADDRESS_TYPE | EAST_SUB_ADDRESS_TYPE_PK | EAST_SUB_ADDRESS_TYPE_PK
PK_EQUIP | EQUIPMENT_PK | EQUIPMENT_PK
PK_ETYP | EQUIPMENT_TYPE_PK | EQUIPMENT_TYPE_PK
PK_OOTY | OFFERING_OFFERING_TYPE_PK | OFFERING_OFFERING_TYPE_PK
PK_OT | OFFERING_TYPE_PK | OFFERING_TYPE_PK
PK_PCMS_CODE | PCMS_CODE_PK | PCMS_CODE_PK
PK_PROG | PROGRAMMING_PK | PROGRAMMING_PK
PK_PSER | PSTS_SERVICE_PK | PSTS_SERVICE_PK
PK_QA | QUEUE_ASSIGNMENT_PK | QUEUE_ASSIGNMENT_PK
PK_QC | QUEUE_CRITERIA_PK | QUEUE_CRITERIA_PK
PK_RIS | REQUEST_ITEM_STATUS_PK | REQUEST_ITEM_STATUS_PK
PK_RISH | REQUEST_ITEM_STATUS_HISTORY_PK | REQUEST_ITEM_STATUS_HISTORY_PK
PK_RS | REQUEST_STATUS_PK | REQUEST_STATUS_PK
PK_RSH | REQUEST_STATUS_HISTORY_PK | REQUEST_STATUS_HISTORY_PK
PK_SN | SP_SHORT_NAME_PK | SP_SHORT_NAME_PK
PK_SPC | SP_CONTACT_PK | SP_CONTACT_PK
PK_SPG | SP_GROUP_PK | SP_GROUP_PK
PK_SPWTA | SP_WORK_TYPE_AUTH_PK | SP_WORK_TYPE_AUTH_PK
PK_WG | WORK_GROUP_PK | WORK_GROUP_PK
PK_WQ | WORK_QUEUE_PK | WORK_QUEUE_PK
PK_WTCAT | WORK_TYPE_CATEGORY_PK | WORK_TYPE_CATEGORY_PK
UK_SPG_01 | SPG_UK1 | SPG_UK1

## A.2.Appln Tbl Constraint Status (hidden)
Application Object Constraint Status Details | [5 empty] | Disabled Constraints | [5 empty] | Application Object Constraint Summary
Before Rename |  |  | After Rename |  |  | Before Change |  | Forecasted |  | After Change |  | Before Rename |  |  | After Rename
CONSTRAINT_TYPE | CONSTRAINT_NAME | STATUS | CONSTRAINT_TYPE | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_TYPE | STATUS | No.Cons | CONSTRAINT_TYPE | STATUS | No.Cons
CK | CC_ASTATE_CODE | ENABLED | CK | AUST_STATE_CK | ENABLED | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | CK | ENABLED | 16 | CK | ENABLED | 16
CK | CC_EQUIP_01 | ENABLED | CK | EQUIPMENT_CK | ENABLED | WORKTYPE_SP_WORKTYPE_AUTH | DISABLED | SP_WORK_TYPE_AUTH_FK | DISABLED | SP_WORK_TYPE_AUTH_FK | DISABLED | FK | DISABLED | 12 | FK | DISABLED | 12
CK | CC_EQUIP_02 | ENABLED | CK | EQUIPMENT_DELVMD_CK | ENABLED | R_53 | DISABLED | MOP_STATUS_FK | DISABLED | MOP_STATUS_FK | DISABLED | FK | ENABLED | 31 | FK | ENABLED | 31
CK | CC_SN_01 | ENABLED | CK | POP_RULE_ACTION_CK | ENABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | PK | ENABLED | 93 | PK | ENABLED | 93
CK | CC_WQ_01 | ENABLED | CK | POP_RULE_CONDITION_CK | ENABLED | PARENT_SERV_OFF_FK | DISABLED | PARENT_SERV_OFF_FK | DISABLED | PARENT_SERV_OFF_FK | DISABLED | UK | ENABLED | 2 | UK | ENABLED | 2
CK | CC_WQ_02 | ENABLED | CK | POP_RULE_CONDN_RULE_CONDN_CK | ENABLED | RQST_STATUS_STATUSHIST_FK | DISABLED | RQST_STATUS_STATUSHIST_FK | DISABLED | SPOFFERINGASSOC_ATT_FK | DISABLED | Total |  | 154 | Total |  | 154
CK | CC_WTCAT_01 | ENABLED | CK | SP_SHORT_NAME_CK | ENABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED
CK | CC_WTCAT_02 | ENABLED | CK | SYS_C0031655 | ENABLED | FK_CREQ_REAS_01 | DISABLED | CHANGE_REQUEST_FK | DISABLED | CHANGE_REQUEST_FK | DISABLED
CK | POP_RULE_ACTION_ACTION_CHK | ENABLED | CK | SYS_C0031656 | ENABLED | REASON_CODE_FK | DISABLED | REASON_CODE_FK | DISABLED | REASON_CODE_FK | DISABLED
CK | POP_RULE_CONDN_RULE_CONDN_CHK | ENABLED | CK | SYS_C0032034 | ENABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED
CK | POP_RULE_CONDN_VALUE_TYPE_CHK | ENABLED | CK | SYS_C0032036 | ENABLED | PARENT_MESSAGE_ID_FK | DISABLED | PARENT_MESSAGE_ID_FK | DISABLED | PARENT_MESSAGE_ID_FK | DISABLED
CK | SYS_C0031655 | ENABLED | CK | SYS_C0032037 | ENABLED | SPOFFERINGASSOC_ATT_FK | DISABLED | SPOFFERINGASSOC_ATT_FK | DISABLED | RQST_STATUS_STATUSHIST_FK | DISABLED
CK | SYS_C0031656 | ENABLED | CK | WORK_QUEUE_CK | ENABLED
CK | SYS_C0032034 | ENABLED | CK | WORK_QUEUE_DELFLG_CK | ENABLED
CK | SYS_C0032036 | ENABLED | CK | WORK_TYPE_CATEGORY_CK | ENABLED
CK | SYS_C0032037 | ENABLED | CK | WORK_TYPE_CATEGORY_DELFLG_CK | ENABLED
FK | CHARACTERISTIC_FK | ENABLED | FK | ACTIVITY_HISTORY_FK | ENABLED | CK - Check
FK | CHARACTERISTIC_FK_01 | ENABLED | FK | ASSIGNMENT_HISTORY_FK | ENABLED | FK - Reference
FK | CHARAC_ASSOC_ID_FK | ENABLED | FK | CHANGE_REQUEST_FK | DISABLED | PK - Primary Key
FK | CHARAC_PARAM_ASSOC_ID_FK | ENABLED | FK | CHARAC_ASSOC_ID_FK | ENABLED | UK - Unique Key
FK | CHARAC_PARAM_ID_FK | ENABLED | FK | CHARAC_PARAM_ASSOC_ID_FK | ENABLED
FK | FK_ASSH_WQ_01 | ENABLED | FK | CHARAC_PARAM_ID_FK | ENABLED
FK | FK_CREQ_REAS_01 | DISABLED | FK | CHARACTERISTIC_FK | ENABLED
FK | FK_EQUIP_ETYP_01 | ENABLED | FK | CHARACTERISTIC_FK_01 | ENABLED
FK | FK_QA_WG_01 | ENABLED | FK | EQUIPMENT_FK | ENABLED
FK | FK_QA_WORK_QUEUE_1 | ENABLED | FK | FK_QA_WORK_QUEUE_1 | ENABLED
FK | FK_REQ_RSTAT_01 | ENABLED | FK | FK_REQ_RSTAT_01 | ENABLED
FK | FK_REQ_WQ | ENABLED | FK | FNN_REL_RSP_REQSTITAM_FK | ENABLED
FK | FK_RITM_RIS_01 | ENABLED | FK | FNN_VLD_RSP_REQSTITAM_FK | ENABLED
FK | FK_USERS_WG_01 | ENABLED | FK | LOLO_MSQ_ATT_ATTRIBUTE_FK | ENABLED
FK | FNN_REL_RSP_REQSTITAM_FK | ENABLED | FK | MOP_STATUS_FK | DISABLED
FK | FNN_VLD_RSP_REQSTITAM_FK | ENABLED | FK | OFFER_ATTT_FK | ENABLED
FK | LOLO_MSQ_ATT_ATTRIBUTE_FK | ENABLED | FK | OFFERING_PCMS_CODE_FK | ENABLED
FK | OFFERING_PCMS_CODE_FK | ENABLED | FK | OFFERTYPE_OFFERING_OT_FK | DISABLED
FK | OFFERTYPE_OFFERING_OT_FK | DISABLED | FK | PARENT_MESSAGE_ID_FK | DISABLED
FK | OFFER_ATTT_FK | ENABLED | FK | PARENT_SERV_OFF_FK | DISABLED
FK | PARENT_MESSAGE_ID_FK | DISABLED | FK | PCO_OFFID_FK | ENABLED
FK | PARENT_SERV_OFF_FK | DISABLED | FK | PCO_PRDID_FK | ENABLED
FK | PCO_OFFID_FK | ENABLED | FK | POSTCODE_LOCALITY_FK | ENABLED
FK | PCO_PRDID_FK | ENABLED | FK | QUEUE_ASSIGNMENT_FK | ENABLED
FK | POSTCODE_LOCALITY_FK | ENABLED | FK | REASON_CODE_FK | DISABLED
FK | REASON_CODE_FK | DISABLED | FK | REQUEST_FK | ENABLED
FK | REQUESTITAM_WORKTYPE_FK | ENABLED | FK | REQUEST_ITEM_FK | ENABLED
FK | RI_STATUSHIST_RI_STATUS_FK | DISABLED | FK | REQUESTITAM_WORKTYPE_FK | ENABLED
FK | RQSTITAM_BUNDLE_FK | ENABLED | FK | RI_STATUSHIST_RI_STATUS_FK | DISABLED
FK | RQSTITEM_REASON_CODE_FK | ENABLED | FK | RQST_RQSTITEM_FK | ENABLED
FK | RQST_RQSTITEM_FK | ENABLED | FK | RQST_STATUS_STATUSHIST_FK | DISABLED
FK | RQST_STATUS_STATUSHIST_FK | DISABLED | FK | RQSTITAM_BUNDLE_FK | ENABLED
FK | R_49 | ENABLED | FK | RQSTITEM_REASON_CODE_FK | ENABLED
FK | R_53 | DISABLED | FK | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED
FK | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | FK | SP_CONACT_ID_FK | ENABLED
FK | SPOFFERINGASSOC_ATT_FK | DISABLED | FK | SP_WORK_TYPE_AUTH_FK | DISABLED
FK | SP_CONACT_ID_FK | ENABLED | FK | SPOFFERINGASSOC_ATT_FK | DISABLED
FK | SRGROUP_SP_GROUP_FK | ENABLED | FK | SRGROUP_SP_GROUP_FK | ENABLED
FK | USER_SPD_FK | ENABLED | FK | USER_SPD_FK | ENABLED
FK | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | FK | USERS_FK | ENABLED
FK | WORKTYPE_SP_WORKTYPE_AUTH | DISABLED | FK | WORKTYPE_CAT_WORKTYPE_FK | DISABLED
FK | WTAO_OFFID_FK | ENABLED | FK | WTAO_OFFID_FK | ENABLED
FK | WTAO_WTID_FK | ENABLED | FK | WTAO_WTID_FK | ENABLED
PK | BPM_USER_PK | ENABLED | PK | ACTIVITY_HISTORY_PK | ENABLED
PK | BUNDLE_PRODUCT_CLASS_PK | ENABLED | PK | ACTIVITY_PK | ENABLED
PK | ERROR_MAPPING_PK | ENABLED | PK | AMEND_LOCK_PK | ENABLED
PK | FNN_RELOCATION_RESPONSE_PK | ENABLED | PK | ASSIGNMENT_HISTORY_PK | ENABLED
PK | FNN_VALIDATION_RESPONSE_PK | ENABLED | PK | ATTRIBUTE_PK | ENABLED
PK | GENERAL_REFERENCE_PK | ENABLED | PK | AUST_STATE_PK | ENABLED
PK | MESSAGE_ID_PK | ENABLED | PK | BPM_USER_PK | ENABLED
PK | OFFERING_PK | ENABLED | PK | BUNDLE_PRODUCT_CLASS_PK | ENABLED
PK | PK_ASSH | ENABLED | PK | CCA_PK | ENABLED
PK | PK_ASTATE | ENABLED | PK | CHANGE_REQUEST_PK | ENABLED
PK | PK_CIDN | ENABLED | PK | CHARAC_ASSOCIATION_PK | ENABLED
PK | PK_CREQ | ENABLED | PK | CHARAC_PARAM_ASSOCIATION_PK | ENABLED
PK | PK_CRIT | ENABLED | PK | CHARAC_PARAMETER_PK | ENABLED
PK | PK_EQUIP | ENABLED | PK | CHARACTERISTIC_PK | ENABLED
PK | PK_ETYP | ENABLED | PK | COMPLEX_REQUEST_ITEM_PK | ENABLED
PK | PK_OOTY | ENABLED | PK | CUSTOMER_COURTESY_TITLE_PK | ENABLED
PK | PK_OT | ENABLED | PK | CUSTOMER_TYPE_PK | ENABLED
PK | PK_PCMS_CODE | ENABLED | PK | DIRECTORY_DETAILS_PK | ENABLED
PK | PK_PROG | ENABLED | PK | EAST_ADDRESS_TYPE_PK | ENABLED
PK | PK_PSER | ENABLED | PK | EAST_AXIS_ADDRESS_TYPE_PK | ENABLED
PK | PK_QA | ENABLED | PK | EAST_AXIS_STREET_TYPE_PK | ENABLED
PK | PK_QC | ENABLED | PK | EAST_AXIS_STRT_TYPE_SUFFIX_PK | ENABLED
PK | PK_RIS | ENABLED | PK | EAST_SUB_ADDRESS_TYPE_PK | ENABLED
PK | PK_RISH | ENABLED | PK | ENTRY_MEDIUM_PK | ENABLED
PK | PK_RS | ENABLED | PK | EQUIPMENT_PK | ENABLED
PK | PK_RSH | ENABLED | PK | EQUIPMENT_TYPE_PK | ENABLED
PK | PK_SN | ENABLED | PK | ERROR_MAPPING_PK | ENABLED
PK | PK_SPC | ENABLED | PK | FNN_RELOCATION_RESPONSE_PK | ENABLED
PK | PK_SPG | ENABLED | PK | FNN_VALIDATION_RESPONSE_PK | ENABLED
PK | PK_SPWTA | ENABLED | PK | FULLY_CONFIG_SQ_RESPONSE_PK | ENABLED
PK | PK_WG | ENABLED | PK | FWOM_TIME_SLOT_PK | ENABLED
PK | PK_WQ | ENABLED | PK | GENERAL_REFERENCE_PK | ENABLED
PK | PK_WTCAT | ENABLED | PK | INSTANT_HOTLINE_PK | ENABLED
PK | PLAN_PK | ENABLED | PK | LOLO_MSQ_ATT_MAP_PK | ENABLED
PK | POP_RULE_ACTION_PK | ENABLED | PK | LOLO_MSQ_SRV_MAP_PK | ENABLED
PK | POP_RULE_BINDING_PK | ENABLED | PK | MESSAGE_ID_PK | ENABLED
PK | POP_RULE_CONDITION_PK | ENABLED | PK | MOP_ORDER_ITEM_NOTIFICATION_PK | ENABLED
PK | PRODUCT_CLASS_PK | ENABLED | PK | MOP_ORDER_PK | ENABLED
PK | REASON_CODE_PK | ENABLED | PK | MOP_STATUS_PK | ENABLED
PK | REQUEST_PK | ENABLED | PK | NOTES_PK | ENABLED
PK | REQUEST_SPCONTACT_PK | ENABLED | PK | OFFERING_ATTRIBUTE_PK | ENABLED
PK | RULEACTION_PK | ENABLED | PK | OFFERING_OFFERING_TYPE_PK | ENABLED
PK | RULECONDITION_PK | ENABLED | PK | OFFERING_PK | ENABLED
PK | SELECTED_PRODUCT_PK | ENABLED | PK | OFFERING_TYPE_PK | ENABLED
PK | SERVICEABILITYRESPONSE_PK | ENABLED | PK | PCMS_CODE_PK | ENABLED
PK | SERVICE_IDENTIFIER_PK | ENABLED | PK | PLAN_PK | ENABLED
PK | SERVICE_OFFERING_PK | ENABLED | PK | POP_LOCK_PK | ENABLED
PK | SERVICE_PROVIDER_PK | ENABLED | PK | POP_RULE_ACTION_PK | ENABLED
PK | SERVICE_STATUS_HISTORY_PK | ENABLED | PK | POP_RULE_BINDING_PK | ENABLED
PK | SPOFFERINGASSOC_PK | ENABLED | PK | POP_RULE_CONDITION_PK | ENABLED
PK | SYS_C0031561 | ENABLED | PK | POSTCODE_LOCALITY_PK | ENABLED
PK | SYS_C0031565 | ENABLED | PK | PRODUCT_CLASS_PK | ENABLED
PK | SYS_C0031567 | ENABLED | PK | PROGRAMMING_PK | ENABLED
PK | SYS_C0031569 | ENABLED | PK | PSTS_SERVICE_PK | ENABLED
PK | SYS_C0031571 | ENABLED | PK | QUEUE_ASSIGNMENT_PK | ENABLED
PK | SYS_C0031579 | ENABLED | PK | QUEUE_CRITERIA_PK | ENABLED
PK | SYS_C0031611 | ENABLED | PK | REASON_CODE_PK | ENABLED
PK | SYS_C0031615 | ENABLED | PK | REASON_PK | ENABLED
PK | SYS_C0031617 | ENABLED | PK | REQUEST_ITEM_PK | ENABLED
PK | SYS_C0031639 | ENABLED | PK | REQUEST_ITEM_STATUS_HISTORY_PK | ENABLED
PK | SYS_C0031694 | ENABLED | PK | REQUEST_ITEM_STATUS_PK | ENABLED
PK | SYS_C0038738 | ENABLED | PK | REQUEST_PK | ENABLED
PK | TIME_SLOT_PK | ENABLED | PK | REQUEST_SPCONTACT_PK | ENABLED
PK | USER_PK | ENABLED | PK | REQUEST_STATUS_HISTORY_PK | ENABLED
PK | WORKQUEUE_DECISION_PK | ENABLED | PK | REQUEST_STATUS_PK | ENABLED
PK | WORK_TYPE_ALLOWED_OFFERING_PK | ENABLED | PK | RULEACTION_PK | ENABLED
PK | WORK_TYPE_PK | ENABLED | PK | RULECONDITION_PK | ENABLED
PK | XPKACTIVITY | ENABLED | PK | SDDB_ATTRIBUTE_PK | ENABLED
PK | XPKACTIVITY_HISTORY | ENABLED | PK | SELECTED_PRODUCT_PK | ENABLED
PK | XPKATTRIBUTE | ENABLED | PK | SERVICE_IDENTIFIER_PK | ENABLED
PK | XPKCUSTOMER_COURTESY_TITLE | ENABLED | PK | SERVICE_NK_NUMBER_INVENTORY_PK | ENABLED
PK | XPKCUSTOMER_TYPE | ENABLED | PK | SERVICE_OFFERING_PK | ENABLED
PK | XPKEAST_ADDRESS_TYPE | ENABLED | PK | SERVICE_PROVIDER_PK | ENABLED
PK | XPKEAST_AXIS_ADDRESS_TYPE | ENABLED | PK | SERVICE_STATUS_HISTORY_PK | ENABLED
PK | XPKEAST_AXIS_STREET_TYPE | ENABLED | PK | SERVICE_STATUS_PK | ENABLED
PK | XPKEAST_AXIS_STREET_TYPE_SUFFI | ENABLED | PK | SERVICEABILITYRESPONSE_PK | ENABLED
PK | XPKEAST_SUB_ADDRESS_TYPE | ENABLED | PK | SP_CIDN_PK | ENABLED
PK | XPKENTRY_MEDIUM | ENABLED | PK | SP_CONTACT_PK | ENABLED
PK | XPKFULLYCONFIGUREDSQRESPONSE | ENABLED | PK | SP_GROUP_PK | ENABLED
PK | XPKFWOM_TIME_SLOT | ENABLED | PK | SP_SHORT_NAME_PK | ENABLED
PK | XPKMOP_ORDER | ENABLED | PK | SP_SP_GROUP_PK | ENABLED
PK | XPKMOP_ORDER_ITEM_NOTIFICATION | ENABLED | PK | SP_WORK_TYPE_AUTH_PK | ENABLED
PK | XPKMOP_STATUS | ENABLED | PK | SPOFFERINGASSOC_PK | ENABLED
PK | XPKNOTES | ENABLED | PK | TARIFF_PK | ENABLED
PK | XPKOFFERING_ATTRIBUTE | ENABLED | PK | TIME_SLOT_PK | ENABLED
PK | XPKPOSTCODE_LOCALITY | ENABLED | PK | USER_PK | ENABLED
PK | XPKREASON | ENABLED | PK | WORK_GROUP_PK | ENABLED
PK | XPKREQUEST_ITEM | ENABLED | PK | WORK_QUEUE_PK | ENABLED
PK | XPKSDDB_ATTRIBUTE | ENABLED | PK | WORK_TYPE_ALLOWED_OFFERING_PK | ENABLED
PK | XPKSERVICE_STATUS | ENABLED | PK | WORK_TYPE_CATEGORY_PK | ENABLED
PK | XPKSP_SP_GROUP | ENABLED | PK | WORK_TYPE_OFFERING_PK | ENABLED
PK | XPKTARIFF | ENABLED | PK | WORK_TYPE_PK | ENABLED
PK | XPKWORK_TYPE_OFFERING | ENABLED | PK | WORKQUEUE_DECISION_PK | ENABLED
UK | RULEFLITER_UK1 | ENABLED | UK | RULEFLITER_UK1 | ENABLED
UK | UK_SPG_01 | ENABLED | UK | SPG_UK1 | ENABLED

## A.3.Appln Schema Object Status (hidden)
Schema Object Status | [5 empty] | Schema Object Status Summary
Before Change |  |  | After Change |  |  | Before Change |  |  | After Change
OBJECT_TYPE | OBJECT_NAME | STATUS | OBJECT_TYPE | OBJECT_NAME | STATUS | OBJECT_TYPE | STATUS | NO OBJS | OBJECT_TYPE | STATUS | NO OBJS
DATABASE_LINK | LOLO | VALID | DATABASE_LINK | LOLO | VALID | DATABASE_LINK | VALID | 3 | DATABASE_LINK | VALID | 3
DATABASE_LINK | CAT | VALID | DATABASE_LINK | CAT | VALID | FUNCTION | VALID | 5 | FUNCTION | VALID | 5
DATABASE_LINK | MYLOLOCAT | VALID | DATABASE_LINK | MYLOLOCAT | VALID | INDEX | VALID | 135 | INDEX | VALID | 135
FUNCTION | GET_FNN | VALID | FUNCTION | GET_FNN | VALID | LOB | VALID | 3 | LOB | VALID | 3
FUNCTION | FN_APP_DATE | VALID | FUNCTION | FN_APP_DATE | VALID | SEQUENCE | VALID | 9 | SEQUENCE | VALID | 9
FUNCTION | GET_ORDER_NO | VALID | FUNCTION | GET_ORDER_NO | VALID | SYNONYM | VALID | 13 | SYNONYM | VALID | 13
FUNCTION | SQUIRREL_GET_ERROR_OFFSET | VALID | FUNCTION | SQUIRREL_GET_ERROR_OFFSET | VALID | TABLE | VALID | 120 | TABLE | VALID | 120
FUNCTION | GET_APP_REV_ID | VALID | FUNCTION | GET_APP_REV_ID | VALID | VIEW | VALID | 1 | VIEW | VALID | 1
INDEX | AH_UPDATED_DATE_IDX | VALID | INDEX | AH_UPDATED_DATE_IDX | VALID | Total |  | 289 | Total |  | 289
INDEX | ECS_USER_IDX | VALID | INDEX | ACTIVITY_PK | VALID
INDEX | SYS_C0031561 | VALID | INDEX | ACTIVITY_HISTORY_PK | VALID
INDEX | SYS_C0031565 | VALID | INDEX | ASSIGNMENT_HISTORY_PK | VALID
INDEX | SYS_C0031567 | VALID | INDEX | ATTRIBUTE_PK | VALID
INDEX | SYS_C0031569 | VALID | INDEX | AUST_STATE_PK | VALID
INDEX | SYS_C0031571 | VALID | INDEX | CHANGE_REQUEST_PK | VALID
INDEX | SYS_C0031579 | VALID | INDEX | CUSTOMER_COURTESY_TITLE_PK | VALID
INDEX | SYS_C0031611 | VALID | INDEX | CUSTOMER_TYPE_PK | VALID
INDEX | SYS_C0031615 | VALID | INDEX | EAST_AXIS_ADDRESS_TYPE_PK | VALID
INDEX | SYS_C0031617 | VALID | INDEX | EAST_AXIS_STREET_TYPE_PK | VALID
INDEX | SYS_C0031639 | VALID | INDEX | EAST_AXIS_STRT_TYPE_SUFFIX_PK | VALID
INDEX | SYS_C0031694 | VALID | INDEX | EAST_SUB_ADDRESS_TYPE_PK | VALID
INDEX | USER_PK | VALID | INDEX | FULLY_CONFIG_SQ_RESPONSE_PK | VALID
INDEX | SERVICE_PROVIDER_PK | VALID | INDEX | FWOM_TIME_SLOT_PK | VALID
INDEX | SYS_C0038738 | VALID | INDEX | MOP_ORDER_PK | VALID
INDEX | CRD_APPMT_REVNID_IDX | VALID | INDEX | MOP_ORDER_ITEM_NOTIFICATION_PK | VALID
INDEX | SYS_IL0000062608C00004$$ | VALID | INDEX | MOP_STATUS_PK | VALID
INDEX | SYS_IL0000062611C00006$$ | VALID | INDEX | NOTES_PK | VALID
INDEX | SYS_IL0000062649C00036$$ | VALID | INDEX | OFFERING_ATTRIBUTE_PK | VALID
INDEX | BPM_USER_PK | VALID | INDEX | PCMS_CODE_PK | VALID
INDEX | BUNDLE_PRODUCT_CLASS_PK | VALID | INDEX | POSTCODE_LOCALITY_PK | VALID
INDEX | ERROR_MAPPING_PK | VALID | INDEX | QUEUE_ASSIGNMENT_PK | VALID
INDEX | FK_ASSH_REQ_01 | VALID | INDEX | REASON_PK | VALID
INDEX | FK_ASSH_USERS_01 | VALID | INDEX | REQUEST_ITEM_STATUS_PK | VALID
INDEX | FK_ASSH_WQ_01 | VALID | INDEX | REQUEST_ITEM_STATUS_HISTORY_PK | VALID
INDEX | FK_CRIT_REQ_01 | VALID | INDEX | REQUEST_STATUS_PK | VALID
INDEX | FK_EQUIP_ETYP_01 | VALID | INDEX | REQUEST_STATUS_HISTORY_PK | VALID
INDEX | FK_EQUIP_RITM_01 | VALID | INDEX | SDDB_ATTRIBUTE_PK | VALID
INDEX | FK_QA_WG_01 | VALID | INDEX | SERVICE_STATUS_PK | VALID
INDEX | FK_QA_WQ_01 | VALID | INDEX | SP_CIDN_PK | VALID
INDEX | FK_WG_WG_01 | VALID | INDEX | SP_CONTACT_PK | VALID
INDEX | FNN_RELOCATION_RESPONSE_PK | VALID | INDEX | SP_SHORT_NAME_PK | VALID
INDEX | FNN_VALIDATION_RESPONSE_PK | VALID | INDEX | SP_WORK_TYPE_AUTH_PK | VALID
INDEX | GENERAL_REFERENCE_PK | VALID | INDEX | WORK_GROUP_PK | VALID
INDEX | MESSAGE_ID_PK | VALID | INDEX | WORK_QUEUE_PK | VALID
INDEX | NK_FNN | VALID | INDEX | WORK_TYPE_CATEGORY_PK | VALID
INDEX | OFFERING_PK | VALID | INDEX | WORK_TYPE_OFFERING_PK | VALID
INDEX | PK_ASSH | VALID | INDEX | REQUEST_ITEM_PK | VALID
INDEX | PK_ASTATE | VALID | INDEX | TARIFF_PK | VALID
INDEX | PK_CIDN | VALID | INDEX | SP_SP_GROUP_PK | VALID
INDEX | PK_CREQ | VALID | INDEX | SP_GROUP_PK | VALID
INDEX | PK_CRIT | VALID | INDEX | QUEUE_CRITERIA_PK | VALID
INDEX | PK_EAST_SUB_ADDRESS_TYPE | VALID | INDEX | PSTS_SERVICE_PK | VALID
INDEX | PK_EQUIP | VALID | INDEX | PROGRAMMING_PK | VALID
INDEX | PK_ETYP | VALID | INDEX | OFFERING_TYPE_PK | VALID
INDEX | PK_OOTY | VALID | INDEX | OFFERING_OFFERING_TYPE_PK | VALID
INDEX | PK_OT | VALID | INDEX | EQUIPMENT_TYPE_PK | VALID
INDEX | PK_PCMS_CODE | VALID | INDEX | EQUIPMENT_PK | VALID
INDEX | PK_PROG | VALID | INDEX | ENTRY_MEDIUM_PK | VALID
INDEX | PK_PSER | VALID | INDEX | EAST_ADDRESS_TYPE_PK | VALID
INDEX | PK_QA | VALID | INDEX | COMPLEX_REQUEST_ITEM_PK | VALID
INDEX | PK_QC | VALID | INDEX | CRD_PK | VALID
INDEX | PK_RIS | VALID | INDEX | ECS_USER_IDX | VALID
INDEX | PK_RISH | VALID | INDEX | SYS_C0031561 | VALID
INDEX | PK_RS | VALID | INDEX | SYS_C0031565 | VALID
INDEX | PK_RSH | VALID | INDEX | SYS_C0031567 | VALID
INDEX | PK_SN | VALID | INDEX | SYS_C0031569 | VALID
INDEX | PK_SPC | VALID | INDEX | SYS_C0031571 | VALID
INDEX | PK_SPG | VALID | INDEX | SYS_C0031579 | VALID
INDEX | PK_SPWTA | VALID | INDEX | SYS_C0031611 | VALID
INDEX | PK_WG | VALID | INDEX | SYS_C0031615 | VALID
INDEX | PK_WQ | VALID | INDEX | SYS_C0031617 | VALID
INDEX | PK_WTCAT | VALID | INDEX | SYS_C0031639 | VALID
INDEX | PLAN_PK | VALID | INDEX | SYS_C0031694 | VALID
INDEX | POP_RULE_ACTION_PK | VALID | INDEX | USER_PK | VALID
INDEX | POP_RULE_BINDING_PK | VALID | INDEX | SERVICE_PROVIDER_PK | VALID
INDEX | POP_RULE_CONDITION_PK | VALID | INDEX | SYS_C0038738 | VALID
INDEX | PRODUCT_CLASS_PK | VALID | INDEX | CRD_APPMT_REVNID_IDX | VALID
INDEX | REASON_CODE_PK | VALID | INDEX | SYS_IL0000062608C00004$$ | VALID
INDEX | REQUEST_PK | VALID | INDEX | SYS_IL0000062611C00006$$ | VALID
INDEX | REQUEST_SPCONTACT_PK | VALID | INDEX | SYS_IL0000062649C00036$$ | VALID
INDEX | RULEACTION_PK | VALID | INDEX | BPM_USER_PK | VALID
INDEX | RULECONDITION_PK | VALID | INDEX | BUNDLE_PRODUCT_CLASS_PK | VALID
INDEX | RULEFLITER_UK1 | VALID | INDEX | ERROR_MAPPING_PK | VALID
INDEX | SELECTED_PRODUCT_PK | VALID | INDEX | FK_ASSH_REQ_01 | VALID
INDEX | SERVICEABILITYRESPONSE_PK | VALID | INDEX | FK_ASSH_USERS_01 | VALID
INDEX | SERVICE_IDENTIFIER_PK | VALID | INDEX | FK_ASSH_WQ_01 | VALID
INDEX | SERVICE_OFFERING_PK | VALID | INDEX | FK_CRIT_REQ_01 | VALID
INDEX | SERVICE_STATUS_HISTORY_PK | VALID | INDEX | FK_EQUIP_ETYP_01 | VALID
INDEX | SPOFFERINGASSOC_PK | VALID | INDEX | FK_EQUIP_RITM_01 | VALID
INDEX | TIME_SLOT_PK | VALID | INDEX | FK_QA_WG_01 | VALID
INDEX | TPSQL_IDX | VALID | INDEX | FK_QA_WQ_01 | VALID
INDEX | UK_SPG_01 | VALID | INDEX | FK_WG_WG_01 | VALID
INDEX | WORKQUEUE_DECISION_PK | VALID | INDEX | FNN_RELOCATION_RESPONSE_PK | VALID
INDEX | WORK_TYPE_ALLOWED_OFFERING_PK | VALID | INDEX | FNN_VALIDATION_RESPONSE_PK | VALID
INDEX | WORK_TYPE_PK | VALID | INDEX | GENERAL_REFERENCE_PK | VALID
INDEX | XPKACTIVITY | VALID | INDEX | MESSAGE_ID_PK | VALID
INDEX | XPKACTIVITY_HISTORY | VALID | INDEX | NK_FNN | VALID
INDEX | XPKATTRIBUTE | VALID | INDEX | OFFERING_PK | VALID
INDEX | XPKCRD | VALID | INDEX | PLAN_PK | VALID
INDEX | XPKCUSTOMER_COURTESY_TITLE | VALID | INDEX | POP_RULE_ACTION_PK | VALID
INDEX | XPKCUSTOMER_TYPE | VALID | INDEX | POP_RULE_BINDING_PK | VALID
INDEX | XPKEAST_ADDRESS_TYPE | VALID | INDEX | POP_RULE_CONDITION_PK | VALID
INDEX | XPKEAST_AXIS_ADDRESS_TYPE | VALID | INDEX | PRODUCT_CLASS_PK | VALID
INDEX | XPKEAST_AXIS_STREET_TYPE | VALID | INDEX | REASON_CODE_PK | VALID
INDEX | XPKEAST_AXIS_STREET_TYPE_SUFFI | VALID | INDEX | REQUEST_PK | VALID
INDEX | XPKENTRY_MEDIUM | VALID | INDEX | REQUEST_SPCONTACT_PK | VALID
INDEX | XPKFULLYCONFIGUREDSQRESPONSE | VALID | INDEX | RULEACTION_PK | VALID
INDEX | XPKFWOM_TIME_SLOT | VALID | INDEX | RULECONDITION_PK | VALID
INDEX | XPKMOP_ORDER | VALID | INDEX | RULEFLITER_UK1 | VALID
INDEX | XPKMOP_ORDER_ITEM_NOTIFICATION | VALID | INDEX | SELECTED_PRODUCT_PK | VALID
INDEX | XPKMOP_STATUS | VALID | INDEX | SERVICEABILITYRESPONSE_PK | VALID
INDEX | XPKNOTES | VALID | INDEX | SERVICE_IDENTIFIER_PK | VALID
INDEX | XPKOFFERING_ATTRIBUTE | VALID | INDEX | SERVICE_OFFERING_PK | VALID
INDEX | XPKPOSTCODE_LOCALITY | VALID | INDEX | SERVICE_STATUS_HISTORY_PK | VALID
INDEX | XPKREASON | VALID | INDEX | SPOFFERINGASSOC_PK | VALID
INDEX | XPKREQUEST_ITEM | VALID | INDEX | SPG_UK1 | VALID
INDEX | XPKSDDB_ATTRIBUTE | VALID | INDEX | TIME_SLOT_PK | VALID
INDEX | XPKSERVICE_STATUS | VALID | INDEX | TPSQL_IDX | VALID
INDEX | XPKSP_SP_GROUP | VALID | INDEX | WORKQUEUE_DECISION_PK | VALID
INDEX | XPKTARIFF | VALID | INDEX | WORK_TYPE_ALLOWED_OFFERING_PK | VALID
INDEX | XPKWORK_TYPE_OFFERING | VALID | INDEX | WORK_TYPE_PK | VALID
INDEX | REQUEST_REVISION_ID_AH_IDX | VALID | INDEX | REQUEST_REVISION_ID_AH_IDX | VALID
INDEX | REQ_STATUS_DESC_IDX | VALID | INDEX | REQ_STATUS_DESC_IDX | VALID
INDEX | REVISION_IDX | VALID | INDEX | REVISION_IDX | VALID
INDEX | REQUEST_ITEM_REVISION_ID_IDX | VALID | INDEX | REQUEST_ITEM_REVISION_ID_IDX | VALID
INDEX | REQUEST_REVISION_ID_IDX | VALID | INDEX | REQUEST_REVISION_ID_IDX | VALID
INDEX | SP_VIEWABLE_FLAG_IDX | VALID | INDEX | SP_VIEWABLE_FLAG_IDX | VALID
INDEX | CREATED_DATE_IDX | VALID | INDEX | CREATED_DATE_IDX | VALID
INDEX | SP_INDEX | VALID | INDEX | SP_INDEX | VALID
INDEX | REQ_STATUS_IDX | VALID | INDEX | REQ_STATUS_IDX | VALID
INDEX | REQUEST_ID_PK | VALID | INDEX | REQUEST_ID_PK | VALID
INDEX | APPOINTMENT_REQREVNID_IDX | VALID | INDEX | APPOINTMENT_REQREVNID_IDX | VALID
INDEX | FNN_VALDN_RESP_REVID_IDX | VALID | INDEX | FNN_VALDN_RESP_REVID_IDX | VALID
INDEX | REQUEST_REVISDTSTAMP_IDX | VALID | INDEX | REQUEST_REVISDTSTAMP_IDX | VALID
INDEX | REQUEST_REV_IDX | VALID | INDEX | REQUEST_REV_IDX | VALID
INDEX | ACTIVITY_ID_IDX | VALID | INDEX | ACTIVITY_ID_IDX | VALID
INDEX | ECS_USER | VALID | INDEX | ECS_USER | VALID
INDEX | ASSIGNED_USER_IDX | VALID | INDEX | ASSIGNED_USER_IDX | VALID
INDEX | REQ_STATUS_CODE_IDX | VALID | INDEX | REQ_STATUS_CODE_IDX | VALID
INDEX | REQ_ID_IDX | VALID | INDEX | REQ_ID_IDX | VALID
INDEX | REQ_REVISION_IDX | VALID | INDEX | REQ_REVISION_IDX | VALID
INDEX | REQ_ITEM_STATUS_IDX | VALID | INDEX | REQ_ITEM_STATUS_IDX | VALID
INDEX | REQ_ITEM_HISTORY_IDX | VALID | INDEX | REQ_ITEM_HISTORY_IDX | VALID
LOB | SYS_LOB0000062608C00004$$ | VALID | LOB | SYS_LOB0000062608C00004$$ | VALID
LOB | SYS_LOB0000062649C00036$$ | VALID | LOB | SYS_LOB0000062649C00036$$ | VALID
LOB | SYS_LOB0000062611C00006$$ | VALID | LOB | SYS_LOB0000062611C00006$$ | VALID
SEQUENCE | ORDERID_SEQ | VALID | SEQUENCE | ORDERID_SEQ | VALID
SEQUENCE | REQUEST_SEQ | VALID | SEQUENCE | REQUEST_SEQ | VALID
SEQUENCE | ORDERITEM_SEQ | VALID | SEQUENCE | ORDERITEM_SEQ | VALID
SEQUENCE | ORDER_SEQ | VALID | SEQUENCE | ORDER_SEQ | VALID
SEQUENCE | REQUESTITEM_SEQ | VALID | SEQUENCE | REQUESTITEM_SEQ | VALID
SEQUENCE | LOLIG_SEQUENCE | VALID | SEQUENCE | LOLIG_SEQUENCE | VALID
SEQUENCE | ORDERITEMID_SEQ | VALID | SEQUENCE | ORDERITEMID_SEQ | VALID
SEQUENCE | REQUESTITEMID_SEQ | VALID | SEQUENCE | REQUESTITEMID_SEQ | VALID
SEQUENCE | REQUESTID_SEQ | VALID | SEQUENCE | REQUESTID_SEQ | VALID
SYNONYM | OFFERING_ATTRIBUTE_1 | VALID | SYNONYM | OFFERING_ATTRIBUTE_1 | VALID
SYNONYM | OFFERING_OFFERING_TYPE_1 | VALID | SYNONYM | OFFERING_OFFERING_TYPE_1 | VALID
SYNONYM | OFFERING_TYPE_1 | VALID | SYNONYM | OFFERING_TYPE_1 | VALID
SYNONYM | WORK_TYPE_CATEGORY_1 | VALID | SYNONYM | WORK_TYPE_CATEGORY_1 | VALID
SYNONYM | REQUEST_STATUS_1 | VALID | SYNONYM | REQUEST_STATUS_1 | VALID
SYNONYM | REQUEST_STATUS_HISTORY_1 | VALID | SYNONYM | REQUEST_STATUS_HISTORY_1 | VALID
SYNONYM | ATTRIBUTE_VALUE_1 | VALID | SYNONYM | ATTRIBUTE_VALUE_1 | VALID
SYNONYM | SERVICE_OFFERING_SETTING_1 | VALID | SYNONYM | SERVICE_OFFERING_SETTING_1 | VALID
SYNONYM | WORK_TYPE_1 | VALID | SYNONYM | WORK_TYPE_1 | VALID
SYNONYM | REQUEST_ITEM_STATUS_HISTORY_1 | VALID | SYNONYM | REQUEST_ITEM_STATUS_HISTORY_1 | VALID
SYNONYM | AUST_STATE_1 | VALID | SYNONYM | AUST_STATE_1 | VALID
SYNONYM | ATTRIBUTE_1 | VALID | SYNONYM | ATTRIBUTE_1 | VALID
SYNONYM | SERVICE_OFFERING_1 | VALID | SYNONYM | SERVICE_OFFERING_1 | VALID
TABLE | ACTIVITY | VALID | TABLE | ACTIVITY | VALID
TABLE | ACTIVITY_HISTORY | VALID | TABLE | ACTIVITY_HISTORY | VALID
TABLE | ATTRIBUTE | VALID | TABLE | ATTRIBUTE | VALID
TABLE | AUST_STATE | VALID | TABLE | AUST_STATE | VALID
TABLE | BUNDLE_NETWORK_TYPE | VALID | TABLE | BUNDLE_NETWORK_TYPE | VALID
TABLE | CCA | VALID | TABLE | CCA | VALID
TABLE | CHANGE_REQUEST | VALID | TABLE | CHANGE_REQUEST | VALID
TABLE | CHANNEL | VALID | TABLE | CHANNEL | VALID
TABLE | CRD | VALID | TABLE | CRD | VALID
TABLE | CUSTOMER_COURTESY_TITLE | VALID | TABLE | CUSTOMER_COURTESY_TITLE | VALID
TABLE | CUSTOMER_TYPE | VALID | TABLE | CUSTOMER_TYPE | VALID
TABLE | EAST_ADDRESS_TYPE | VALID | TABLE | EAST_ADDRESS_TYPE | VALID
TABLE | EAST_AXIS_ADDRESS_TYPE | VALID | TABLE | EAST_AXIS_ADDRESS_TYPE | VALID
TABLE | EAST_AXIS_STREET_TYPE | VALID | TABLE | EAST_AXIS_STREET_TYPE | VALID
TABLE | EAST_AXIS_STREET_TYPE_SUFFIX | VALID | TABLE | EAST_AXIS_STREET_TYPE_SUFFIX | VALID
TABLE | ENTRY_MEDIUM | VALID | TABLE | ENTRY_MEDIUM | VALID
TABLE | ERROR_MAPPING | VALID | TABLE | ERROR_MAPPING | VALID
TABLE | FULLY_CONFIG_SQ_RESPONSE | VALID | TABLE | FULLY_CONFIG_SQ_RESPONSE | VALID
TABLE | FWOM_TIME_SLOT | VALID | TABLE | FWOM_TIME_SLOT | VALID
TABLE | LOLO_FWOM_REASON_MAP | VALID | TABLE | LOLO_FWOM_REASON_MAP | VALID
TABLE | MESSAGE | VALID | TABLE | MESSAGE | VALID
TABLE | MOP_ORDER | VALID | TABLE | MOP_ORDER | VALID
TABLE | MOP_ORDER_ITEM | VALID | TABLE | MOP_ORDER_ITEM | VALID
TABLE | MOP_ORDER_ITEM_NOTIFICATION | VALID | TABLE | MOP_ORDER_ITEM_NOTIFICATION | VALID
TABLE | MOP_SERVICE_INVENTORY | VALID | TABLE | MOP_SERVICE_INVENTORY | VALID
TABLE | MOP_STATUS | VALID | TABLE | MOP_STATUS | VALID
TABLE | NOTES | VALID | TABLE | NOTES | VALID
TABLE | OFFERING_ATTRIBUTE | VALID | TABLE | OFFERING_ATTRIBUTE | VALID
TABLE | OFFERING_OFFERING_TYPE | VALID | TABLE | OFFERING_OFFERING_TYPE | VALID
TABLE | OFFERING_TYPE | VALID | TABLE | OFFERING_TYPE | VALID
TABLE | REASON | VALID | TABLE | REASON | VALID
TABLE | REQUEST_ITEM_STATUS | VALID | TABLE | REQUEST_ITEM_STATUS | VALID
TABLE | REQUEST_ITEM_STATUS_HISTORY | VALID | TABLE | REQUEST_ITEM_STATUS_HISTORY | VALID
TABLE | REQUEST_SPCONTACT | VALID | TABLE | REQUEST_SPCONTACT | VALID
TABLE | REQUEST_STATUS | VALID | TABLE | REQUEST_STATUS | VALID
TABLE | REQUEST_STATUS_HISTORY | VALID | TABLE | REQUEST_STATUS_HISTORY | VALID
TABLE | SDDB_ATTRIBUTE | VALID | TABLE | SDDB_ATTRIBUTE | VALID
TABLE | SELECTED_PRODUCT | VALID | TABLE | SELECTED_PRODUCT | VALID
TABLE | SERVICEABILITY_RESPONSE | VALID | TABLE | SERVICEABILITY_RESPONSE | VALID
TABLE | SERVICE_IDENTIFIER | VALID | TABLE | SERVICE_IDENTIFIER | VALID
TABLE | SERVICE_OFFERING | VALID | TABLE | SERVICE_OFFERING | VALID
TABLE | SERVICE_STATUS | VALID | TABLE | SERVICE_STATUS | VALID
TABLE | SERVICE_STATUS_HISTORY | VALID | TABLE | SERVICE_STATUS_HISTORY | VALID
TABLE | SP_CIDN | VALID | TABLE | SP_CIDN | VALID
TABLE | SP_CONTACT | VALID | TABLE | SP_CONTACT | VALID
TABLE | SP_GROUP | VALID | TABLE | SP_GROUP | VALID
TABLE | SP_OFFERING_ASSOCIATION | VALID | TABLE | SP_OFFERING_ASSOCIATION | VALID
TABLE | SP_SHORT_NAME | VALID | TABLE | SP_SHORT_NAME | VALID
TABLE | SP_SP_GROUP | VALID | TABLE | SP_SP_GROUP | VALID
TABLE | SP_WORK_TYPE_AUTH | VALID | TABLE | SP_WORK_TYPE_AUTH | VALID
TABLE | TARIFF | VALID | TABLE | TARIFF | VALID
TABLE | TIME_SLOT | VALID | TABLE | TIME_SLOT | VALID
TABLE | WORK_TYPE | VALID | TABLE | WORK_TYPE | VALID
TABLE | WORK_TYPE_CATEGORY | VALID | TABLE | WORK_TYPE_CATEGORY | VALID
TABLE | WORK_TYPE_OFFERING | VALID | TABLE | WORK_TYPE_OFFERING | VALID
TABLE | TOAD_PLAN_TABLE | VALID | TABLE | TOAD_PLAN_TABLE | VALID
TABLE | USERS | VALID | TABLE | USERS | VALID
TABLE | SERVICE_PROVIDER | VALID | TABLE | SERVICE_PROVIDER | VALID
TABLE | SYS_TEMP_FBT | VALID | TABLE | SYS_TEMP_FBT | VALID
TABLE | AMEND_LOCK | VALID | TABLE | AMEND_LOCK | VALID
TABLE | APPOINTMENT | VALID | TABLE | APPOINTMENT | VALID
TABLE | ADDRESS | VALID | TABLE | ADDRESS | VALID
TABLE | ASSIGNMENT_HISTORY | VALID | TABLE | ASSIGNMENT_HISTORY | VALID
TABLE | ATTRIBUTE_VALUE | VALID | TABLE | ATTRIBUTE_VALUE | VALID
TABLE | BPM_USERS | VALID | TABLE | BPM_USERS | VALID
TABLE | BUNDLE | VALID | TABLE | BUNDLE | VALID
TABLE | BUNDLE_PRODUCT_CLASS | VALID | TABLE | BUNDLE_PRODUCT_CLASS | VALID
TABLE | CHAINED_ROWS | VALID | TABLE | CHAINED_ROWS | VALID
TABLE | CHARACTERISTIC | VALID | TABLE | CHARACTERISTIC | VALID
TABLE | CHARAC_ASSOCIATION | VALID | TABLE | CHARAC_ASSOCIATION | VALID
TABLE | CHARAC_PARAMETER | VALID | TABLE | CHARAC_PARAMETER | VALID
TABLE | CHARAC_PARAM_ASSOCIATION | VALID | TABLE | CHARAC_PARAM_ASSOCIATION | VALID
TABLE | CHARAC_PARAM_VALUE | VALID | TABLE | CHARAC_PARAM_VALUE | VALID
TABLE | COMPLEX_REQUEST_ITEM | VALID | TABLE | COMPLEX_REQUEST_ITEM | VALID
TABLE | CUSTOMER | VALID | TABLE | CUSTOMER | VALID
TABLE | DIRECTORY_DETAILS | VALID | TABLE | DIRECTORY_DETAILS | VALID
TABLE | EAST_SUB_ADDRESS_TYPE | VALID | TABLE | EAST_SUB_ADDRESS_TYPE | VALID
TABLE | EQUIPMENT | VALID | TABLE | EQUIPMENT | VALID
TABLE | EQUIPMENT_TYPE | VALID | TABLE | EQUIPMENT_TYPE | VALID
TABLE | FNN_RELOCATION_RESPONSE | VALID | TABLE | FNN_RELOCATION_RESPONSE | VALID
TABLE | FNN_VALIDATION_RESPONSE | VALID | TABLE | FNN_VALIDATION_RESPONSE | VALID
TABLE | GENERAL_REFERENCE | VALID | TABLE | GENERAL_REFERENCE | VALID
TABLE | INSTANT_HOTLINE | VALID | TABLE | INSTANT_HOTLINE | VALID
TABLE | LOLO_MSQ_ATT_MAP | VALID | TABLE | LOLO_MSQ_ATT_MAP | VALID
TABLE | LOLO_MSQ_SRV_MAP | VALID | TABLE | LOLO_MSQ_SRV_MAP | VALID
TABLE | OFFERING | VALID | TABLE | OFFERING | VALID
TABLE | OFFERING_BUNDLE_ASSOCIATION | VALID | TABLE | OFFERING_BUNDLE_ASSOCIATION | VALID
TABLE | OFFERING_CATEGORY | VALID | TABLE | OFFERING_CATEGORY | VALID
TABLE | PCMS_CODE | VALID | TABLE | PCMS_CODE | VALID
TABLE | POP_LOCK | VALID | TABLE | POP_LOCK | VALID
TABLE | POP_RULE_ACTION | VALID | TABLE | POP_RULE_ACTION | VALID
TABLE | POP_RULE_BINDING | VALID | TABLE | POP_RULE_BINDING | VALID
TABLE | POP_RULE_CONDITION | VALID | TABLE | POP_RULE_CONDITION | VALID
TABLE | PORT_CHURN_INFO | VALID | TABLE | PORT_CHURN_INFO | VALID
TABLE | POSTCODE_LOCALITY | VALID | TABLE | POSTCODE_LOCALITY | VALID
TABLE | PRODUCT_CLASS | VALID | TABLE | PRODUCT_CLASS | VALID
TABLE | PRODUCT_CLASS_OFFERING | VALID | TABLE | PRODUCT_CLASS_OFFERING | VALID
TABLE | PROGRAMMING | VALID | TABLE | PROGRAMMING | VALID
TABLE | PSTS_SERVICE | VALID | TABLE | PSTS_SERVICE | VALID
TABLE | QUEUE_ASSIGNMENT | VALID | TABLE | QUEUE_ASSIGNMENT | VALID
TABLE | QUEUE_CRITERIA | VALID | TABLE | QUEUE_CRITERIA | VALID
TABLE | REQUEST | VALID | TABLE | REQUEST | VALID
TABLE | REQUEST_ITEM | VALID | TABLE | REQUEST_ITEM | VALID
TABLE | RULEACTION | VALID | TABLE | RULEACTION | VALID
TABLE | RULECONDITION | VALID | TABLE | RULECONDITION | VALID
TABLE | RULEFLITER | VALID | TABLE | RULEFLITER | VALID
TABLE | SERVICE | VALID | TABLE | SERVICE | VALID
TABLE | SERVICE_AREA_ASSOCIATION | VALID | TABLE | SERVICE_AREA_ASSOCIATION | VALID
TABLE | SERVICE_NK_NUMBER_INVENTORY | VALID | TABLE | SERVICE_NK_NUMBER_INVENTORY | VALID
TABLE | SERVICE_OFFERING_SETTING | VALID | TABLE | SERVICE_OFFERING_SETTING | VALID
TABLE | SP_BUNDLE | VALID | TABLE | SP_BUNDLE | VALID
TABLE | SP_OFFERING | VALID | TABLE | SP_OFFERING | VALID
TABLE | SQ_MAPPING | VALID | TABLE | SQ_MAPPING | VALID
TABLE | TBL_AUDIT_LOLIG | VALID | TABLE | TBL_AUDIT_LOLIG | VALID
TABLE | TOAD_PLAN_SQL | VALID | TABLE | TOAD_PLAN_SQL | VALID
TABLE | T_ERROR_CODE_MAST | VALID | TABLE | T_ERROR_CODE_MAST | VALID
TABLE | WORKQUEUE_DECISION | VALID | TABLE | WORKQUEUE_DECISION | VALID
TABLE | WORK_GROUP | VALID | TABLE | WORK_GROUP | VALID
TABLE | WORK_QUEUE | VALID | TABLE | WORK_QUEUE | VALID
TABLE | WORK_TYPE_ALLOWED_OFFERING | VALID | TABLE | WORK_TYPE_ALLOWED_OFFERING | VALID
VIEW | PCMS_CODE_OFFERING_VIEW | VALID | VIEW | PCMS_CODE_OFFERING_VIEW | VALID

## B.1.AH Table Partitions (hidden)
ACTIVITY_HISTORY TABLE BEFORE AND AFTER CHANGE
Details | Before Change | Forecasted | After Change
DDL | CREATE TABLE NBNLOLO.ACTIVITY_HISTORY ( ACTIVITY_ID NUMBER(10), ACTIVITY_HISTORY_ID NUMBER(10), STATUS VARCHAR2(15 BYTE), NOTES VARCHAR2(4000 BYTE), CREATED_DATE TIMESTAMP(6), REVIEW_DATE DATE, REASON_CODE VARCHAR2(5 BYTE), ECS_USER_ID VARCHAR2(50 BYTE), REQUEST_ITEM_REVISION_ID NUMBER(10), REQUEST_REVISION_ID NUMBER(10), SERVICE_REVISION_ID NUMBER(10), REVIEW_ECS_USER_ID VARCHAR2(50 BYTE), REJECT_REASON_CODE VARCHAR2(5 BYTE), NOTIFICATION_FLAG VARCHAR2(1 BYTE), UPDATED_DATE DATE, DESCRIPTION VARCHAR2(100 BYTE), SP_VIEWABLE_FLAG VARCHAR2(1 BYTE), NOTES1 VARCHAR2(4000 BYTE) ) TABLESPACE LOLO_DATA_UL03 PCTUSED 0 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT ) LOGGING NOCOMPRESS NOCACHE NOPARALLEL MONITORING; | CREATE TABLE ACTIVITY_HISTORY ( ACTIVITY_ID NUMBER(10), ACTIVITY_HISTORY_ID NUMBER(10), STATUS VARCHAR2(15 BYTE), NOTES VARCHAR2(4000 BYTE), CREATED_DATE TIMESTAMP(6), REVIEW_DATE DATE, REASON_CODE VARCHAR2(5 BYTE), ECS_USER_ID VARCHAR2(50 BYTE), REQUEST_ITEM_REVISION_ID NUMBER(10), REQUEST_REVISION_ID NUMBER(10), SERVICE_REVISION_ID NUMBER(10), REVIEW_ECS_USER_ID VARCHAR2(50 BYTE), REJECT_REASON_CODE VARCHAR2(5 BYTE), NOTIFICATION_FLAG VARCHAR2(1 BYTE), UPDATED_DATE DATE, DESCRIPTION VARCHAR2(100 BYTE), SP_VIEWABLE_FLAG VARCHAR2(1 BYTE), NOTES1 VARCHAR2(4000 BYTE) ) TABLESPACE LOLO_DATA_UL03 PCTUSED 0 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 ) LOGGING PARTITION BY RANGE (CREATED_DATE) ( PARTITION ACTIVITY_HISTORY_201314_WK1 VALUES LESS THAN (TIMESTAMP' 2013-07-07 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK2 VALUES LESS THAN (TIMESTAMP' 2013-07-14 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK3 VALUES LESS THAN (TIMESTAMP' 2013-07-21 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK4 VALUES LESS THAN (TIMESTAMP' 2013-07-28 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK5 VALUES LESS THAN (TIMESTAMP' 2013-08-04 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK6 VALUES LESS THAN (TIMESTAMP' 2013-08-11 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK7 VALUES LESS THAN (TIMESTAMP' 2013-08-18 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK8 VALUES LESS THAN (TIMESTAMP' 2013-08-25 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK9 VALUES LESS THAN (TIMESTAMP' 2013-09-01 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK10 VALUES LESS THAN (TIMESTAMP' 2013-09-08 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK11 VALUES LESS THAN (TIMESTAMP' 2013-09-15 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK12 VALUES LESS THAN (TIMESTAMP' 2013-09-22 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK13 VALUES LESS THAN (TIMESTAMP' 2013-09-29 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK14 VALUES LESS THAN (TIMESTAMP' 2013-10-06 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTR | CREATE TABLE ACTIVITY_HISTORY ( ACTIVITY_ID NUMBER(10), ACTIVITY_HISTORY_ID NUMBER(10), STATUS VARCHAR2(15 BYTE), NOTES VARCHAR2(4000 BYTE), CREATED_DATE TIMESTAMP(6), REVIEW_DATE DATE, REASON_CODE VARCHAR2(5 BYTE), ECS_USER_ID VARCHAR2(50 BYTE), REQUEST_ITEM_REVISION_ID NUMBER(10), REQUEST_REVISION_ID NUMBER(10), SERVICE_REVISION_ID NUMBER(10), REVIEW_ECS_USER_ID VARCHAR2(50 BYTE), REJECT_REASON_CODE VARCHAR2(5 BYTE), NOTIFICATION_FLAG VARCHAR2(1 BYTE), UPDATED_DATE DATE, DESCRIPTION VARCHAR2(100 BYTE), SP_VIEWABLE_FLAG VARCHAR2(1 BYTE), NOTES1 VARCHAR2(4000 BYTE) ) TABLESPACE LOLO_DATA_UL03 PCTUSED 0 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 ) LOGGING PARTITION BY RANGE (CREATED_DATE) ( PARTITION ACTIVITY_HISTORY_201314_WK1 VALUES LESS THAN (TIMESTAMP' 2013-07-07 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK2 VALUES LESS THAN (TIMESTAMP' 2013-07-14 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK3 VALUES LESS THAN (TIMESTAMP' 2013-07-21 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK4 VALUES LESS THAN (TIMESTAMP' 2013-07-28 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK5 VALUES LESS THAN (TIMESTAMP' 2013-08-04 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK6 VALUES LESS THAN (TIMESTAMP' 2013-08-11 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK7 VALUES LESS THAN (TIMESTAMP' 2013-08-18 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK8 VALUES LESS THAN (TIMESTAMP' 2013-08-25 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK9 VALUES LESS THAN (TIMESTAMP' 2013-09-01 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK10 VALUES LESS THAN (TIMESTAMP' 2013-09-08 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK11 VALUES LESS THAN (TIMESTAMP' 2013-09-15 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK12 VALUES LESS THAN (TIMESTAMP' 2013-09-22 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK13 VALUES LESS THAN (TIMESTAMP' 2013-09-29 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED BUFFER_POOL DEFAULT ), PARTITION ACTIVITY_HISTORY_201314_WK14 VALUES LESS THAN (TIMESTAMP' 2013-10-06 00:00:00') LOGGING NOCOMPRESS TABLESPACE LOLO_DATA_UL03 PCTFREE 10 INITRANS 1 MAXTR
INDEXES | XPKACTIVITY_HISTORY | ACTIVITY_HISTORY_PK | ACTIVITY_HISTORY_PK
| CREATED_DATE_IDX | CREATED_DATE_IDX | CREATED_DATE_IDX
| SP_VIEWABLE_FLAG_IDX | SP_VIEWABLE_FLAG_IDX | SP_VIEWABLE_FLAG_IDX
| REQUEST_REVISION_ID_AH_IDX | REQUEST_REVISION_ID_AH_IDX | REQUEST_REVISION_ID_AH_IDX
| ACTIVITY_ID_IDX | ACTIVITY_ID_IDX | ACTIVITY_ID_IDX
| REQUEST_REV_IDX | REQUEST_REV_IDX | REQUEST_REV_IDX
| AH_UPDATED_DATE_IDX | AH_UPDATED_DATE_IDX | AH_UPDATED_DATE_IDX
CONSTRAINTS | XPKACTIVITY_HISTORY | ACTIVITY_HISTORY_PK | ACTIVITY_HISTORY_PK
ROWCOUNT | 24014412 | 24014412 | 24014412
PARENT TABLE | ACTIVITY | ACTIVITY | ACTIVITY
CHILD TABLE | Nill | Nill | Nill
Forecasted Partiions After Change |  |  | Actual Partiions After Change
PARTITION NAME | HIGH VALUE | ROWCOUNT | ROWCOUNT
ACTIVITY_HISTORY_201314_WK1 | 2013-07-07:00:00:00 | 2054771 | 2054771
ACTIVITY_HISTORY_201314_WK2 | 2013-07-14:00:00:00 | 860908 | 860908
ACTIVITY_HISTORY_201314_WK3 | 2013-07-21:00:00:00 | 937222 | 937222
ACTIVITY_HISTORY_201314_WK4 | 2013-07-28:00:00:00 | 752958 | 752958
ACTIVITY_HISTORY_201314_WK5 | 2013-08-04:00:00:00 | 1200725 | 1200725
ACTIVITY_HISTORY_201314_WK6 | 2013-08-11:00:00:00 | 1069580 | 1069580
ACTIVITY_HISTORY_201314_WK7 | 2013-08-18:00:00:00 | 1103165 | 1103165
ACTIVITY_HISTORY_201314_WK8 | 2013-08-25:00:00:00 | 1127893 | 1127893
ACTIVITY_HISTORY_201314_WK9 | 2013-09-01:00:00:00 | 1127775 | 1127775
ACTIVITY_HISTORY_201314_WK10 | 2013-09-08:00:00:00 | 977955 | 977955
ACTIVITY_HISTORY_201314_WK11 | 2013-09-15:00:00:00 | 937413 | 937413
ACTIVITY_HISTORY_201314_WK12 | 2013-09-22:00:00:00 | 1041034 | 1041034
ACTIVITY_HISTORY_201314_WK13 | 2013-09-29:00:00:00 | 1014838 | 1014838
ACTIVITY_HISTORY_201314_WK14 | 2013-10-06:00:00:00 | 944785 | 944785
ACTIVITY_HISTORY_201314_WK15 | 2013-10-13:00:00:00 | 921872 | 921872
ACTIVITY_HISTORY_201314_WK16 | 2013-10-20:00:00:00 | 945123 | 945123
ACTIVITY_HISTORY_201314_WK17 | 2013-10-27:00:00:00 | 964367 | 964367
ACTIVITY_HISTORY_201314_WK18 | 2013-11-03:00:00:00 | 1118742 | 1118742
ACTIVITY_HISTORY_201314_WK19 | 2013-11-10:00:00:00 | 1488171 | 1488171
ACTIVITY_HISTORY_201314_WK20 | 2013-11-17:00:00:00 | 1063352 | 1063352
ACTIVITY_HISTORY_201314_WK21 | 2013-11-24:00:00:00 | 1045803 | 1045803
ACTIVITY_HISTORY_201314_WK22 | 2013-12-01:00:00:00 | 1315960 | 1315960
ACTIVITY_HISTORY_201314_WK23 | 2013-12-08:00:00:00
ACTIVITY_HISTORY_201314_WK24 | 2013-12-15:00:00:00
ACTIVITY_HISTORY_201314_WK25 | 2013-12-22:00:00:00
ACTIVITY_HISTORY_201314_WK26 | 2013-12-29:00:00:00
ACTIVITY_HISTORY_201314_WK27 | 2014-01-05:00:00:00
ACTIVITY_HISTORY_201314_WK28 | 2014-01-12:00:00:00
ACTIVITY_HISTORY_201314_WK29 | 2014-01-19:00:00:00
ACTIVITY_HISTORY_201314_WK30 | 2014-01-26:00:00:00
ACTIVITY_HISTORY_201314_WK31 | 2014-02-02:00:00:00
ACTIVITY_HISTORY_201314_WK32 | 2014-02-09:00:00:00
ACTIVITY_HISTORY_201314_WK33 | 2014-02-16:00:00:00
ACTIVITY_HISTORY_201314_WK34 | 2014-02-23:00:00:00
ACTIVITY_HISTORY_201314_WK35 | 2014-03-02:00:00:00
ACTIVITY_HISTORY_201314_WK36 | 2014-03-09:00:00:00
ACTIVITY_HISTORY_201314_WK37 | 2014-03-16:00:00:00
ACTIVITY_HISTORY_201314_WK38 | 2014-03-23:00:00:00
ACTIVITY_HISTORY_201314_WK39 | 2014-03-30:00:00:00
ACTIVITY_HISTORY_201314_WK40 | 2014-04-06:00:00:00
ACTIVITY_HISTORY_201314_WK41 | 2014-04-13:00:00:00
ACTIVITY_HISTORY_201314_WK42 | 2014-04-20:00:00:00
ACTIVITY_HISTORY_201314_WK43 | 2014-04-27:00:00:00
ACTIVITY_HISTORY_201314_WK44 | 2014-05-04:00:00:00
ACTIVITY_HISTORY_201314_WK45 | 2014-05-11:00:00:00
ACTIVITY_HISTORY_201314_WK46 | 2014-05-18:00:00:00
ACTIVITY_HISTORY_201314_WK47 | 2014-05-25:00:00:00
ACTIVITY_HISTORY_201314_WK48 | 2014-06-01:00:00:00
ACTIVITY_HISTORY_201314_WK49 | 2014-06-08:00:00:00
ACTIVITY_HISTORY_201314_WK50 | 2014-06-15:00:00:00
ACTIVITY_HISTORY_201314_WK51 | 2014-06-22:00:00:00
ACTIVITY_HISTORY_201314_WK52 | 2014-07-01:00:00:00

## B.2.Appln TablConstraint Status (hidden)
Application Object Constraint Status Details | [5 empty] | Disabled Constraints | [5 empty] | Application Object Constraint Summary
Before Rename |  |  | After Rename |  |  | Before Change |  | Forecasted |  | After Change |  | Before Rename |  |  | After Rename
CONSTRAINT_TYPE | CONSTRAINT_NAME | STATUS | CONSTRAINT_TYPE | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_TYPE | STATUS | No.Cons | CONSTRAINT_TYPE | STATUS | No.Cons
CK | AUST_STATE_CK | ENABLED | CK | WORK_QUEUE_DELFLG_CK | ENABLED | CHANGE_REQUEST_FK | DISABLED | CHANGE_REQUEST_FK | DISABLED | CHANGE_REQUEST_FK | DISABLED | CK | ENABLED | 16 | CK | ENABLED | 16
CK | EQUIPMENT_CK | ENABLED | CK | POP_RULE_CONDITION_CK | ENABLED | MOP_STATUS_FK | DISABLED | MOP_STATUS_FK | DISABLED | MOP_STATUS_FK | DISABLED | FK | DISABLED | 12 | FK | DISABLED | 12
CK | EQUIPMENT_DELVMD_CK | ENABLED | CK | SYS_C0031655 | ENABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED | FK | ENABLED | 31 | FK | ENABLED | 32
CK | POP_RULE_ACTION_CK | ENABLED | CK | SYS_C0031656 | ENABLED | PARENT_MESSAGE_ID_FK | DISABLED | PARENT_MESSAGE_ID_FK | DISABLED | PARENT_MESSAGE_ID_FK | DISABLED | PK | ENABLED | 93 | PK | ENABLED | 94
CK | POP_RULE_CONDITION_CK | ENABLED | CK | AUST_STATE_CK | ENABLED | PARENT_SERV_OFF_FK | DISABLED | PARENT_SERV_OFF_FK | DISABLED | PARENT_SERV_OFF_FK | DISABLED | UK | ENABLED | 2 | UK | ENABLED | 2
CK | POP_RULE_CONDN_RULE_CONDN_CK | ENABLED | CK | WORK_TYPE_CATEGORY_CK | ENABLED | REASON_CODE_FK | DISABLED | REASON_CODE_FK | DISABLED | REASON_CODE_FK | DISABLED | Total |  | 154 | Total |  | 156
CK | SP_SHORT_NAME_CK | ENABLED | CK | SYS_C0032034 | ENABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED |  | Diff | 2
CK | SYS_C0031655 | ENABLED | CK | POP_RULE_CONDN_RULE_CONDN_CK | ENABLED | RQST_STATUS_STATUSHIST_FK | DISABLED | RQST_STATUS_STATUSHIST_FK | DISABLED | RQST_STATUS_STATUSHIST_FK | DISABLED
CK | SYS_C0031656 | ENABLED | CK | WORK_TYPE_CATEGORY_DELFLG_CK | ENABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED
CK | SYS_C0032034 | ENABLED | CK | SYS_C0032036 | ENABLED | SP_WORK_TYPE_AUTH_FK | DISABLED | SP_WORK_TYPE_AUTH_FK | DISABLED | SP_WORK_TYPE_AUTH_FK | DISABLED
CK | SYS_C0032036 | ENABLED | CK | SYS_C0032037 | ENABLED | SPOFFERINGASSOC_ATT_FK | DISABLED | SPOFFERINGASSOC_ATT_FK | DISABLED | SPOFFERINGASSOC_ATT_FK | DISABLED
CK | SYS_C0032037 | ENABLED | CK | POP_RULE_ACTION_CK | ENABLED | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | WORKTYPE_CAT_WORKTYPE_FK | DISABLED
CK | WORK_QUEUE_CK | ENABLED | CK | EQUIPMENT_CK | ENABLED
CK | WORK_QUEUE_DELFLG_CK | ENABLED | CK | SP_SHORT_NAME_CK | ENABLED | Note : After completion of task A, all constraints are named with standared names without oracle system generated names
CK | WORK_TYPE_CATEGORY_CK | ENABLED | CK | EQUIPMENT_DELVMD_CK | ENABLED
CK | WORK_TYPE_CATEGORY_DELFLG_CK | ENABLED | CK | WORK_QUEUE_CK | ENABLED
FK | ACTIVITY_HISTORY_FK | ENABLED | FK | FK_QA_WORK_QUEUE_1 | ENABLED | CK - Check |  | Note : SYS_C00nnnn Reprecents NOT NULL
FK | ASSIGNMENT_HISTORY_FK | ENABLED | FK | ASSIGNMENT_HISTORY_FK | ENABLED | FK - Reference |  | After Rename , total count increased by two due to existannce of OLD table with two constraints
FK | CHANGE_REQUEST_FK | DISABLED | FK | ACTIVITY_HISTORY_FK | ENABLED | PK - Primary Key
FK | CHARAC_ASSOC_ID_FK | ENABLED | FK | AHOLD_HISTORY_FK | ENABLED | UK - Unique Key
FK | CHARAC_PARAM_ASSOC_ID_FK | ENABLED | FK | OFFER_ATTT_FK | ENABLED
FK | CHARAC_PARAM_ID_FK | ENABLED | FK | LOLO_MSQ_ATT_ATTRIBUTE_FK | ENABLED
FK | CHARACTERISTIC_FK | ENABLED | FK | SPOFFERINGASSOC_ATT_FK | DISABLED
FK | CHARACTERISTIC_FK_01 | ENABLED | FK | POSTCODE_LOCALITY_FK | ENABLED
FK | EQUIPMENT_FK | ENABLED | FK | PARENT_MESSAGE_ID_FK | DISABLED
FK | FK_QA_WORK_QUEUE_1 | ENABLED | FK | OFFERTYPE_OFFERING_OT_FK | DISABLED
FK | FK_REQ_RSTAT_01 | ENABLED | FK | CHANGE_REQUEST_FK | DISABLED
FK | FNN_REL_RSP_REQSTITAM_FK | ENABLED | FK | REASON_CODE_FK | DISABLED
FK | FNN_VLD_RSP_REQSTITAM_FK | ENABLED | FK | RQSTITEM_REASON_CODE_FK | ENABLED
FK | LOLO_MSQ_ATT_ATTRIBUTE_FK | ENABLED | FK | RI_STATUSHIST_RI_STATUS_FK | DISABLED
FK | MOP_STATUS_FK | DISABLED | FK | REQUEST_ITEM_FK | ENABLED
FK | OFFER_ATTT_FK | ENABLED | FK | SP_CONACT_ID_FK | ENABLED
FK | OFFERING_PCMS_CODE_FK | ENABLED | FK | RQST_STATUS_STATUSHIST_FK | DISABLED
FK | OFFERTYPE_OFFERING_OT_FK | DISABLED | FK | FK_REQ_RSTAT_01 | ENABLED
FK | PARENT_MESSAGE_ID_FK | DISABLED | FK | PARENT_SERV_OFF_FK | DISABLED
FK | PARENT_SERV_OFF_FK | DISABLED | FK | MOP_STATUS_FK | DISABLED
FK | PCO_OFFID_FK | ENABLED | FK | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED
FK | PCO_PRDID_FK | ENABLED | FK | SRGROUP_SP_GROUP_FK | ENABLED
FK | POSTCODE_LOCALITY_FK | ENABLED | FK | WTAO_WTID_FK | ENABLED
FK | QUEUE_ASSIGNMENT_FK | ENABLED | FK | SP_WORK_TYPE_AUTH_FK | DISABLED
FK | REASON_CODE_FK | DISABLED | FK | REQUESTITAM_WORKTYPE_FK | ENABLED
FK | REQUEST_FK | ENABLED | FK | WORKTYPE_CAT_WORKTYPE_FK | DISABLED
FK | REQUEST_ITEM_FK | ENABLED | FK | USER_SPD_FK | ENABLED
FK | REQUESTITAM_WORKTYPE_FK | ENABLED | FK | REQUEST_FK | ENABLED
FK | RI_STATUSHIST_RI_STATUS_FK | DISABLED | FK | QUEUE_ASSIGNMENT_FK | ENABLED
FK | RQST_RQSTITEM_FK | ENABLED | FK | USERS_FK | ENABLED
FK | RQST_STATUS_STATUSHIST_FK | DISABLED | FK | FNN_REL_RSP_REQSTITAM_FK | ENABLED
FK | RQSTITAM_BUNDLE_FK | ENABLED | FK | FNN_VLD_RSP_REQSTITAM_FK | ENABLED
FK | RQSTITEM_REASON_CODE_FK | ENABLED | FK | RQST_RQSTITEM_FK | ENABLED
FK | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | FK | PCO_PRDID_FK | ENABLED
FK | SP_CONACT_ID_FK | ENABLED | FK | OFFERING_PCMS_CODE_FK | ENABLED
FK | SP_WORK_TYPE_AUTH_FK | DISABLED | FK | PCO_OFFID_FK | ENABLED
FK | SPOFFERINGASSOC_ATT_FK | DISABLED | FK | WTAO_OFFID_FK | ENABLED
FK | SRGROUP_SP_GROUP_FK | ENABLED | FK | EQUIPMENT_FK | ENABLED
FK | USER_SPD_FK | ENABLED | FK | CHARAC_PARAM_ASSOC_ID_FK | ENABLED
FK | USERS_FK | ENABLED | FK | CHARAC_PARAM_ID_FK | ENABLED
FK | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | FK | CHARAC_ASSOC_ID_FK | ENABLED
FK | WTAO_OFFID_FK | ENABLED | FK | CHARACTERISTIC_FK_01 | ENABLED
FK | WTAO_WTID_FK | ENABLED | FK | RQSTITAM_BUNDLE_FK | ENABLED
PK | ACTIVITY_HISTORY_PK | ENABLED | FK | CHARACTERISTIC_FK | ENABLED
PK | ACTIVITY_PK | ENABLED | PK | EAST_AXIS_STRT_TYPE_SUFFIX_PK | ENABLED
PK | AMEND_LOCK_PK | ENABLED | PK | LOLO_MSQ_SRV_MAP_PK | ENABLED
PK | ASSIGNMENT_HISTORY_PK | ENABLED | PK | INSTANT_HOTLINE_PK | ENABLED
PK | ATTRIBUTE_PK | ENABLED | PK | DIRECTORY_DETAILS_PK | ENABLED
PK | AUST_STATE_PK | ENABLED | PK | CHARAC_PARAM_ASSOCIATION_PK | ENABLED
PK | BPM_USER_PK | ENABLED | PK | CHARAC_PARAMETER_PK | ENABLED
PK | BUNDLE_PRODUCT_CLASS_PK | ENABLED | PK | CHARACTERISTIC_PK | ENABLED
PK | CCA_PK | ENABLED | PK | FWOM_TIME_SLOT_PK | ENABLED
PK | CHANGE_REQUEST_PK | ENABLED | PK | FULLY_CONFIG_SQ_RESPONSE_PK | ENABLED
PK | CHARAC_ASSOCIATION_PK | ENABLED | PK | ENTRY_MEDIUM_PK | ENABLED
PK | CHARAC_PARAM_ASSOCIATION_PK | ENABLED | PK | EAST_AXIS_STREET_TYPE_PK | ENABLED
PK | CHARAC_PARAMETER_PK | ENABLED | PK | EAST_AXIS_ADDRESS_TYPE_PK | ENABLED
PK | CHARACTERISTIC_PK | ENABLED | PK | EAST_ADDRESS_TYPE_PK | ENABLED
PK | COMPLEX_REQUEST_ITEM_PK | ENABLED | PK | CUSTOMER_TYPE_PK | ENABLED
PK | CUSTOMER_COURTESY_TITLE_PK | ENABLED | PK | CUSTOMER_COURTESY_TITLE_PK | ENABLED
PK | CUSTOMER_TYPE_PK | ENABLED | PK | ACTIVITY_HISTORY_PK | ENABLED
PK | DIRECTORY_DETAILS_PK | ENABLED | PK | PCMS_CODE_PK | ENABLED
PK | EAST_ADDRESS_TYPE_PK | ENABLED | PK | OFFERING_OFFERING_TYPE_PK | ENABLED
PK | EAST_AXIS_ADDRESS_TYPE_PK | ENABLED | PK | EQUIPMENT_TYPE_PK | ENABLED
PK | EAST_AXIS_STREET_TYPE_PK | ENABLED | PK | EQUIPMENT_PK | ENABLED
PK | EAST_AXIS_STRT_TYPE_SUFFIX_PK | ENABLED | PK | EAST_SUB_ADDRESS_TYPE_PK | ENABLED
PK | EAST_SUB_ADDRESS_TYPE_PK | ENABLED | PK | CHANGE_REQUEST_PK | ENABLED
PK | ENTRY_MEDIUM_PK | ENABLED | PK | AUST_STATE_PK | ENABLED
PK | EQUIPMENT_PK | ENABLED | PK | SP_CIDN_PK | ENABLED
PK | EQUIPMENT_TYPE_PK | ENABLED | PK | SERVICE_PROVIDER_PK | ENABLED
PK | ERROR_MAPPING_PK | ENABLED | PK | ASSIGNMENT_HISTORY_PK | ENABLED
PK | FNN_RELOCATION_RESPONSE_PK | ENABLED | PK | CHARAC_ASSOCIATION_PK | ENABLED
PK | FNN_VALIDATION_RESPONSE_PK | ENABLED | PK | ATTRIBUTE_PK | ENABLED
PK | FULLY_CONFIG_SQ_RESPONSE_PK | ENABLED | PK | WORK_TYPE_ALLOWED_OFFERING_PK | ENABLED
PK | FWOM_TIME_SLOT_PK | ENABLED | PK | WORK_TYPE_PK | ENABLED
PK | GENERAL_REFERENCE_PK | ENABLED | PK | ACTIVITY_PK | ENABLED
PK | INSTANT_HOTLINE_PK | ENABLED | PK | AHOLD_HISTORY_PK | ENABLED
PK | LOLO_MSQ_ATT_MAP_PK | ENABLED | PK | WORK_TYPE_CATEGORY_PK | ENABLED
PK | LOLO_MSQ_SRV_MAP_PK | ENABLED | PK | WORKQUEUE_DECISION_PK | ENABLED
PK | MESSAGE_ID_PK | ENABLED | PK | TIME_SLOT_PK | ENABLED
PK | MOP_ORDER_ITEM_NOTIFICATION_PK | ENABLED | PK | CCA_PK | ENABLED
PK | MOP_ORDER_PK | ENABLED | PK | WORK_QUEUE_PK | ENABLED
PK | MOP_STATUS_PK | ENABLED | PK | WORK_TYPE_OFFERING_PK | ENABLED
PK | NOTES_PK | ENABLED | PK | SP_WORK_TYPE_AUTH_PK | ENABLED
PK | OFFERING_ATTRIBUTE_PK | ENABLED | PK | SPOFFERINGASSOC_PK | ENABLED
PK | OFFERING_OFFERING_TYPE_PK | ENABLED | PK | WORK_GROUP_PK | ENABLED
PK | OFFERING_PK | ENABLED | PK | SP_GROUP_PK | ENABLED
PK | OFFERING_TYPE_PK | ENABLED | PK | COMPLEX_REQUEST_ITEM_PK | ENABLED
PK | PCMS_CODE_PK | ENABLED | PK | SERVICE_STATUS_HISTORY_PK | ENABLED
PK | PLAN_PK | ENABLED | PK | TARIFF_PK | ENABLED
PK | POP_LOCK_PK | ENABLED | PK | USER_PK | ENABLED
PK | POP_RULE_ACTION_PK | ENABLED | PK | SERVICE_OFFERING_PK | ENABLED
PK | POP_RULE_BINDING_PK | ENABLED | PK | SERVICE_IDENTIFIER_PK | ENABLED
PK | POP_RULE_CONDITION_PK | ENABLED | PK | SERVICEABILITYRESPONSE_PK | ENABLED
PK | POSTCODE_LOCALITY_PK | ENABLED | PK | SELECTED_PRODUCT_PK | ENABLED
PK | PRODUCT_CLASS_PK | ENABLED | PK | SP_SP_GROUP_PK | ENABLED
PK | PROGRAMMING_PK | ENABLED | PK | RULECONDITION_PK | ENABLED
PK | PSTS_SERVICE_PK | ENABLED | PK | RULEACTION_PK | ENABLED
PK | QUEUE_ASSIGNMENT_PK | ENABLED | PK | SP_CONTACT_PK | ENABLED
PK | QUEUE_CRITERIA_PK | ENABLED | PK | SP_SHORT_NAME_PK | ENABLED
PK | REASON_CODE_PK | ENABLED | PK | REQUEST_SPCONTACT_PK | ENABLED
PK | REASON_PK | ENABLED | PK | REQUEST_STATUS_HISTORY_PK | ENABLED
PK | REQUEST_ITEM_PK | ENABLED | PK | REQUEST_STATUS_PK | ENABLED
PK | REQUEST_ITEM_STATUS_HISTORY_PK | ENABLED | PK | SERVICE_STATUS_PK | ENABLED
PK | REQUEST_ITEM_STATUS_PK | ENABLED | PK | REQUEST_PK | ENABLED
PK | REQUEST_PK | ENABLED | PK | SDDB_ATTRIBUTE_PK | ENABLED
PK | REQUEST_SPCONTACT_PK | ENABLED | PK | REQUEST_ITEM_STATUS_HISTORY_PK | ENABLED
PK | REQUEST_STATUS_HISTORY_PK | ENABLED | PK | REQUEST_ITEM_STATUS_PK | ENABLED
PK | REQUEST_STATUS_PK | ENABLED | PK | QUEUE_CRITERIA_PK | ENABLED
PK | RULEACTION_PK | ENABLED | PK | QUEUE_ASSIGNMENT_PK | ENABLED
PK | RULECONDITION_PK | ENABLED | PK | PRODUCT_CLASS_PK | ENABLED
PK | SDDB_ATTRIBUTE_PK | ENABLED | PK | REQUEST_ITEM_PK | ENABLED
PK | SELECTED_PRODUCT_PK | ENABLED | PK | POP_RULE_CONDITION_PK | ENABLED
PK | SERVICE_IDENTIFIER_PK | ENABLED | PK | POP_RULE_BINDING_PK | ENABLED
PK | SERVICE_NK_NUMBER_INVENTORY_PK | ENABLED | PK | POP_RULE_ACTION_PK | ENABLED
PK | SERVICE_OFFERING_PK | ENABLED | PK | AMEND_LOCK_PK | ENABLED
PK | SERVICE_PROVIDER_PK | ENABLED | PK | PSTS_SERVICE_PK | ENABLED
PK | SERVICE_STATUS_HISTORY_PK | ENABLED | PK | PROGRAMMING_PK | ENABLED
PK | SERVICE_STATUS_PK | ENABLED | PK | OFFERING_TYPE_PK | ENABLED
PK | SERVICEABILITYRESPONSE_PK | ENABLED | PK | REASON_PK | ENABLED
PK | SP_CIDN_PK | ENABLED | PK | OFFERING_PK | ENABLED
PK | SP_CONTACT_PK | ENABLED | PK | POSTCODE_LOCALITY_PK | ENABLED
PK | SP_GROUP_PK | ENABLED | PK | OFFERING_ATTRIBUTE_PK | ENABLED
PK | SP_SHORT_NAME_PK | ENABLED | PK | NOTES_PK | ENABLED
PK | SP_SP_GROUP_PK | ENABLED | PK | MOP_STATUS_PK | ENABLED
PK | SP_WORK_TYPE_AUTH_PK | ENABLED | PK | MESSAGE_ID_PK | ENABLED
PK | SPOFFERINGASSOC_PK | ENABLED | PK | SERVICE_NK_NUMBER_INVENTORY_PK | ENABLED
PK | TARIFF_PK | ENABLED | PK | POP_LOCK_PK | ENABLED
PK | TIME_SLOT_PK | ENABLED | PK | REASON_CODE_PK | ENABLED
PK | USER_PK | ENABLED | PK | LOLO_MSQ_ATT_MAP_PK | ENABLED
PK | WORK_GROUP_PK | ENABLED | PK | GENERAL_REFERENCE_PK | ENABLED
PK | WORK_QUEUE_PK | ENABLED | PK | MOP_ORDER_ITEM_NOTIFICATION_PK | ENABLED
PK | WORK_TYPE_ALLOWED_OFFERING_PK | ENABLED | PK | MOP_ORDER_PK | ENABLED
PK | WORK_TYPE_CATEGORY_PK | ENABLED | PK | FNN_VALIDATION_RESPONSE_PK | ENABLED
PK | WORK_TYPE_OFFERING_PK | ENABLED | PK | FNN_RELOCATION_RESPONSE_PK | ENABLED
PK | WORK_TYPE_PK | ENABLED | PK | ERROR_MAPPING_PK | ENABLED
PK | WORKQUEUE_DECISION_PK | ENABLED | PK | BUNDLE_PRODUCT_CLASS_PK | ENABLED
UK | RULEFLITER_UK1 | ENABLED | PK | PLAN_PK | ENABLED
UK | SPG_UK1 | ENABLED | PK | BPM_USER_PK | ENABLED
|  |  | UK | RULEFLITER_UK1 | ENABLED
|  |  | UK | SPG_UK1 | ENABLED
Note on S12: Vaikunda Moni: After Rename , total count increased by two due to existannce of OLD table with two constraints

## B.3.Appln Schema Object Status (hidden)
Application Schema Object Status | [5 empty] | Application Schema Object Status Summary
Before Change |  |  | After Change |  |  | Before Change |  |  | After Change
OBJECT_TYPE | OBJECT_NAME | STATUS | OBJECT_TYPE | OBJECT_NAME | STATUS | OBJECT_TYPE | STATUS | NO OBJS | OBJECT_TYPE | STATUS | NO OBJS
DATABASE_LINK | CAT | VALID | DATABASE_LINK | CAT | VALID | DATABASE_LINK | VALID | 3 | DATABASE_LINK | VALID | 3
DATABASE_LINK | LOLO | VALID | DATABASE_LINK | LOLO | VALID | FUNCTION | VALID | 5 | FUNCTION | VALID | 5
DATABASE_LINK | MYLOLOCAT | VALID | DATABASE_LINK | MYLOLOCAT | VALID | INDEX | VALID | 135 | INDEX | VALID | 142
FUNCTION | FN_APP_DATE | VALID | FUNCTION | FN_APP_DATE | VALID | LOB | VALID | 3 | LOB | VALID | 3
FUNCTION | GET_APP_REV_ID | VALID | FUNCTION | GET_APP_REV_ID | VALID | SEQUENCE | VALID | 9 | SEQUENCE | VALID | 9
FUNCTION | GET_FNN | VALID | FUNCTION | GET_FNN | VALID | SYNONYM | VALID | 13 | SYNONYM | VALID | 13
FUNCTION | GET_ORDER_NO | VALID | FUNCTION | GET_ORDER_NO | VALID | TABLE | VALID | 120 | TABLE | VALID | 121
FUNCTION | SQUIRREL_GET_ERROR_OFFSET | VALID | FUNCTION | SQUIRREL_GET_ERROR_OFFSET | VALID | VIEW | VALID | 1 | VIEW | VALID | 1
INDEX | ACTIVITY_ID_IDX | VALID | INDEX | ACTIVITY_HISTORY_PK | VALID | Total |  | 289 | Total |  | 297
INDEX | AH_UPDATED_DATE_IDX | VALID | INDEX | ACTIVITY_HISTORY_PK_OLD | VALID |  | Diff | 8
INDEX | APPOINTMENT_REQREVNID_IDX | VALID | INDEX | ACTIVITY_ID_IDX | VALID
INDEX | ASSIGNED_USER_IDX | VALID | INDEX | ACTIVITY_ID_IDX_OLD | VALID |  | Note : As the rename old table ACTIVITY_HISTORY_OLD and its indexes exists
INDEX | BPM_USER_PK | VALID | INDEX | ACTIVITY_PK | VALID
INDEX | BUNDLE_PRODUCT_CLASS_PK | VALID | INDEX | AH_UPDATED_DATE_IDX | VALID
INDEX | CRD_APPMT_REVNID_IDX | VALID | INDEX | AH_UPDATED_DATE_IDX_OLD | VALID
INDEX | CREATED_DATE_IDX | VALID | INDEX | AMEND_LOCK_PK | VALID
INDEX | ECS_USER | VALID | INDEX | APPOINTMENT_REQREVNID_IDX | VALID
INDEX | ECS_USER_IDX | VALID | INDEX | ASSIGNED_USER_IDX | VALID
INDEX | ERROR_MAPPING_PK | VALID | INDEX | ASSIGNMENT_HISTORY_PK | VALID
INDEX | FK_ASSH_REQ_01 | VALID | INDEX | ATTRIBUTE_PK | VALID
INDEX | FK_ASSH_USERS_01 | VALID | INDEX | AUST_STATE_PK | VALID
INDEX | FK_ASSH_WQ_01 | VALID | INDEX | BPM_USER_PK | VALID
INDEX | FK_CRIT_REQ_01 | VALID | INDEX | BUNDLE_PRODUCT_CLASS_PK | VALID
INDEX | FK_EQUIP_ETYP_01 | VALID | INDEX | CCA_PK | VALID
INDEX | FK_EQUIP_RITM_01 | VALID | INDEX | CHANGE_REQUEST_PK | VALID
INDEX | FK_QA_WG_01 | VALID | INDEX | CHARAC_ASSOCIATION_PK | VALID
INDEX | FK_QA_WQ_01 | VALID | INDEX | CHARAC_PARAM_ASSOCIATION_PK | VALID
INDEX | FK_WG_WG_01 | VALID | INDEX | CHARAC_PARAMETER_PK | VALID
INDEX | FNN_RELOCATION_RESPONSE_PK | VALID | INDEX | CHARACTERISTIC_PK | VALID
INDEX | FNN_VALDN_RESP_REVID_IDX | VALID | INDEX | COMPLEX_REQUEST_ITEM_PK | VALID
INDEX | FNN_VALIDATION_RESPONSE_PK | VALID | INDEX | CRD_APPMT_REVNID_IDX | VALID
INDEX | GENERAL_REFERENCE_PK | VALID | INDEX | CRD_PK | VALID
INDEX | MESSAGE_ID_PK | VALID | INDEX | CREATED_DATE_IDX | VALID
INDEX | NK_FNN | VALID | INDEX | CREATED_DATE_IDX_OLD | VALID
INDEX | OFFERING_PK | VALID | INDEX | CUSTOMER_COURTESY_TITLE_PK | VALID
INDEX | PK_ASSH | VALID | INDEX | CUSTOMER_TYPE_PK | VALID
INDEX | PK_ASTATE | VALID | INDEX | DIRECTORY_DETAILS_PK | VALID
INDEX | PK_CIDN | VALID | INDEX | EAST_ADDRESS_TYPE_PK | VALID
INDEX | PK_CREQ | VALID | INDEX | EAST_AXIS_ADDRESS_TYPE_PK | VALID
INDEX | PK_CRIT | VALID | INDEX | EAST_AXIS_STREET_TYPE_PK | VALID
INDEX | PK_EAST_SUB_ADDRESS_TYPE | VALID | INDEX | EAST_AXIS_STRT_TYPE_SUFFIX_PK | VALID
INDEX | PK_EQUIP | VALID | INDEX | EAST_SUB_ADDRESS_TYPE_PK | VALID
INDEX | PK_ETYP | VALID | INDEX | ECS_USER | VALID
INDEX | PK_OOTY | VALID | INDEX | ECS_USER_IDX | VALID
INDEX | PK_OT | VALID | INDEX | ENTRY_MEDIUM_PK | VALID
INDEX | PK_PCMS_CODE | VALID | INDEX | EQUIPMENT_PK | VALID
INDEX | PK_PROG | VALID | INDEX | EQUIPMENT_TYPE_PK | VALID
INDEX | PK_PSER | VALID | INDEX | ERROR_MAPPING_PK | VALID
INDEX | PK_QA | VALID | INDEX | FK_ASSH_REQ_01 | VALID
INDEX | PK_QC | VALID | INDEX | FK_ASSH_USERS_01 | VALID
INDEX | PK_RIS | VALID | INDEX | FK_ASSH_WQ_01 | VALID
INDEX | PK_RISH | VALID | INDEX | FK_CRIT_REQ_01 | VALID
INDEX | PK_RS | VALID | INDEX | FK_EQUIP_ETYP_01 | VALID
INDEX | PK_RSH | VALID | INDEX | FK_EQUIP_RITM_01 | VALID
INDEX | PK_SN | VALID | INDEX | FK_QA_WG_01 | VALID
INDEX | PK_SPC | VALID | INDEX | FK_QA_WQ_01 | VALID
INDEX | PK_SPG | VALID | INDEX | FK_WG_WG_01 | VALID
INDEX | PK_SPWTA | VALID | INDEX | FNN_RELOCATION_RESPONSE_PK | VALID
INDEX | PK_WG | VALID | INDEX | FNN_VALDN_RESP_REVID_IDX | VALID
INDEX | PK_WQ | VALID | INDEX | FNN_VALIDATION_RESPONSE_PK | VALID
INDEX | PK_WTCAT | VALID | INDEX | FULLY_CONFIG_SQ_RESPONSE_PK | VALID
INDEX | PLAN_PK | VALID | INDEX | FWOM_TIME_SLOT_PK | VALID
INDEX | POP_RULE_ACTION_PK | VALID | INDEX | GENERAL_REFERENCE_PK | VALID
INDEX | POP_RULE_BINDING_PK | VALID | INDEX | INSTANT_HOTLINE_PK | VALID
INDEX | POP_RULE_CONDITION_PK | VALID | INDEX | LOLO_MSQ_ATT_MAP_PK | VALID
INDEX | PRODUCT_CLASS_PK | VALID | INDEX | LOLO_MSQ_SRV_MAP_PK | VALID
INDEX | REASON_CODE_PK | VALID | INDEX | MESSAGE_ID_PK | VALID
INDEX | REQ_ID_IDX | VALID | INDEX | MOP_ORDER_ITEM_NOTIFICATION_PK | VALID
INDEX | REQ_ITEM_HISTORY_IDX | VALID | INDEX | MOP_ORDER_PK | VALID
INDEX | REQ_ITEM_STATUS_IDX | VALID | INDEX | MOP_STATUS_PK | VALID
INDEX | REQ_REVISION_IDX | VALID | INDEX | NK_FNN | VALID
INDEX | REQ_STATUS_CODE_IDX | VALID | INDEX | NOTES_PK | VALID
INDEX | REQ_STATUS_DESC_IDX | VALID | INDEX | OFFERING_ATTRIBUTE_PK | VALID
INDEX | REQ_STATUS_IDX | VALID | INDEX | OFFERING_OFFERING_TYPE_PK | VALID
INDEX | REQUEST_ID_PK | VALID | INDEX | OFFERING_PK | VALID
INDEX | REQUEST_ITEM_REVISION_ID_IDX | VALID | INDEX | OFFERING_TYPE_PK | VALID
INDEX | REQUEST_PK | VALID | INDEX | PCMS_CODE_PK | VALID
INDEX | REQUEST_REV_IDX | VALID | INDEX | PLAN_PK | VALID
INDEX | REQUEST_REVISDTSTAMP_IDX | VALID | INDEX | POP_LOCK_PK | VALID
INDEX | REQUEST_REVISION_ID_AH_IDX | VALID | INDEX | POP_RULE_ACTION_PK | VALID
INDEX | REQUEST_REVISION_ID_IDX | VALID | INDEX | POP_RULE_BINDING_PK | VALID
INDEX | REQUEST_SPCONTACT_PK | VALID | INDEX | POP_RULE_CONDITION_PK | VALID
INDEX | REVISION_IDX | VALID | INDEX | POSTCODE_LOCALITY_PK | VALID
INDEX | RULEACTION_PK | VALID | INDEX | PRODUCT_CLASS_PK | VALID
INDEX | RULECONDITION_PK | VALID | INDEX | PROGRAMMING_PK | VALID
INDEX | RULEFLITER_UK1 | VALID | INDEX | PSTS_SERVICE_PK | VALID
INDEX | SELECTED_PRODUCT_PK | VALID | INDEX | QUEUE_ASSIGNMENT_PK | VALID
INDEX | SERVICE_IDENTIFIER_PK | VALID | INDEX | QUEUE_CRITERIA_PK | VALID
INDEX | SERVICE_OFFERING_PK | VALID | INDEX | REASON_CODE_PK | VALID
INDEX | SERVICE_PROVIDER_PK | VALID | INDEX | REASON_PK | VALID
INDEX | SERVICE_STATUS_HISTORY_PK | VALID | INDEX | REQ_ID_IDX | VALID
INDEX | SERVICEABILITYRESPONSE_PK | VALID | INDEX | REQ_ITEM_HISTORY_IDX | VALID
INDEX | SP_INDEX | VALID | INDEX | REQ_ITEM_STATUS_IDX | VALID
INDEX | SP_VIEWABLE_FLAG_IDX | VALID | INDEX | REQ_REVISION_IDX | VALID
INDEX | SPOFFERINGASSOC_PK | VALID | INDEX | REQ_STATUS_CODE_IDX | VALID
INDEX | SYS_C0031561 | VALID | INDEX | REQ_STATUS_DESC_IDX | VALID
INDEX | SYS_C0031565 | VALID | INDEX | REQ_STATUS_IDX | VALID
INDEX | SYS_C0031567 | VALID | INDEX | REQUEST_ID_PK | VALID
INDEX | SYS_C0031569 | VALID | INDEX | REQUEST_ITEM_PK | VALID
INDEX | SYS_C0031571 | VALID | INDEX | REQUEST_ITEM_REVISION_ID_IDX | VALID
INDEX | SYS_C0031579 | VALID | INDEX | REQUEST_ITEM_STATUS_HISTORY_PK | VALID
INDEX | SYS_C0031611 | VALID | INDEX | REQUEST_ITEM_STATUS_PK | VALID
INDEX | SYS_C0031615 | VALID | INDEX | REQUEST_PK | VALID
INDEX | SYS_C0031617 | VALID | INDEX | REQUEST_REV_IDX | VALID
INDEX | SYS_C0031639 | VALID | INDEX | REQUEST_REV_IDX_OLD | VALID
INDEX | SYS_C0031694 | VALID | INDEX | REQUEST_REVISDTSTAMP_IDX | VALID
INDEX | SYS_C0038738 | VALID | INDEX | REQUEST_REVISION_ID_AH_IDX | VALID
INDEX | SYS_IL0000062608C00004$$ | VALID | INDEX | REQUEST_REVISION_ID_AH_IDX_OLD | VALID
INDEX | SYS_IL0000062611C00006$$ | VALID | INDEX | REQUEST_REVISION_ID_IDX | VALID
INDEX | SYS_IL0000062649C00036$$ | VALID | INDEX | REQUEST_SPCONTACT_PK | VALID
INDEX | TIME_SLOT_PK | VALID | INDEX | REQUEST_STATUS_HISTORY_PK | VALID
INDEX | TPSQL_IDX | VALID | INDEX | REQUEST_STATUS_PK | VALID
INDEX | UK_SPG_01 | VALID | INDEX | REVISION_IDX | VALID
INDEX | USER_PK | VALID | INDEX | RULEACTION_PK | VALID
INDEX | WORK_TYPE_ALLOWED_OFFERING_PK | VALID | INDEX | RULECONDITION_PK | VALID
INDEX | WORK_TYPE_PK | VALID | INDEX | RULEFLITER_UK1 | VALID
INDEX | WORKQUEUE_DECISION_PK | VALID | INDEX | SDDB_ATTRIBUTE_PK | VALID
INDEX | XPKACTIVITY | VALID | INDEX | SELECTED_PRODUCT_PK | VALID
INDEX | XPKACTIVITY_HISTORY | VALID | INDEX | SERVICE_IDENTIFIER_PK | VALID
INDEX | XPKATTRIBUTE | VALID | INDEX | SERVICE_NK_NUMBER_INVENTORY_PK | VALID
INDEX | XPKCRD | VALID | INDEX | SERVICE_OFFERING_PK | VALID
INDEX | XPKCUSTOMER_COURTESY_TITLE | VALID | INDEX | SERVICE_PROVIDER_PK | VALID
INDEX | XPKCUSTOMER_TYPE | VALID | INDEX | SERVICE_STATUS_HISTORY_PK | VALID
INDEX | XPKEAST_ADDRESS_TYPE | VALID | INDEX | SERVICE_STATUS_PK | VALID
INDEX | XPKEAST_AXIS_ADDRESS_TYPE | VALID | INDEX | SERVICEABILITYRESPONSE_PK | VALID
INDEX | XPKEAST_AXIS_STREET_TYPE | VALID | INDEX | SP_CIDN_PK | VALID
INDEX | XPKEAST_AXIS_STREET_TYPE_SUFFI | VALID | INDEX | SP_CONTACT_PK | VALID
INDEX | XPKENTRY_MEDIUM | VALID | INDEX | SP_GROUP_PK | VALID
INDEX | XPKFULLYCONFIGUREDSQRESPONSE | VALID | INDEX | SP_INDEX | VALID
INDEX | XPKFWOM_TIME_SLOT | VALID | INDEX | SP_SHORT_NAME_PK | VALID
INDEX | XPKMOP_ORDER | VALID | INDEX | SP_SP_GROUP_PK | VALID
INDEX | XPKMOP_ORDER_ITEM_NOTIFICATION | VALID | INDEX | SP_VIEWABLE_FLAG_IDX | VALID
INDEX | XPKMOP_STATUS | VALID | INDEX | SP_VIEWABLE_FLAG_IDX_OLD | VALID
INDEX | XPKNOTES | VALID | INDEX | SP_WORK_TYPE_AUTH_PK | VALID
INDEX | XPKOFFERING_ATTRIBUTE | VALID | INDEX | SPOFFERINGASSOC_PK | VALID
INDEX | XPKPOSTCODE_LOCALITY | VALID | INDEX | SYS_IL0000062608C00004$$ | VALID
INDEX | XPKREASON | VALID | INDEX | SYS_IL0000062611C00006$$ | VALID
INDEX | XPKREQUEST_ITEM | VALID | INDEX | SYS_IL0000062649C00036$$ | VALID
INDEX | XPKSDDB_ATTRIBUTE | VALID | INDEX | TARIFF_PK | VALID
INDEX | XPKSERVICE_STATUS | VALID | INDEX | TIME_SLOT_PK | VALID
INDEX | XPKSP_SP_GROUP | VALID | INDEX | TPSQL_IDX | VALID
INDEX | XPKTARIFF | VALID | INDEX | UK_SPG_01 | VALID
INDEX | XPKWORK_TYPE_OFFERING | VALID | INDEX | USER_PK | VALID
LOB | SYS_LOB0000062608C00004$$ | VALID | INDEX | WORK_GROUP_PK | VALID
LOB | SYS_LOB0000062611C00006$$ | VALID | INDEX | WORK_QUEUE_PK | VALID
LOB | SYS_LOB0000062649C00036$$ | VALID | INDEX | WORK_TYPE_ALLOWED_OFFERING_PK | VALID
SEQUENCE | LOLIG_SEQUENCE | VALID | INDEX | WORK_TYPE_CATEGORY_PK | VALID
SEQUENCE | ORDER_SEQ | VALID | INDEX | WORK_TYPE_OFFERING_PK | VALID
SEQUENCE | ORDERID_SEQ | VALID | INDEX | WORK_TYPE_PK | VALID
SEQUENCE | ORDERITEM_SEQ | VALID | INDEX | WORKQUEUE_DECISION_PK | VALID
SEQUENCE | ORDERITEMID_SEQ | VALID | LOB | SYS_LOB0000062608C00004$$ | VALID
SEQUENCE | REQUEST_SEQ | VALID | LOB | SYS_LOB0000062611C00006$$ | VALID
SEQUENCE | REQUESTID_SEQ | VALID | LOB | SYS_LOB0000062649C00036$$ | VALID
SEQUENCE | REQUESTITEM_SEQ | VALID | SEQUENCE | LOLIG_SEQUENCE | VALID
SEQUENCE | REQUESTITEMID_SEQ | VALID | SEQUENCE | ORDER_SEQ | VALID
SYNONYM | ATTRIBUTE_1 | VALID | SEQUENCE | ORDERID_SEQ | VALID
SYNONYM | ATTRIBUTE_VALUE_1 | VALID | SEQUENCE | ORDERITEM_SEQ | VALID
SYNONYM | AUST_STATE_1 | VALID | SEQUENCE | ORDERITEMID_SEQ | VALID
SYNONYM | OFFERING_ATTRIBUTE_1 | VALID | SEQUENCE | REQUEST_SEQ | VALID
SYNONYM | OFFERING_OFFERING_TYPE_1 | VALID | SEQUENCE | REQUESTID_SEQ | VALID
SYNONYM | OFFERING_TYPE_1 | VALID | SEQUENCE | REQUESTITEM_SEQ | VALID
SYNONYM | REQUEST_ITEM_STATUS_HISTORY_1 | VALID | SEQUENCE | REQUESTITEMID_SEQ | VALID
SYNONYM | REQUEST_STATUS_1 | VALID | SYNONYM | ATTRIBUTE_1 | VALID
SYNONYM | REQUEST_STATUS_HISTORY_1 | VALID | SYNONYM | ATTRIBUTE_VALUE_1 | VALID
SYNONYM | SERVICE_OFFERING_1 | VALID | SYNONYM | AUST_STATE_1 | VALID
SYNONYM | SERVICE_OFFERING_SETTING_1 | VALID | SYNONYM | OFFERING_ATTRIBUTE_1 | VALID
SYNONYM | WORK_TYPE_1 | VALID | SYNONYM | OFFERING_OFFERING_TYPE_1 | VALID
SYNONYM | WORK_TYPE_CATEGORY_1 | VALID | SYNONYM | OFFERING_TYPE_1 | VALID
TABLE | ACTIVITY | VALID | SYNONYM | REQUEST_ITEM_STATUS_HISTORY_1 | VALID
TABLE | ACTIVITY_HISTORY | VALID | SYNONYM | REQUEST_STATUS_1 | VALID
TABLE | ADDRESS | VALID | SYNONYM | REQUEST_STATUS_HISTORY_1 | VALID
TABLE | AMEND_LOCK | VALID | SYNONYM | SERVICE_OFFERING_1 | VALID
TABLE | APPOINTMENT | VALID | SYNONYM | SERVICE_OFFERING_SETTING_1 | VALID
TABLE | ASSIGNMENT_HISTORY | VALID | SYNONYM | WORK_TYPE_1 | VALID
TABLE | ATTRIBUTE | VALID | SYNONYM | WORK_TYPE_CATEGORY_1 | VALID
TABLE | ATTRIBUTE_VALUE | VALID | TABLE | ACTIVITY | VALID
TABLE | AUST_STATE | VALID | TABLE | ACTIVITY_HISTORY | VALID
TABLE | BPM_USERS | VALID | TABLE | ACTIVITY_HISTORY_OLD | VALID
TABLE | BUNDLE | VALID | TABLE | ADDRESS | VALID
TABLE | BUNDLE_NETWORK_TYPE | VALID | TABLE | AMEND_LOCK | VALID
TABLE | BUNDLE_PRODUCT_CLASS | VALID | TABLE | APPOINTMENT | VALID
TABLE | CCA | VALID | TABLE | ASSIGNMENT_HISTORY | VALID
TABLE | CHAINED_ROWS | VALID | TABLE | ATTRIBUTE | VALID
TABLE | CHANGE_REQUEST | VALID | TABLE | ATTRIBUTE_VALUE | VALID
TABLE | CHANNEL | VALID | TABLE | AUST_STATE | VALID
TABLE | CHARAC_ASSOCIATION | VALID | TABLE | BPM_USERS | VALID
TABLE | CHARAC_PARAM_ASSOCIATION | VALID | TABLE | BUNDLE | VALID
TABLE | CHARAC_PARAM_VALUE | VALID | TABLE | BUNDLE_NETWORK_TYPE | VALID
TABLE | CHARAC_PARAMETER | VALID | TABLE | BUNDLE_PRODUCT_CLASS | VALID
TABLE | CHARACTERISTIC | VALID | TABLE | CCA | VALID
TABLE | COMPLEX_REQUEST_ITEM | VALID | TABLE | CHAINED_ROWS | VALID
TABLE | CRD | VALID | TABLE | CHANGE_REQUEST | VALID
TABLE | CUSTOMER | VALID | TABLE | CHANNEL | VALID
TABLE | CUSTOMER_COURTESY_TITLE | VALID | TABLE | CHARAC_ASSOCIATION | VALID
TABLE | CUSTOMER_TYPE | VALID | TABLE | CHARAC_PARAM_ASSOCIATION | VALID
TABLE | DIRECTORY_DETAILS | VALID | TABLE | CHARAC_PARAM_VALUE | VALID
TABLE | EAST_ADDRESS_TYPE | VALID | TABLE | CHARAC_PARAMETER | VALID
TABLE | EAST_AXIS_ADDRESS_TYPE | VALID | TABLE | CHARACTERISTIC | VALID
TABLE | EAST_AXIS_STREET_TYPE | VALID | TABLE | COMPLEX_REQUEST_ITEM | VALID
TABLE | EAST_AXIS_STREET_TYPE_SUFFIX | VALID | TABLE | CRD | VALID
TABLE | EAST_SUB_ADDRESS_TYPE | VALID | TABLE | CUSTOMER | VALID
TABLE | ENTRY_MEDIUM | VALID | TABLE | CUSTOMER_COURTESY_TITLE | VALID
TABLE | EQUIPMENT | VALID | TABLE | CUSTOMER_TYPE | VALID
TABLE | EQUIPMENT_TYPE | VALID | TABLE | DIRECTORY_DETAILS | VALID
TABLE | ERROR_MAPPING | VALID | TABLE | EAST_ADDRESS_TYPE | VALID
TABLE | FNN_RELOCATION_RESPONSE | VALID | TABLE | EAST_AXIS_ADDRESS_TYPE | VALID
TABLE | FNN_VALIDATION_RESPONSE | VALID | TABLE | EAST_AXIS_STREET_TYPE | VALID
TABLE | FULLY_CONFIG_SQ_RESPONSE | VALID | TABLE | EAST_AXIS_STREET_TYPE_SUFFIX | VALID
TABLE | FWOM_TIME_SLOT | VALID | TABLE | EAST_SUB_ADDRESS_TYPE | VALID
TABLE | GENERAL_REFERENCE | VALID | TABLE | ENTRY_MEDIUM | VALID
TABLE | INSTANT_HOTLINE | VALID | TABLE | EQUIPMENT | VALID
TABLE | LOLO_FWOM_REASON_MAP | VALID | TABLE | EQUIPMENT_TYPE | VALID
TABLE | LOLO_MSQ_ATT_MAP | VALID | TABLE | ERROR_MAPPING | VALID
TABLE | LOLO_MSQ_SRV_MAP | VALID | TABLE | FNN_RELOCATION_RESPONSE | VALID
TABLE | MESSAGE | VALID | TABLE | FNN_VALIDATION_RESPONSE | VALID
TABLE | MOP_ORDER | VALID | TABLE | FULLY_CONFIG_SQ_RESPONSE | VALID
TABLE | MOP_ORDER_ITEM | VALID | TABLE | FWOM_TIME_SLOT | VALID
TABLE | MOP_ORDER_ITEM_NOTIFICATION | VALID | TABLE | GENERAL_REFERENCE | VALID
TABLE | MOP_SERVICE_INVENTORY | VALID | TABLE | INSTANT_HOTLINE | VALID
TABLE | MOP_STATUS | VALID | TABLE | LOLO_FWOM_REASON_MAP | VALID
TABLE | NOTES | VALID | TABLE | LOLO_MSQ_ATT_MAP | VALID
TABLE | OFFERING | VALID | TABLE | LOLO_MSQ_SRV_MAP | VALID
TABLE | OFFERING_ATTRIBUTE | VALID | TABLE | MESSAGE | VALID
TABLE | OFFERING_BUNDLE_ASSOCIATION | VALID | TABLE | MOP_ORDER | VALID
TABLE | OFFERING_CATEGORY | VALID | TABLE | MOP_ORDER_ITEM | VALID
TABLE | OFFERING_OFFERING_TYPE | VALID | TABLE | MOP_ORDER_ITEM_NOTIFICATION | VALID
TABLE | OFFERING_TYPE | VALID | TABLE | MOP_SERVICE_INVENTORY | VALID
TABLE | PCMS_CODE | VALID | TABLE | MOP_STATUS | VALID
TABLE | POP_LOCK | VALID | TABLE | NOTES | VALID
TABLE | POP_RULE_ACTION | VALID | TABLE | OFFERING | VALID
TABLE | POP_RULE_BINDING | VALID | TABLE | OFFERING_ATTRIBUTE | VALID
TABLE | POP_RULE_CONDITION | VALID | TABLE | OFFERING_BUNDLE_ASSOCIATION | VALID
TABLE | PORT_CHURN_INFO | VALID | TABLE | OFFERING_CATEGORY | VALID
TABLE | POSTCODE_LOCALITY | VALID | TABLE | OFFERING_OFFERING_TYPE | VALID
TABLE | PRODUCT_CLASS | VALID | TABLE | OFFERING_TYPE | VALID
TABLE | PRODUCT_CLASS_OFFERING | VALID | TABLE | PCMS_CODE | VALID
TABLE | PROGRAMMING | VALID | TABLE | POP_LOCK | VALID
TABLE | PSTS_SERVICE | VALID | TABLE | POP_RULE_ACTION | VALID
TABLE | QUEUE_ASSIGNMENT | VALID | TABLE | POP_RULE_BINDING | VALID
TABLE | QUEUE_CRITERIA | VALID | TABLE | POP_RULE_CONDITION | VALID
TABLE | REASON | VALID | TABLE | PORT_CHURN_INFO | VALID
TABLE | REQUEST | VALID | TABLE | POSTCODE_LOCALITY | VALID
TABLE | REQUEST_ITEM | VALID | TABLE | PRODUCT_CLASS | VALID
TABLE | REQUEST_ITEM_STATUS | VALID | TABLE | PRODUCT_CLASS_OFFERING | VALID
TABLE | REQUEST_ITEM_STATUS_HISTORY | VALID | TABLE | PROGRAMMING | VALID
TABLE | REQUEST_SPCONTACT | VALID | TABLE | PSTS_SERVICE | VALID
TABLE | REQUEST_STATUS | VALID | TABLE | QUEUE_ASSIGNMENT | VALID
TABLE | REQUEST_STATUS_HISTORY | VALID | TABLE | QUEUE_CRITERIA | VALID
TABLE | RULEACTION | VALID | TABLE | REASON | VALID
TABLE | RULECONDITION | VALID | TABLE | REQUEST | VALID
TABLE | RULEFLITER | VALID | TABLE | REQUEST_ITEM | VALID
TABLE | SDDB_ATTRIBUTE | VALID | TABLE | REQUEST_ITEM_STATUS | VALID
TABLE | SELECTED_PRODUCT | VALID | TABLE | REQUEST_ITEM_STATUS_HISTORY | VALID
TABLE | SERVICE | VALID | TABLE | REQUEST_SPCONTACT | VALID
TABLE | SERVICE_AREA_ASSOCIATION | VALID | TABLE | REQUEST_STATUS | VALID
TABLE | SERVICE_IDENTIFIER | VALID | TABLE | REQUEST_STATUS_HISTORY | VALID
TABLE | SERVICE_NK_NUMBER_INVENTORY | VALID | TABLE | RULEACTION | VALID
TABLE | SERVICE_OFFERING | VALID | TABLE | RULECONDITION | VALID
TABLE | SERVICE_OFFERING_SETTING | VALID | TABLE | RULEFLITER | VALID
TABLE | SERVICE_PROVIDER | VALID | TABLE | SDDB_ATTRIBUTE | VALID
TABLE | SERVICE_STATUS | VALID | TABLE | SELECTED_PRODUCT | VALID
TABLE | SERVICE_STATUS_HISTORY | VALID | TABLE | SERVICE | VALID
TABLE | SERVICEABILITY_RESPONSE | VALID | TABLE | SERVICE_AREA_ASSOCIATION | VALID
TABLE | SP_BUNDLE | VALID | TABLE | SERVICE_IDENTIFIER | VALID
TABLE | SP_CIDN | VALID | TABLE | SERVICE_NK_NUMBER_INVENTORY | VALID
TABLE | SP_CONTACT | VALID | TABLE | SERVICE_OFFERING | VALID
TABLE | SP_GROUP | VALID | TABLE | SERVICE_OFFERING_SETTING | VALID
TABLE | SP_OFFERING | VALID | TABLE | SERVICE_PROVIDER | VALID
TABLE | SP_OFFERING_ASSOCIATION | VALID | TABLE | SERVICE_STATUS | VALID
TABLE | SP_SHORT_NAME | VALID | TABLE | SERVICE_STATUS_HISTORY | VALID
TABLE | SP_SP_GROUP | VALID | TABLE | SERVICEABILITY_RESPONSE | VALID
TABLE | SP_WORK_TYPE_AUTH | VALID | TABLE | SP_BUNDLE | VALID
TABLE | SQ_MAPPING | VALID | TABLE | SP_CIDN | VALID
TABLE | SYS_TEMP_FBT | VALID | TABLE | SP_CONTACT | VALID
TABLE | T_ERROR_CODE_MAST | VALID | TABLE | SP_GROUP | VALID
TABLE | TARIFF | VALID | TABLE | SP_OFFERING | VALID
TABLE | TBL_AUDIT_LOLIG | VALID | TABLE | SP_OFFERING_ASSOCIATION | VALID
TABLE | TIME_SLOT | VALID | TABLE | SP_SHORT_NAME | VALID
TABLE | TOAD_PLAN_SQL | VALID | TABLE | SP_SP_GROUP | VALID
TABLE | TOAD_PLAN_TABLE | VALID | TABLE | SP_WORK_TYPE_AUTH | VALID
TABLE | USERS | VALID | TABLE | SQ_MAPPING | VALID
TABLE | WORK_GROUP | VALID | TABLE | SYS_TEMP_FBT | VALID
TABLE | WORK_QUEUE | VALID | TABLE | T_ERROR_CODE_MAST | VALID
TABLE | WORK_TYPE | VALID | TABLE | TARIFF | VALID
TABLE | WORK_TYPE_ALLOWED_OFFERING | VALID | TABLE | TBL_AUDIT_LOLIG | VALID
TABLE | WORK_TYPE_CATEGORY | VALID | TABLE | TIME_SLOT | VALID
TABLE | WORK_TYPE_OFFERING | VALID | TABLE | TOAD_PLAN_SQL | VALID
TABLE | WORKQUEUE_DECISION | VALID | TABLE | TOAD_PLAN_TABLE | VALID
VIEW | PCMS_CODE_OFFERING_VIEW | VALID | TABLE | USERS | VALID
|  |  | TABLE | WORK_GROUP | VALID
|  |  | TABLE | WORK_QUEUE | VALID
|  |  | TABLE | WORK_TYPE | VALID
|  |  | TABLE | WORK_TYPE_ALLOWED_OFFERING | VALID
|  |  | TABLE | WORK_TYPE_CATEGORY | VALID
|  |  | TABLE | WORK_TYPE_OFFERING | VALID
|  |  | TABLE | WORKQUEUE_DECISION | VALID
|  |  | VIEW | PCMS_CODE_OFFERING_VIEW | VALID

## B.4.AH Table SQL Perfrm Metrics (hidden)
Activity History Table SQL Performance Metrics
SQL ID | SQL Text | Execution Timings
|  | Before Reorg | Before Partition | After partition | Before Re-org with Partition | After Reorg
SQL_AH1 | SELECT DISTINCT AH.REJECT_REASON_CODE,S.REVISION,R.CUSTOMER_NAME,R.PROJECT_ID, R.RECEIVED_TIMESTAMP,R.CHANNEL_TYPE,R.REQUEST_ID, R.REQUEST_REVISION_ID,R.SP_REFERENCE_NO,RI.REQUEST_ITEM_REVISION_ID, CASE WHEN ( AH.STATUS='REJECTED' OR UPPER(AH.DESCRIPTION) ='REJECT' ) THEN AH.UPDATED_DATE ELSE AH.CREATED_DATE END AS "UPDATED_DATE",RI.WORK_TYPE_ID FROM ACTIVITY_HISTORY AH, REQUEST_ITEM RI, REQUEST R,SERVICE S WHERE (( AH.STATUS = 'REJECTED' OR UPPER(AH.DESCRIPTION) = 'REJECT' ) OR AH.NOTES LIKE '%Rejected%') AND AH.SP_VIEWABLE_FLAG = 'Y' AND ( (AH.CREATED_DATE BETWEEN TO_DATE('05/10/13 00:00:00','dd/mm/yy hh24:mi:ss') and TO_DATE('05/10/13 23:59:59','dd/mm/yy hh24:mi:ss') ) ) AND ( (AH.REQUEST_ITEM_REVISION_ID = RI.REQUEST_ITEM_REVISION_ID) OR (AH.REQUEST_REVISION_ID = R.REQUEST_REVISION_ID) ) AND RI.REQUEST_REVISION_ID = R.REQUEST_REVISION_ID AND R.SP_ID = 95 AND RI.REQUEST_ITEM_REVISION_ID = S.REQUEST_ITEM_REVISION_ID | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
SQL_AH2 | SELECT DISTINCT AH.REJECT_REASON_CODE,S.REVISION,R.CUSTOMER_NAME,R.PROJECT_ID, R.RECEIVED_TIMESTAMP,R.CHANNEL_TYPE,R.REQUEST_ID, R.REQUEST_REVISION_ID,R.SP_REFERENCE_NO,RI.REQUEST_ITEM_REVISION_ID, CASE WHEN ( AH.STATUS='REJECTED' OR UPPER(AH.DESCRIPTION) ='REJECT' ) THEN AH.UPDATED_DATE ELSE AH.CREATED_DATE END AS "UPDATED_DATE",RI.WORK_TYPE_ID FROM ACTIVITY_HISTORY AH, REQUEST_ITEM RI, REQUEST R,SERVICE S WHERE (( AH.STATUS = 'REJECTED' OR UPPER(AH.DESCRIPTION) = 'REJECT' ) OR AH.NOTES LIKE '%Rejected%') AND AH.SP_VIEWABLE_FLAG = 'Y' AND ( (AH.CREATED_DATE BETWEEN TO_DATE('28/11/13 00:00:00','dd/mm/yy hh24:mi:ss') and TO_DATE('28/11/13 23:59:59','dd/mm/yy hh24:mi:ss') ) ) AND ( (AH.REQUEST_ITEM_REVISION_ID = RI.REQUEST_ITEM_REVISION_ID) OR (AH.REQUEST_REVISION_ID = R.REQUEST_REVISION_ID) ) AND RI.REQUEST_REVISION_ID = R.REQUEST_REVISION_ID AND R.SP_ID = 95 AND RI.REQUEST_ITEM_REVISION_ID = S.REQUEST_ITEM_REVISION_ID | 0:00 | 0:00 | 0:00 | 0:00 | 0:03
SQL_AH3 | select count(*) from activity_history where created_date between trunc(sysdate-1) and trunc(sysdate); | 0:00 | 0:00 | 0:00 | 0:00 | 0:00

## C.1.Tablespace Usage Report (hidden)
Logical (Tablespace) Reclaimed Space | [11 empty] | Space Utilization After Re-org and Before Shrinking the Data Files
SPACE USAGE BEFORE THE CHANGE | [6 empty] | SPACE USAGE AFTER THE CHANGE
Tablespace Name | Total (MB) | Used (MB) | Free (MB) | %Used | %Free |  | Total (MB) | Used (MB) | Free (MB) | %Used | %Free
AUDIT1 | 2000 | 1199.5 | 800.5 | 59.975 | 40.025 |  | 2000 | 1209.5 | 790.5 | 60.475 | 39.525
GENUSER | 3072 | 2326.25 | 745.75 | 75.7243 | 24.2757 |  | 3072 | 1998.25 | 1073.75 | 65.0472 | 34.9528
LOLO_DATA_A01 | 24500 | 7505 | 16995 | 30.6327 | 69.3673 |  | 24500 | 7906 | 16594 | 32.2694 | 67.7306
LOLO_DATA_LOB | 41080 | 88 | 40992 | 0.21422 | 99.7858 |  | 41080 | 88 | 40992 | 0.21422 | 99.7858
LOLO_DATA_UL01 | 43160 | 88 | 43072 | 0.20389 | 99.7961 |  | 43160 | 88 | 43072 | 0.20389 | 99.7961
LOLO_DATA_UL02 | 41500 | 92 | 41408 | 0.22169 | 99.7783 |  | 41500 | 11100 | 30400 | 26.747 | 73.253
LOLO_DATA_UL03 | 96750 | 93870 | 2880 | 97.0233 | 2.9767 |  | 111750 | 98502 | 13248 | 88.145 | 11.855
LOLO_DATA_UL04 | 34120 | 72 | 34048 | 0.21102 | 99.789 |  | 34120 | 72 | 34048 | 0.21102 | 99.789
LOLO_DATA_UM01 | 12934 | 6 | 12928 | 0.046389 | 99.9536 |  | 12934 | 6 | 12928 | 0.046389 | 99.9536
LOLO_IDX_A01 | 26510 | 91 | 26419 | 0.34327 | 99.6567 |  | 26510 | 91 | 26419 | 0.34327 | 99.6567
LOLO_IDX_UL01 | 53060 | 6660 | 46400 | 12.5518 | 87.4482 |  | 53060 | 9444 | 43616 | 17.7987 | 82.2013
LOLO_IDX_UL02 | 53480 | 72 | 53408 | 0.13463 | 99.8654 |  | 53480 | 72 | 53408 | 0.13463 | 99.8654
LOLO_IDX_UL03 | 48120 | 88 | 48032 | 0.18288 | 99.8171 |  | 48120 | 88 | 48032 | 0.18288 | 99.8171
LOLO_IDX_UM01 | 32443 | 11 | 32432 | 0.033906 | 99.9661 |  | 32443 | 11 | 32432 | 0.033906 | 99.9661
LOLO_IDX_UM02 | 5347 | 3 | 5344 | 0.056106 | 99.9439 |  | 5347 | 3 | 5344 | 0.056106 | 99.9439
LOLO_PLR_DATA | 2020 | 4 | 2016 | 0.19802 | 99.802 |  | 2020 | 4 | 2016 | 0.19802 | 99.802
LOLO_PLR_IDX | 4040 | 8 | 4032 | 0.19802 | 99.802 |  | 4040 | 8 | 4032 | 0.19802 | 99.802
SYSAUX | 5120 | 1468.687 | 3651.313 | 28.6853 | 71.3147 |  | 5120 | 1442.437 | 3677.563 | 28.1726 | 71.8274
SYSTEM | 1000 | 304.687 | 695.313 | 30.4687 | 69.5313 |  | 1000 | 304.75 | 695.25 | 30.475 | 69.525
TEMP | 20480 | 16388 | 4092 | 80.0195 | 19.9805 |  | 20480 | 16388 | 4092 | 80.0195 | 19.9805
TOOLS | 500 | 1.312 | 498.688 | 0.2624 | 99.7376 |  | 500 | 1.312 | 498.688 | 0.2624 | 99.7376
UNDOTS1 | 10000 | 9997.625 | 2.375 | 99.9762 | 0.02375 |  | 10000 | 8599.312 | 1400.688 | 85.9931 | 14.0069
UNDOTS2 | 10000 | 8911.25 | 1088.75 | 89.1125 | 10.8875 |  | 10000 | 9137.25 | 862.75 | 91.3725 | 8.6275
Total | 571236 | 149255.311 | 421980.689 |  |  | 0 | 586236 | 166563.811 | 419672.189
Logical Reclaimed Space | -2.2544 | GB
2
Reclaimable Space After retention period |  | Space In GB
Rename LOB Object |  | 71.5
Renamed Activity_history table and indexes |  | 12.9688
Total |  | 84.4688

## C.2.ApSchema Object Size Report (hidden)
Application DB Schema Object Size Report
SEGMENT_TYPE | SEGMENT_NAME | Before Change |  |  | After Change
|  | SIZE_MB | SEGMENT TYPE | SEGMENT NAME | SIZE_MB
LOBSEGMENT | SYS_LOB0000062608C00004$$ | 72640 | LOBSEGMENT | SYS_LOB0000062608C00004$$ | 72640
TABLE_PARTITION | ACTIVITY_HISTORY |  | TABLE_PARTITION | ACTIVITY_HISTORY | 11072
TABLE | ACTIVITY_HISTORY | 10240 | TABLE | ACTIVITY_HISTORY_OLD | 10240
TABLE | MESSAGE | 8384 | TABLE | MESSAGE_20131230 | 8384
TABLE | MESSAGE |  | TABLE | MESSAGE | 64
INDEX | CREATED_DATE_IDX |  | INDEX | CREATED_DATE_IDX | 1088
INDEX | CREATED_DATE_IDX_OLD | 1088 | INDEX | CREATED_DATE_IDX_OLD | 1088
INDEX | REQUEST_REV_IDX | 968 | INDEX | ACTIVITY_HISTORY_PK | 960
INDEX | XPKACTIVITY_HISTORY | 960 | INDEX | ACTIVITY_HISTORY_PK_OLD | 960
INDEX | ACTIVITY_ID_IDX | 616 | INDEX_PARTITION | SP_VIEWABLE_FLAG_IDX | 736
LOBSEGMENT | SYS_LOB0000062611C00006$$ | 512 | INDEX | REQUEST_REV_IDX | 656
TABLE | REQUEST | 320 | INDEX | ACTIVITY_ID_IDX | 512
INDEX | MESSAGE_ID_PK | 256 | LOBSEGMENT | SYS_LOB0000062611C00006$$ | 512
INDEX | REQ_ITEM_HISTORY_IDX | 224 | INDEX | REQUEST_REV_IDX_OLD | 480
INDEX | SERVICE_IDENTIFIER_PK | 224 | INDEX | ACTIVITY_ID_IDX_OLD | 384
INDEX | PK_RSH | 192 | TABLE | REQUEST | 320
INDEX | REQUEST_PK | 192 | INDEX | MESSAGE_PK_20131230 | 256
INDEX | REQ_ID_IDX | 184 | INDEX | REQUEST_REVISION_ID_AH_IDX | 128
INDEX | REQUEST_ID_PK | 160 | INDEX | REQUEST_REVISION_ID_AH_IDX_OLD | 128
INDEX | REQ_REVISION_IDX | 136 | TABLE | CRD | 128
INDEX | PK_RISH | 128 | TABLE | REQUEST_ITEM_STATUS_HISTORY | 128
INDEX | REQUEST_ITEM_REVISION_ID_IDX | 128 | TABLE | REQUEST_SPCONTACT | 128
INDEX | REQUEST_REVISDTSTAMP_IDX | 128 | TABLE | REQUEST_STATUS_HISTORY | 128
INDEX | REQUEST_REVISION_ID_AH_IDX | 128 | TABLE | SERVICE | 128
TABLE | REQUEST_ITEM_STATUS_HISTORY | 128 | TABLE | REQUEST_ITEM | 120
TABLE | REQUEST_SPCONTACT | 128 | INDEX | REQUEST_REVISDTSTAMP_IDX | 96
TABLE | REQUEST_STATUS_HISTORY | 128 | TABLE | APPOINTMENT | 90
TABLE | SERVICE | 128 | INDEX | ECS_USER | 88
TABLE | CRD | 126 | INDEX | REQ_ITEM_HISTORY_IDX | 72
INDEX | ECS_USER | 120 | TABLE | ADDRESS | 68
TABLE | REQUEST_ITEM | 118 | INDEX | APPOINTMENT_REQREVNID_IDX | 64
INDEX | REQ_STATUS_CODE_IDX | 112 | INDEX | CRD_APPMT_REVNID_IDX | 64
INDEX | REQUEST_SPCONTACT_PK | 96 | INDEX | CRD_PK | 64
TABLE | APPOINTMENT | 89 | INDEX | REQUEST_ID_PK | 64
TABLE | ADDRESS | 68 | INDEX | REQUEST_ITEM_PK | 64
INDEX | APPOINTMENT_REQREVNID_IDX | 64 | INDEX | REQUEST_ITEM_REVISION_ID_IDX | 64
INDEX | CRD_APPMT_REVNID_IDX | 64 | INDEX | REQUEST_ITEM_STATUS_HISTORY_PK | 64
INDEX | REQUEST_REVISION_ID_IDX | 64 | INDEX | REQUEST_PK | 64
INDEX | XPKCRD | 64 | INDEX | REQUEST_REVISION_ID_IDX | 64
INDEX | XPKREQUEST_ITEM | 64 | INDEX | REQUEST_SPCONTACT_PK | 64
LOBINDEX | SYS_IL0000062608C00004$$ | 64 | INDEX | REQUEST_STATUS_HISTORY_PK | 64
LOBINDEX | SYS_IL0000062611C00006$$ | 64 | INDEX | SERVICE_IDENTIFIER_PK | 64
TABLE | ACTIVITY | 64 | LOBINDEX | SYS_IL0000062608C00004$$ | 64
TABLE | ASSIGNMENT_HISTORY | 64 | LOBINDEX | SYS_IL0000062611C00006$$ | 64
TABLE | ATTRIBUTE | 64 | LOBSEGMENT | MSG_CONTENT_CLOB_SGMNT | 64
TABLE | ATTRIBUTE_VALUE | 64 | TABLE | ACTIVITY | 64
TABLE | AUST_STATE | 64 | TABLE | AMEND_LOCK | 64
TABLE | BPM_USERS | 64 | TABLE | ASSIGNMENT_HISTORY | 64
TABLE | BUNDLE | 64 | TABLE | ATTRIBUTE | 64
TABLE | BUNDLE_NETWORK_TYPE | 64 | TABLE | ATTRIBUTE_VALUE | 64
TABLE | BUNDLE_PRODUCT_CLASS | 64 | TABLE | AUST_STATE | 64
TABLE | CCA | 64 | TABLE | BPM_USERS | 64
TABLE | CHANGE_REQUEST | 64 | TABLE | BUNDLE | 64
TABLE | CHARACTERISTIC | 64 | TABLE | BUNDLE_NETWORK_TYPE | 64
TABLE | CHARAC_ASSOCIATION | 64 | TABLE | BUNDLE_PRODUCT_CLASS | 64
TABLE | CHARAC_PARAMETER | 64 | TABLE | CCA | 64
TABLE | CHARAC_PARAM_ASSOCIATION | 64 | TABLE | CHANGE_REQUEST | 64
TABLE | CHARAC_PARAM_VALUE | 64 | TABLE | CHARACTERISTIC | 64
TABLE | CUSTOMER | 64 | TABLE | CHARAC_ASSOCIATION | 64
TABLE | CUSTOMER_COURTESY_TITLE | 64 | TABLE | CHARAC_PARAMETER | 64
TABLE | CUSTOMER_TYPE | 64 | TABLE | CHARAC_PARAM_ASSOCIATION | 64
TABLE | DIRECTORY_DETAILS | 64 | TABLE | CHARAC_PARAM_VALUE | 64
TABLE | EAST_AXIS_ADDRESS_TYPE | 64 | TABLE | CUSTOMER | 64
TABLE | EAST_AXIS_STREET_TYPE | 64 | TABLE | CUSTOMER_COURTESY_TITLE | 64
TABLE | EAST_AXIS_STREET_TYPE_SUFFIX | 64 | TABLE | CUSTOMER_TYPE | 64
TABLE | EAST_SUB_ADDRESS_TYPE | 64 | TABLE | DIRECTORY_DETAILS | 64
TABLE | ERROR_MAPPING | 64 | TABLE | EAST_AXIS_ADDRESS_TYPE | 64
TABLE | FNN_RELOCATION_RESPONSE | 64 | TABLE | EAST_AXIS_STREET_TYPE | 64
TABLE | FNN_VALIDATION_RESPONSE | 64 | TABLE | EAST_AXIS_STREET_TYPE_SUFFIX | 64
TABLE | FULLY_CONFIG_SQ_RESPONSE | 64 | TABLE | EAST_SUB_ADDRESS_TYPE | 64
TABLE | FWOM_TIME_SLOT | 64 | TABLE | ERROR_MAPPING | 64
TABLE | GENERAL_REFERENCE | 64 | TABLE | FNN_RELOCATION_RESPONSE | 64
TABLE | LOLO_FWOM_REASON_MAP | 64 | TABLE | FNN_VALIDATION_RESPONSE | 64
TABLE | LOLO_MSQ_ATT_MAP | 64 | TABLE | FULLY_CONFIG_SQ_RESPONSE | 64
TABLE | LOLO_MSQ_SRV_MAP | 64 | TABLE | FWOM_TIME_SLOT | 64
TABLE | MOP_ORDER | 64 | TABLE | GENERAL_REFERENCE | 64
TABLE | MOP_ORDER_ITEM | 64 | TABLE | LOLO_FWOM_REASON_MAP | 64
TABLE | MOP_ORDER_ITEM_NOTIFICATION | 64 | TABLE | LOLO_MSQ_ATT_MAP | 64
TABLE | MOP_SERVICE_INVENTORY | 64 | TABLE | LOLO_MSQ_SRV_MAP | 64
TABLE | MOP_STATUS | 64 | TABLE | MOP_ORDER | 64
TABLE | NOTES | 64 | TABLE | MOP_ORDER_ITEM | 64
TABLE | OFFERING | 64 | TABLE | MOP_ORDER_ITEM_NOTIFICATION | 64
TABLE | OFFERING_ATTRIBUTE | 64 | TABLE | MOP_SERVICE_INVENTORY | 64
TABLE | OFFERING_BUNDLE_ASSOCIATION | 64 | TABLE | MOP_STATUS | 64 |  | As the Constraints and associtated index names are chaged, only high value objects mapped.
TABLE | OFFERING_CATEGORY | 64 | TABLE | NOTES | 64
TABLE | PCMS_CODE | 64 | TABLE | OFFERING | 64
TABLE | POP_LOCK | 64 | TABLE | OFFERING_ATTRIBUTE | 64
TABLE | POP_RULE_ACTION | 64 | TABLE | OFFERING_BUNDLE_ASSOCIATION | 64
TABLE | POP_RULE_BINDING | 64 | TABLE | OFFERING_CATEGORY | 64
TABLE | POP_RULE_CONDITION | 64 | TABLE | PCMS_CODE | 64
TABLE | PORT_CHURN_INFO | 64 | TABLE | POP_LOCK | 64
TABLE | POSTCODE_LOCALITY | 64 | TABLE | POP_RULE_ACTION | 64
TABLE | PRODUCT_CLASS | 64 | TABLE | POP_RULE_BINDING | 64
TABLE | PRODUCT_CLASS_OFFERING | 64 | TABLE | POP_RULE_CONDITION | 64
TABLE | QUEUE_ASSIGNMENT | 64 | TABLE | PORT_CHURN_INFO | 64
TABLE | REASON | 64 | TABLE | POSTCODE_LOCALITY | 64
TABLE | REQUEST_ITEM_STATUS | 64 | TABLE | PRODUCT_CLASS | 64
TABLE | REQUEST_STATUS | 64 | TABLE | PRODUCT_CLASS_OFFERING | 64
TABLE | RULEACTION | 64 | TABLE | QUEUE_ASSIGNMENT | 64
TABLE | RULECONDITION | 64 | TABLE | REASON | 64
TABLE | RULEFLITER | 64 | TABLE | REQUEST_ITEM_STATUS | 64
TABLE | SDDB_ATTRIBUTE | 64 | TABLE | REQUEST_STATUS | 64
TABLE | SELECTED_PRODUCT | 64 | TABLE | RULEACTION | 64
TABLE | SERVICEABILITY_RESPONSE | 64 | TABLE | RULECONDITION | 64
TABLE | SERVICE_AREA_ASSOCIATION | 64 | TABLE | RULEFLITER | 64
TABLE | SERVICE_IDENTIFIER | 64 | TABLE | SDDB_ATTRIBUTE | 64
TABLE | SERVICE_NK_NUMBER_INVENTORY | 64 | TABLE | SELECTED_PRODUCT | 64
TABLE | SERVICE_OFFERING | 64 | TABLE | SERVICEABILITY_RESPONSE | 64
TABLE | SERVICE_OFFERING_SETTING | 64 | TABLE | SERVICE_AREA_ASSOCIATION | 64
TABLE | SERVICE_STATUS | 64 | TABLE | SERVICE_IDENTIFIER | 64
TABLE | SERVICE_STATUS_HISTORY | 64 | TABLE | SERVICE_NK_NUMBER_INVENTORY | 64
TABLE | SP_BUNDLE | 64 | TABLE | SERVICE_OFFERING | 64
TABLE | SP_CIDN | 64 | TABLE | SERVICE_OFFERING_SETTING | 64
TABLE | SP_CONTACT | 64 | TABLE | SERVICE_STATUS | 64
TABLE | SP_OFFERING | 64 | TABLE | SERVICE_STATUS_HISTORY | 64
TABLE | SP_OFFERING_ASSOCIATION | 64 | TABLE | SP_BUNDLE | 64
TABLE | SP_SHORT_NAME | 64 | TABLE | SP_CIDN | 64
TABLE | SP_WORK_TYPE_AUTH | 64 | TABLE | SP_CONTACT | 64
TABLE | SQ_MAPPING | 64 | TABLE | SP_OFFERING | 64
TABLE | TBL_AUDIT_LOLIG | 64 | TABLE | SP_OFFERING_ASSOCIATION | 64
TABLE | TIME_SLOT | 64 | TABLE | SP_SHORT_NAME | 64
TABLE | T_ERROR_CODE_MAST | 64 | TABLE | SP_WORK_TYPE_AUTH | 64
TABLE | WORKQUEUE_DECISION | 64 | TABLE | SQ_MAPPING | 64
TABLE | WORK_GROUP | 64 | TABLE | TBL_AUDIT_LOLIG | 64
TABLE | WORK_QUEUE | 64 | TABLE | TIME_SLOT | 64
TABLE | WORK_TYPE | 64 | TABLE | T_ERROR_CODE_MAST | 64
TABLE | WORK_TYPE_ALLOWED_OFFERING | 64 | TABLE | WORKQUEUE_DECISION | 64
TABLE | WORK_TYPE_CATEGORY | 64 | TABLE | WORK_GROUP | 64
TABLE | WORK_TYPE_OFFERING | 64 | TABLE | WORK_QUEUE | 64
INDEX | AH_UPDATED_DATE_IDX | 32 | TABLE | WORK_TYPE | 64
INDEX | BPM_USER_PK | 32 | TABLE | WORK_TYPE_ALLOWED_OFFERING | 64
INDEX | BUNDLE_PRODUCT_CLASS_PK | 32 | TABLE | WORK_TYPE_CATEGORY | 64
INDEX | ERROR_MAPPING_PK | 32 | TABLE | WORK_TYPE_OFFERING | 64
INDEX | FK_ASSH_REQ_01 | 32 | INDEX | REQ_ID_IDX | 53
INDEX | FK_ASSH_USERS_01 | 32 | INDEX | REQ_REVISION_IDX | 53
INDEX | FK_ASSH_WQ_01 | 32 | INDEX | REQ_STATUS_CODE_IDX | 47
INDEX | FK_QA_WG_01 | 32 | INDEX | ACTIVITY_PK | 32
INDEX | FK_QA_WQ_01 | 32 | INDEX | AH_UPDATED_DATE_IDX | 32
INDEX | FK_WG_WG_01 | 32 | INDEX | AH_UPDATED_DATE_IDX_OLD | 32
INDEX | FNN_RELOCATION_RESPONSE_PK | 32 | INDEX | ASSIGNMENT_HISTORY_PK | 32
INDEX | FNN_VALDN_RESP_REVID_IDX | 32 | INDEX | ATTRIBUTE_PK | 32
INDEX | FNN_VALIDATION_RESPONSE_PK | 32 | INDEX | AUST_STATE_PK | 32
INDEX | GENERAL_REFERENCE_PK | 32 | INDEX | BPM_USER_PK | 32
INDEX | OFFERING_PK | 32 | INDEX | BUNDLE_PRODUCT_CLASS_PK | 32
INDEX | PK_ASSH | 32 | INDEX | CCA_PK | 32
INDEX | PK_ASTATE | 32 | INDEX | CHANGE_REQUEST_PK | 32
INDEX | PK_CIDN | 32 | INDEX | CHARACTERISTIC_PK | 32
INDEX | PK_CREQ | 32 | INDEX | CHARAC_ASSOCIATION_PK | 32
INDEX | PK_EAST_SUB_ADDRESS_TYPE | 32 | INDEX | CHARAC_PARAMETER_PK | 32
INDEX | PK_PCMS_CODE | 32 | INDEX | CHARAC_PARAM_ASSOCIATION_PK | 32
INDEX | PK_QA | 32 | INDEX | CUSTOMER_COURTESY_TITLE_PK | 32
INDEX | PK_RIS | 32 | INDEX | CUSTOMER_TYPE_PK | 32
INDEX | PK_RS | 32 | INDEX | DIRECTORY_DETAILS_PK | 32
INDEX | PK_SN | 32 | INDEX | EAST_AXIS_ADDRESS_TYPE_PK | 32
INDEX | PK_SPC | 32 | INDEX | EAST_AXIS_STREET_TYPE_PK | 32
INDEX | PK_SPWTA | 32 | INDEX | EAST_AXIS_STRT_TYPE_SUFFIX_PK | 32
INDEX | PK_WG | 32 | INDEX | EAST_SUB_ADDRESS_TYPE_PK | 32
INDEX | PK_WQ | 32 | INDEX | ERROR_MAPPING_PK | 32
INDEX | PK_WTCAT | 32 | INDEX | FK_ASSH_REQ_01 | 32
INDEX | PLAN_PK | 32 | INDEX | FK_ASSH_USERS_01 | 32
INDEX | POP_RULE_ACTION_PK | 32 | INDEX | FK_ASSH_WQ_01 | 32
INDEX | POP_RULE_BINDING_PK | 32 | INDEX | FK_QA_WG_01 | 32
INDEX | POP_RULE_CONDITION_PK | 32 | INDEX | FK_QA_WQ_01 | 32
INDEX | PRODUCT_CLASS_PK | 32 | INDEX | FK_WG_WG_01 | 32
INDEX | REASON_CODE_PK | 32 | INDEX | FNN_RELOCATION_RESPONSE_PK | 32
INDEX | REQ_STATUS_IDX | 32 | INDEX | FNN_VALDN_RESP_REVID_IDX | 32
INDEX | REVISION_IDX | 32 | INDEX | FNN_VALIDATION_RESPONSE_PK | 32
INDEX | RULEACTION_PK | 32 | INDEX | FULLY_CONFIG_SQ_RESPONSE_PK | 32
INDEX | RULECONDITION_PK | 32 | INDEX | FWOM_TIME_SLOT_PK | 32
INDEX | RULEFLITER_UK1 | 32 | INDEX | GENERAL_REFERENCE_PK | 32
INDEX | SELECTED_PRODUCT_PK | 32 | INDEX | LOLO_MSQ_ATT_MAP_PK | 32
INDEX | SERVICEABILITYRESPONSE_PK | 32 | INDEX | MESSAGE_ID_PK | 32
INDEX | SERVICE_OFFERING_PK | 32 | INDEX | MOP_ORDER_ITEM_NOTIFICATION_PK | 32
INDEX | SERVICE_STATUS_HISTORY_PK | 32 | INDEX | MOP_ORDER_PK | 32
INDEX | SPOFFERINGASSOC_PK | 32 | INDEX | MOP_STATUS_PK | 32
INDEX | SP_INDEX | 32 | INDEX | NOTES_PK | 32
INDEX | SP_VIEWABLE_FLAG_IDX | 32 | INDEX | OFFERING_ATTRIBUTE_PK | 32
INDEX | TIME_SLOT_PK | 32 | INDEX | OFFERING_PK | 32
INDEX | WORKQUEUE_DECISION_PK | 32 | INDEX | PCMS_CODE_PK | 32
INDEX | WORK_TYPE_ALLOWED_OFFERING_PK | 32 | INDEX | PLAN_PK | 32
INDEX | WORK_TYPE_PK | 32 | INDEX | POP_LOCK_PK | 32
INDEX | XPKACTIVITY | 32 | INDEX | POP_RULE_ACTION_PK | 32
INDEX | XPKATTRIBUTE | 32 | INDEX | POP_RULE_BINDING_PK | 32
INDEX | XPKCUSTOMER_COURTESY_TITLE | 32 | INDEX | POP_RULE_CONDITION_PK | 32
INDEX | XPKCUSTOMER_TYPE | 32 | INDEX | POSTCODE_LOCALITY_PK | 32
INDEX | XPKEAST_AXIS_ADDRESS_TYPE | 32 | INDEX | PRODUCT_CLASS_PK | 32
INDEX | XPKEAST_AXIS_STREET_TYPE | 32 | INDEX | QUEUE_ASSIGNMENT_PK | 32
INDEX | XPKEAST_AXIS_STREET_TYPE_SUFFI | 32 | INDEX | REASON_CODE_PK | 32
INDEX | XPKFULLYCONFIGUREDSQRESPONSE | 32 | INDEX | REASON_PK | 32
INDEX | XPKFWOM_TIME_SLOT | 32 | INDEX | REQUEST_ITEM_STATUS_PK | 32
INDEX | XPKMOP_ORDER | 32 | INDEX | REQUEST_STATUS_PK | 32
INDEX | XPKMOP_ORDER_ITEM_NOTIFICATION | 32 | INDEX | REQ_STATUS_IDX | 32
INDEX | XPKMOP_STATUS | 32 | INDEX | REVISION_IDX | 32
INDEX | XPKNOTES | 32 | INDEX | RULEACTION_PK | 32
INDEX | XPKOFFERING_ATTRIBUTE | 32 | INDEX | RULECONDITION_PK | 32
INDEX | XPKPOSTCODE_LOCALITY | 32 | INDEX | RULEFLITER_UK1 | 32
INDEX | XPKREASON | 32 | INDEX | SDDB_ATTRIBUTE_PK | 32
INDEX | XPKSDDB_ATTRIBUTE | 32 | INDEX | SELECTED_PRODUCT_PK | 32
INDEX | XPKSERVICE_STATUS | 32 | INDEX | SERVICEABILITYRESPONSE_PK | 32
INDEX | XPKWORK_TYPE_OFFERING | 32 | INDEX | SERVICE_OFFERING_PK | 32
TABLE | USERS | 11 | INDEX | SERVICE_STATUS_HISTORY_PK | 32
INDEX | SYS_C0031565 | 8 | INDEX | SERVICE_STATUS_PK | 32
INDEX | SYS_C0031567 | 8 | INDEX | SPOFFERINGASSOC_PK | 32
INDEX | SYS_C0031569 | 8 | INDEX | SP_CIDN_PK | 32
INDEX | SYS_C0031571 | 8 | INDEX | SP_CONTACT_PK | 32
INDEX | SYS_C0031617 | 8 | INDEX | SP_INDEX | 32
INDEX | SYS_C0031639 | 8 | INDEX | SP_SHORT_NAME_PK | 32
INDEX | ECS_USER_IDX | 4 | INDEX | SP_VIEWABLE_FLAG_IDX_OLD | 32
INDEX | USER_PK | 3 | INDEX | SP_WORK_TYPE_AUTH_PK | 32
TABLE | SERVICE_PROVIDER | 2 | INDEX | TIME_SLOT_PK | 32
INDEX | SERVICE_PROVIDER_PK | 1 | INDEX | WORKQUEUE_DECISION_PK | 32
INDEX | SYS_C0031561 | 0.125 | INDEX | WORK_GROUP_PK | 32
INDEX | SYS_C0031579 | 0.125 | INDEX | WORK_QUEUE_PK | 32
INDEX | SYS_C0031615 | 0.125 | INDEX | WORK_TYPE_ALLOWED_OFFERING_PK | 32
INDEX | SYS_C0031694 | 0.125 | INDEX | WORK_TYPE_CATEGORY_PK | 32
INDEX | ASSIGNED_USER_IDX | 0.0625 | INDEX | WORK_TYPE_OFFERING_PK | 32
INDEX | REQ_ITEM_STATUS_IDX | 0.0625 | INDEX | WORK_TYPE_PK | 32
INDEX | REQ_STATUS_DESC_IDX | 0.0625 | LOBINDEX | SYS_IL0000093502C00004$$ | 32
INDEX | SYS_C0038738 | 0.0625 | INDEX | LOLO_MSQ_SRV_MAP_PK | 8
TABLE | AMEND_LOCK | 0.0625 | TABLE | USERS | 6
|  |  | INDEX | ECS_USER_IDX | 2
|  |  | INDEX | USER_PK | 2
|  |  | INDEX | SERVICE_PROVIDER_PK | 1
|  |  | TABLE | SERVICE_PROVIDER | 1
|  |  | INDEX | SERVICE_NK_NUMBER_INVENTORY_PK | 0.125
|  |  | INDEX | AMEND_LOCK_PK | 0.0625
|  |  | INDEX | ASSIGNED_USER_IDX | 0.0625
|  |  | INDEX | REQ_ITEM_STATUS_IDX | 0.0625
|  |  | INDEX | REQ_STATUS_DESC_IDX | 0.0625
| Total | 104.8895 | GB |  | 118.3314 | GB
| Diff | 13.442 | GB
Reclaimable Space After retention period
| Rename LOB Object | 71.5 | GB
| Renamed Activity_history table and indexes | 12.9688 | GB
| Total | 84.4688 | GB

## C.3. ApplnSchema Object Status (hidden)
Application Schema Object Status | [5 empty] | Application Schema Object Status Summary
Before Change |  |  | After Change |  |  | Before Change |  |  | After Change
OBJECT_TYPE | OBJECT_NAME | STATUS | OBJECT_TYPE | OBJECT_NAME | STATUS | OBJECT_TYPE | STATUS | NO OBJS | OBJECT_TYPE | STATUS | NO OBJS
DATABASE_LINK | CAT | VALID | DATABASE_LINK | CAT | VALID | DATABASE_LINK | VALID | 3 | DATABASE_LINK | VALID | 3
DATABASE_LINK | LOLO | VALID | DATABASE_LINK | LOLO | VALID | FUNCTION | VALID | 5 | FUNCTION | VALID | 5
DATABASE_LINK | MYLOLOCAT | VALID | DATABASE_LINK | MYLOLOCAT | VALID | INDEX | VALID | 142 | INDEX | VALID | 142
FUNCTION | FN_APP_DATE | VALID | FUNCTION | FN_APP_DATE | VALID | LOB | VALID | 3 | LOB | VALID | 3
FUNCTION | GET_APP_REV_ID | VALID | FUNCTION | GET_APP_REV_ID | VALID | SEQUENCE | VALID | 9 | SEQUENCE | VALID | 9
FUNCTION | GET_FNN | VALID | FUNCTION | GET_FNN | VALID | SYNONYM | VALID | 13 | SYNONYM | VALID | 13
FUNCTION | GET_ORDER_NO | VALID | FUNCTION | GET_ORDER_NO | VALID | TABLE | VALID | 121 | TABLE | VALID | 121
FUNCTION | SQUIRREL_GET_ERROR_OFFSET | VALID | FUNCTION | SQUIRREL_GET_ERROR_OFFSET | VALID | VIEW | VALID | 1 | VIEW | VALID | 1
INDEX | ACTIVITY_HISTORY_PK | VALID | INDEX | ACTIVITY_HISTORY_PK | VALID | Total |  | 297 | Total |  | 297
INDEX | ACTIVITY_HISTORY_PK_OLD | VALID | INDEX | ACTIVITY_HISTORY_PK_OLD | VALID
INDEX | ACTIVITY_ID_IDX | VALID | INDEX | ACTIVITY_ID_IDX | VALID
INDEX | ACTIVITY_ID_IDX_OLD | VALID | INDEX | ACTIVITY_ID_IDX_OLD | VALID
INDEX | ACTIVITY_PK | VALID | INDEX | ACTIVITY_PK | VALID
INDEX | AH_UPDATED_DATE_IDX | VALID | INDEX | AH_UPDATED_DATE_IDX | VALID
INDEX | AH_UPDATED_DATE_IDX_OLD | VALID | INDEX | AH_UPDATED_DATE_IDX_OLD | VALID
INDEX | AMEND_LOCK_PK | VALID | INDEX | AMEND_LOCK_PK | VALID
INDEX | APPOINTMENT_REQREVNID_IDX | VALID | INDEX | APPOINTMENT_REQREVNID_IDX | VALID
INDEX | ASSIGNED_USER_IDX | VALID | INDEX | ASSIGNED_USER_IDX | VALID
INDEX | ASSIGNMENT_HISTORY_PK | VALID | INDEX | ASSIGNMENT_HISTORY_PK | VALID
INDEX | ATTRIBUTE_PK | VALID | INDEX | ATTRIBUTE_PK | VALID
INDEX | AUST_STATE_PK | VALID | INDEX | AUST_STATE_PK | VALID
INDEX | BPM_USER_PK | VALID | INDEX | BPM_USER_PK | VALID
INDEX | BUNDLE_PRODUCT_CLASS_PK | VALID | INDEX | BUNDLE_PRODUCT_CLASS_PK | VALID
INDEX | CCA_PK | VALID | INDEX | CCA_PK | VALID
INDEX | CHANGE_REQUEST_PK | VALID | INDEX | CHANGE_REQUEST_PK | VALID
INDEX | CHARAC_ASSOCIATION_PK | VALID | INDEX | CHARAC_ASSOCIATION_PK | VALID
INDEX | CHARAC_PARAM_ASSOCIATION_PK | VALID | INDEX | CHARAC_PARAM_ASSOCIATION_PK | VALID
INDEX | CHARAC_PARAMETER_PK | VALID | INDEX | CHARAC_PARAMETER_PK | VALID
INDEX | CHARACTERISTIC_PK | VALID | INDEX | CHARACTERISTIC_PK | VALID
INDEX | COMPLEX_REQUEST_ITEM_PK | VALID | INDEX | COMPLEX_REQUEST_ITEM_PK | VALID
INDEX | CRD_APPMT_REVNID_IDX | VALID | INDEX | CRD_APPMT_REVNID_IDX | VALID
INDEX | CRD_PK | VALID | INDEX | CRD_PK | VALID
INDEX | CREATED_DATE_IDX | VALID | INDEX | CREATED_DATE_IDX | VALID
INDEX | CREATED_DATE_IDX_OLD | VALID | INDEX | CREATED_DATE_IDX_OLD | VALID
INDEX | CUSTOMER_COURTESY_TITLE_PK | VALID | INDEX | CUSTOMER_COURTESY_TITLE_PK | VALID
INDEX | CUSTOMER_TYPE_PK | VALID | INDEX | CUSTOMER_TYPE_PK | VALID
INDEX | DIRECTORY_DETAILS_PK | VALID | INDEX | DIRECTORY_DETAILS_PK | VALID
INDEX | EAST_ADDRESS_TYPE_PK | VALID | INDEX | EAST_ADDRESS_TYPE_PK | VALID
INDEX | EAST_AXIS_ADDRESS_TYPE_PK | VALID | INDEX | EAST_AXIS_ADDRESS_TYPE_PK | VALID
INDEX | EAST_AXIS_STREET_TYPE_PK | VALID | INDEX | EAST_AXIS_STREET_TYPE_PK | VALID
INDEX | EAST_AXIS_STRT_TYPE_SUFFIX_PK | VALID | INDEX | EAST_AXIS_STRT_TYPE_SUFFIX_PK | VALID
INDEX | EAST_SUB_ADDRESS_TYPE_PK | VALID | INDEX | EAST_SUB_ADDRESS_TYPE_PK | VALID
INDEX | ECS_USER | VALID | INDEX | ECS_USER | VALID
INDEX | ECS_USER_IDX | VALID | INDEX | ECS_USER_IDX | VALID
INDEX | ENTRY_MEDIUM_PK | VALID | INDEX | ENTRY_MEDIUM_PK | VALID
INDEX | EQUIPMENT_PK | VALID | INDEX | EQUIPMENT_PK | VALID
INDEX | EQUIPMENT_TYPE_PK | VALID | INDEX | EQUIPMENT_TYPE_PK | VALID
INDEX | ERROR_MAPPING_PK | VALID | INDEX | ERROR_MAPPING_PK | VALID
INDEX | FK_ASSH_REQ_01 | VALID | INDEX | FK_ASSH_REQ_01 | VALID
INDEX | FK_ASSH_USERS_01 | VALID | INDEX | FK_ASSH_USERS_01 | VALID
INDEX | FK_ASSH_WQ_01 | VALID | INDEX | FK_ASSH_WQ_01 | VALID
INDEX | FK_CRIT_REQ_01 | VALID | INDEX | FK_CRIT_REQ_01 | VALID
INDEX | FK_EQUIP_ETYP_01 | VALID | INDEX | FK_EQUIP_ETYP_01 | VALID
INDEX | FK_EQUIP_RITM_01 | VALID | INDEX | FK_EQUIP_RITM_01 | VALID
INDEX | FK_QA_WG_01 | VALID | INDEX | FK_QA_WG_01 | VALID
INDEX | FK_QA_WQ_01 | VALID | INDEX | FK_QA_WQ_01 | VALID
INDEX | FK_WG_WG_01 | VALID | INDEX | FK_WG_WG_01 | VALID
INDEX | FNN_RELOCATION_RESPONSE_PK | VALID | INDEX | FNN_RELOCATION_RESPONSE_PK | VALID
INDEX | FNN_VALDN_RESP_REVID_IDX | VALID | INDEX | FNN_VALDN_RESP_REVID_IDX | VALID
INDEX | FNN_VALIDATION_RESPONSE_PK | VALID | INDEX | FNN_VALIDATION_RESPONSE_PK | VALID
INDEX | FULLY_CONFIG_SQ_RESPONSE_PK | VALID | INDEX | FULLY_CONFIG_SQ_RESPONSE_PK | VALID
INDEX | FWOM_TIME_SLOT_PK | VALID | INDEX | FWOM_TIME_SLOT_PK | VALID
INDEX | GENERAL_REFERENCE_PK | VALID | INDEX | GENERAL_REFERENCE_PK | VALID
INDEX | INSTANT_HOTLINE_PK | VALID | INDEX | INSTANT_HOTLINE_PK | VALID
INDEX | LOLO_MSQ_ATT_MAP_PK | VALID | INDEX | LOLO_MSQ_ATT_MAP_PK | VALID
INDEX | LOLO_MSQ_SRV_MAP_PK | VALID | INDEX | LOLO_MSQ_SRV_MAP_PK | VALID
INDEX | MESSAGE_ID_PK | VALID | INDEX | MESSAGE_ID_PK | VALID
INDEX | MOP_ORDER_ITEM_NOTIFICATION_PK | VALID | INDEX | MOP_ORDER_ITEM_NOTIFICATION_PK | VALID
INDEX | MOP_ORDER_PK | VALID | INDEX | MOP_ORDER_PK | VALID
INDEX | MOP_STATUS_PK | VALID | INDEX | MOP_STATUS_PK | VALID
INDEX | NK_FNN | VALID | INDEX | NK_FNN | VALID
INDEX | NOTES_PK | VALID | INDEX | NOTES_PK | VALID
INDEX | OFFERING_ATTRIBUTE_PK | VALID | INDEX | OFFERING_ATTRIBUTE_PK | VALID
INDEX | OFFERING_OFFERING_TYPE_PK | VALID | INDEX | OFFERING_OFFERING_TYPE_PK | VALID
INDEX | OFFERING_PK | VALID | INDEX | OFFERING_PK | VALID
INDEX | OFFERING_TYPE_PK | VALID | INDEX | OFFERING_TYPE_PK | VALID
INDEX | PCMS_CODE_PK | VALID | INDEX | PCMS_CODE_PK | VALID
INDEX | PLAN_PK | VALID | INDEX | PLAN_PK | VALID
INDEX | POP_LOCK_PK | VALID | INDEX | POP_LOCK_PK | VALID
INDEX | POP_RULE_ACTION_PK | VALID | INDEX | POP_RULE_ACTION_PK | VALID
INDEX | POP_RULE_BINDING_PK | VALID | INDEX | POP_RULE_BINDING_PK | VALID
INDEX | POP_RULE_CONDITION_PK | VALID | INDEX | POP_RULE_CONDITION_PK | VALID
INDEX | POSTCODE_LOCALITY_PK | VALID | INDEX | POSTCODE_LOCALITY_PK | VALID
INDEX | PRODUCT_CLASS_PK | VALID | INDEX | PRODUCT_CLASS_PK | VALID
INDEX | PROGRAMMING_PK | VALID | INDEX | PROGRAMMING_PK | VALID
INDEX | PSTS_SERVICE_PK | VALID | INDEX | PSTS_SERVICE_PK | VALID
INDEX | QUEUE_ASSIGNMENT_PK | VALID | INDEX | QUEUE_ASSIGNMENT_PK | VALID
INDEX | QUEUE_CRITERIA_PK | VALID | INDEX | QUEUE_CRITERIA_PK | VALID
INDEX | REASON_CODE_PK | VALID | INDEX | REASON_CODE_PK | VALID
INDEX | REASON_PK | VALID | INDEX | REASON_PK | VALID
INDEX | REQ_ID_IDX | VALID | INDEX | REQ_ID_IDX | VALID
INDEX | REQ_ITEM_HISTORY_IDX | VALID | INDEX | REQ_ITEM_HISTORY_IDX | VALID
INDEX | REQ_ITEM_STATUS_IDX | VALID | INDEX | REQ_ITEM_STATUS_IDX | VALID
INDEX | REQ_REVISION_IDX | VALID | INDEX | REQ_REVISION_IDX | VALID
INDEX | REQ_STATUS_CODE_IDX | VALID | INDEX | REQ_STATUS_CODE_IDX | VALID
INDEX | REQ_STATUS_DESC_IDX | VALID | INDEX | REQ_STATUS_DESC_IDX | VALID
INDEX | REQ_STATUS_IDX | VALID | INDEX | REQ_STATUS_IDX | VALID
INDEX | REQUEST_ID_PK | VALID | INDEX | REQUEST_ID_PK | VALID
INDEX | REQUEST_ITEM_PK | VALID | INDEX | REQUEST_ITEM_PK | VALID
INDEX | REQUEST_ITEM_REVISION_ID_IDX | VALID | INDEX | REQUEST_ITEM_REVISION_ID_IDX | VALID
INDEX | REQUEST_ITEM_STATUS_HISTORY_PK | VALID | INDEX | REQUEST_ITEM_STATUS_HISTORY_PK | VALID
INDEX | REQUEST_ITEM_STATUS_PK | VALID | INDEX | REQUEST_ITEM_STATUS_PK | VALID
INDEX | REQUEST_PK | VALID | INDEX | REQUEST_PK | VALID
INDEX | REQUEST_REV_IDX | VALID | INDEX | REQUEST_REV_IDX | VALID
INDEX | REQUEST_REV_IDX_OLD | VALID | INDEX | REQUEST_REV_IDX_OLD | VALID
INDEX | REQUEST_REVISDTSTAMP_IDX | VALID | INDEX | REQUEST_REVISDTSTAMP_IDX | VALID
INDEX | REQUEST_REVISION_ID_AH_IDX | VALID | INDEX | REQUEST_REVISION_ID_AH_IDX | VALID
INDEX | REQUEST_REVISION_ID_AH_IDX_OLD | VALID | INDEX | REQUEST_REVISION_ID_AH_IDX_OLD | VALID
INDEX | REQUEST_REVISION_ID_IDX | VALID | INDEX | REQUEST_REVISION_ID_IDX | VALID
INDEX | REQUEST_SPCONTACT_PK | VALID | INDEX | REQUEST_SPCONTACT_PK | VALID
INDEX | REQUEST_STATUS_HISTORY_PK | VALID | INDEX | REQUEST_STATUS_HISTORY_PK | VALID
INDEX | REQUEST_STATUS_PK | VALID | INDEX | REQUEST_STATUS_PK | VALID
INDEX | REVISION_IDX | VALID | INDEX | REVISION_IDX | VALID
INDEX | RULEACTION_PK | VALID | INDEX | RULEACTION_PK | VALID
INDEX | RULECONDITION_PK | VALID | INDEX | RULECONDITION_PK | VALID
INDEX | RULEFLITER_UK1 | VALID | INDEX | RULEFLITER_UK1 | VALID
INDEX | SDDB_ATTRIBUTE_PK | VALID | INDEX | SDDB_ATTRIBUTE_PK | VALID
INDEX | SELECTED_PRODUCT_PK | VALID | INDEX | SELECTED_PRODUCT_PK | VALID
INDEX | SERVICE_IDENTIFIER_PK | VALID | INDEX | SERVICE_IDENTIFIER_PK | VALID
INDEX | SERVICE_NK_NUMBER_INVENTORY_PK | VALID | INDEX | SERVICE_NK_NUMBER_INVENTORY_PK | VALID
INDEX | SERVICE_OFFERING_PK | VALID | INDEX | SERVICE_OFFERING_PK | VALID
INDEX | SERVICE_PROVIDER_PK | VALID | INDEX | SERVICE_PROVIDER_PK | VALID
INDEX | SERVICE_STATUS_HISTORY_PK | VALID | INDEX | SERVICE_STATUS_HISTORY_PK | VALID
INDEX | SERVICE_STATUS_PK | VALID | INDEX | SERVICE_STATUS_PK | VALID
INDEX | SERVICEABILITYRESPONSE_PK | VALID | INDEX | SERVICEABILITYRESPONSE_PK | VALID
INDEX | SP_CIDN_PK | VALID | INDEX | SP_CIDN_PK | VALID
INDEX | SP_CONTACT_PK | VALID | INDEX | SP_CONTACT_PK | VALID
INDEX | SP_GROUP_PK | VALID | INDEX | SP_GROUP_PK | VALID
INDEX | SP_INDEX | VALID | INDEX | SP_INDEX | VALID
INDEX | SP_SHORT_NAME_PK | VALID | INDEX | SP_SHORT_NAME_PK | VALID
INDEX | SP_SP_GROUP_PK | VALID | INDEX | SP_SP_GROUP_PK | VALID
INDEX | SP_VIEWABLE_FLAG_IDX | VALID | INDEX | SP_VIEWABLE_FLAG_IDX | VALID
INDEX | SP_VIEWABLE_FLAG_IDX_OLD | VALID | INDEX | SP_VIEWABLE_FLAG_IDX_OLD | VALID
INDEX | SP_WORK_TYPE_AUTH_PK | VALID | INDEX | SP_WORK_TYPE_AUTH_PK | VALID
INDEX | SPOFFERINGASSOC_PK | VALID | INDEX | SPOFFERINGASSOC_PK | VALID
INDEX | SYS_IL0000062608C00004$$ | VALID | INDEX | SYS_IL0000062608C00004$$ | VALID
INDEX | SYS_IL0000062611C00006$$ | VALID | INDEX | SYS_IL0000062611C00006$$ | VALID
INDEX | SYS_IL0000062649C00036$$ | VALID | INDEX | SYS_IL0000062649C00036$$ | VALID
INDEX | TARIFF_PK | VALID | INDEX | TARIFF_PK | VALID
INDEX | TIME_SLOT_PK | VALID | INDEX | TIME_SLOT_PK | VALID
INDEX | TPSQL_IDX | VALID | INDEX | TPSQL_IDX | VALID
INDEX | UK_SPG_01 | VALID | INDEX | UK_SPG_01 | VALID
INDEX | USER_PK | VALID | INDEX | USER_PK | VALID
INDEX | WORK_GROUP_PK | VALID | INDEX | WORK_GROUP_PK | VALID
INDEX | WORK_QUEUE_PK | VALID | INDEX | WORK_QUEUE_PK | VALID
INDEX | WORK_TYPE_ALLOWED_OFFERING_PK | VALID | INDEX | WORK_TYPE_ALLOWED_OFFERING_PK | VALID
INDEX | WORK_TYPE_CATEGORY_PK | VALID | INDEX | WORK_TYPE_CATEGORY_PK | VALID
INDEX | WORK_TYPE_OFFERING_PK | VALID | INDEX | WORK_TYPE_OFFERING_PK | VALID
INDEX | WORK_TYPE_PK | VALID | INDEX | WORK_TYPE_PK | VALID
INDEX | WORKQUEUE_DECISION_PK | VALID | INDEX | WORKQUEUE_DECISION_PK | VALID
LOB | SYS_LOB0000062608C00004$$ | VALID | LOB | SYS_LOB0000062608C00004$$ | VALID
LOB | SYS_LOB0000062611C00006$$ | VALID | LOB | SYS_LOB0000062611C00006$$ | VALID
LOB | SYS_LOB0000062649C00036$$ | VALID | LOB | SYS_LOB0000062649C00036$$ | VALID
SEQUENCE | LOLIG_SEQUENCE | VALID | SEQUENCE | LOLIG_SEQUENCE | VALID
SEQUENCE | ORDER_SEQ | VALID | SEQUENCE | ORDER_SEQ | VALID
SEQUENCE | ORDERID_SEQ | VALID | SEQUENCE | ORDERID_SEQ | VALID
SEQUENCE | ORDERITEM_SEQ | VALID | SEQUENCE | ORDERITEM_SEQ | VALID
SEQUENCE | ORDERITEMID_SEQ | VALID | SEQUENCE | ORDERITEMID_SEQ | VALID
SEQUENCE | REQUEST_SEQ | VALID | SEQUENCE | REQUEST_SEQ | VALID
SEQUENCE | REQUESTID_SEQ | VALID | SEQUENCE | REQUESTID_SEQ | VALID
SEQUENCE | REQUESTITEM_SEQ | VALID | SEQUENCE | REQUESTITEM_SEQ | VALID
SEQUENCE | REQUESTITEMID_SEQ | VALID | SEQUENCE | REQUESTITEMID_SEQ | VALID
SYNONYM | ATTRIBUTE_1 | VALID | SYNONYM | ATTRIBUTE_1 | VALID
SYNONYM | ATTRIBUTE_VALUE_1 | VALID | SYNONYM | ATTRIBUTE_VALUE_1 | VALID
SYNONYM | AUST_STATE_1 | VALID | SYNONYM | AUST_STATE_1 | VALID
SYNONYM | OFFERING_ATTRIBUTE_1 | VALID | SYNONYM | OFFERING_ATTRIBUTE_1 | VALID
SYNONYM | OFFERING_OFFERING_TYPE_1 | VALID | SYNONYM | OFFERING_OFFERING_TYPE_1 | VALID
SYNONYM | OFFERING_TYPE_1 | VALID | SYNONYM | OFFERING_TYPE_1 | VALID
SYNONYM | REQUEST_ITEM_STATUS_HISTORY_1 | VALID | SYNONYM | REQUEST_ITEM_STATUS_HISTORY_1 | VALID
SYNONYM | REQUEST_STATUS_1 | VALID | SYNONYM | REQUEST_STATUS_1 | VALID
SYNONYM | REQUEST_STATUS_HISTORY_1 | VALID | SYNONYM | REQUEST_STATUS_HISTORY_1 | VALID
SYNONYM | SERVICE_OFFERING_1 | VALID | SYNONYM | SERVICE_OFFERING_1 | VALID
SYNONYM | SERVICE_OFFERING_SETTING_1 | VALID | SYNONYM | SERVICE_OFFERING_SETTING_1 | VALID
SYNONYM | WORK_TYPE_1 | VALID | SYNONYM | WORK_TYPE_1 | VALID
SYNONYM | WORK_TYPE_CATEGORY_1 | VALID | SYNONYM | WORK_TYPE_CATEGORY_1 | VALID
TABLE | ACTIVITY | VALID | TABLE | ACTIVITY | VALID
TABLE | ACTIVITY_HISTORY | VALID | TABLE | ACTIVITY_HISTORY | VALID
TABLE | ACTIVITY_HISTORY_OLD | VALID | TABLE | ACTIVITY_HISTORY_OLD | VALID
TABLE | ADDRESS | VALID | TABLE | ADDRESS | VALID
TABLE | AMEND_LOCK | VALID | TABLE | AMEND_LOCK | VALID
TABLE | APPOINTMENT | VALID | TABLE | APPOINTMENT | VALID
TABLE | ASSIGNMENT_HISTORY | VALID | TABLE | ASSIGNMENT_HISTORY | VALID
TABLE | ATTRIBUTE | VALID | TABLE | ATTRIBUTE | VALID
TABLE | ATTRIBUTE_VALUE | VALID | TABLE | ATTRIBUTE_VALUE | VALID
TABLE | AUST_STATE | VALID | TABLE | AUST_STATE | VALID
TABLE | BPM_USERS | VALID | TABLE | BPM_USERS | VALID
TABLE | BUNDLE | VALID | TABLE | BUNDLE | VALID
TABLE | BUNDLE_NETWORK_TYPE | VALID | TABLE | BUNDLE_NETWORK_TYPE | VALID
TABLE | BUNDLE_PRODUCT_CLASS | VALID | TABLE | BUNDLE_PRODUCT_CLASS | VALID
TABLE | CCA | VALID | TABLE | CCA | VALID
TABLE | CHAINED_ROWS | VALID | TABLE | CHAINED_ROWS | VALID
TABLE | CHANGE_REQUEST | VALID | TABLE | CHANGE_REQUEST | VALID
TABLE | CHANNEL | VALID | TABLE | CHANNEL | VALID
TABLE | CHARAC_ASSOCIATION | VALID | TABLE | CHARAC_ASSOCIATION | VALID
TABLE | CHARAC_PARAM_ASSOCIATION | VALID | TABLE | CHARAC_PARAM_ASSOCIATION | VALID
TABLE | CHARAC_PARAM_VALUE | VALID | TABLE | CHARAC_PARAM_VALUE | VALID
TABLE | CHARAC_PARAMETER | VALID | TABLE | CHARAC_PARAMETER | VALID
TABLE | CHARACTERISTIC | VALID | TABLE | CHARACTERISTIC | VALID
TABLE | COMPLEX_REQUEST_ITEM | VALID | TABLE | COMPLEX_REQUEST_ITEM | VALID
TABLE | CRD | VALID | TABLE | CRD | VALID
TABLE | CUSTOMER | VALID | TABLE | CUSTOMER | VALID
TABLE | CUSTOMER_COURTESY_TITLE | VALID | TABLE | CUSTOMER_COURTESY_TITLE | VALID
TABLE | CUSTOMER_TYPE | VALID | TABLE | CUSTOMER_TYPE | VALID
TABLE | DIRECTORY_DETAILS | VALID | TABLE | DIRECTORY_DETAILS | VALID
TABLE | EAST_ADDRESS_TYPE | VALID | TABLE | EAST_ADDRESS_TYPE | VALID
TABLE | EAST_AXIS_ADDRESS_TYPE | VALID | TABLE | EAST_AXIS_ADDRESS_TYPE | VALID
TABLE | EAST_AXIS_STREET_TYPE | VALID | TABLE | EAST_AXIS_STREET_TYPE | VALID
TABLE | EAST_AXIS_STREET_TYPE_SUFFIX | VALID | TABLE | EAST_AXIS_STREET_TYPE_SUFFIX | VALID
TABLE | EAST_SUB_ADDRESS_TYPE | VALID | TABLE | EAST_SUB_ADDRESS_TYPE | VALID
TABLE | ENTRY_MEDIUM | VALID | TABLE | ENTRY_MEDIUM | VALID
TABLE | EQUIPMENT | VALID | TABLE | EQUIPMENT | VALID
TABLE | EQUIPMENT_TYPE | VALID | TABLE | EQUIPMENT_TYPE | VALID
TABLE | ERROR_MAPPING | VALID | TABLE | ERROR_MAPPING | VALID
TABLE | FNN_RELOCATION_RESPONSE | VALID | TABLE | FNN_RELOCATION_RESPONSE | VALID
TABLE | FNN_VALIDATION_RESPONSE | VALID | TABLE | FNN_VALIDATION_RESPONSE | VALID
TABLE | FULLY_CONFIG_SQ_RESPONSE | VALID | TABLE | FULLY_CONFIG_SQ_RESPONSE | VALID
TABLE | FWOM_TIME_SLOT | VALID | TABLE | FWOM_TIME_SLOT | VALID
TABLE | GENERAL_REFERENCE | VALID | TABLE | GENERAL_REFERENCE | VALID
TABLE | INSTANT_HOTLINE | VALID | TABLE | INSTANT_HOTLINE | VALID
TABLE | LOLO_FWOM_REASON_MAP | VALID | TABLE | LOLO_FWOM_REASON_MAP | VALID
TABLE | LOLO_MSQ_ATT_MAP | VALID | TABLE | LOLO_MSQ_ATT_MAP | VALID
TABLE | LOLO_MSQ_SRV_MAP | VALID | TABLE | LOLO_MSQ_SRV_MAP | VALID
TABLE | MESSAGE | VALID | TABLE | MESSAGE | VALID
TABLE | MOP_ORDER | VALID | TABLE | MOP_ORDER | VALID
TABLE | MOP_ORDER_ITEM | VALID | TABLE | MOP_ORDER_ITEM | VALID
TABLE | MOP_ORDER_ITEM_NOTIFICATION | VALID | TABLE | MOP_ORDER_ITEM_NOTIFICATION | VALID
TABLE | MOP_SERVICE_INVENTORY | VALID | TABLE | MOP_SERVICE_INVENTORY | VALID
TABLE | MOP_STATUS | VALID | TABLE | MOP_STATUS | VALID
TABLE | NOTES | VALID | TABLE | NOTES | VALID
TABLE | OFFERING | VALID | TABLE | OFFERING | VALID
TABLE | OFFERING_ATTRIBUTE | VALID | TABLE | OFFERING_ATTRIBUTE | VALID
TABLE | OFFERING_BUNDLE_ASSOCIATION | VALID | TABLE | OFFERING_BUNDLE_ASSOCIATION | VALID
TABLE | OFFERING_CATEGORY | VALID | TABLE | OFFERING_CATEGORY | VALID
TABLE | OFFERING_OFFERING_TYPE | VALID | TABLE | OFFERING_OFFERING_TYPE | VALID
TABLE | OFFERING_TYPE | VALID | TABLE | OFFERING_TYPE | VALID
TABLE | PCMS_CODE | VALID | TABLE | PCMS_CODE | VALID
TABLE | POP_LOCK | VALID | TABLE | POP_LOCK | VALID
TABLE | POP_RULE_ACTION | VALID | TABLE | POP_RULE_ACTION | VALID
TABLE | POP_RULE_BINDING | VALID | TABLE | POP_RULE_BINDING | VALID
TABLE | POP_RULE_CONDITION | VALID | TABLE | POP_RULE_CONDITION | VALID
TABLE | PORT_CHURN_INFO | VALID | TABLE | PORT_CHURN_INFO | VALID
TABLE | POSTCODE_LOCALITY | VALID | TABLE | POSTCODE_LOCALITY | VALID
TABLE | PRODUCT_CLASS | VALID | TABLE | PRODUCT_CLASS | VALID
TABLE | PRODUCT_CLASS_OFFERING | VALID | TABLE | PRODUCT_CLASS_OFFERING | VALID
TABLE | PROGRAMMING | VALID | TABLE | PROGRAMMING | VALID
TABLE | PSTS_SERVICE | VALID | TABLE | PSTS_SERVICE | VALID
TABLE | QUEUE_ASSIGNMENT | VALID | TABLE | QUEUE_ASSIGNMENT | VALID
TABLE | QUEUE_CRITERIA | VALID | TABLE | QUEUE_CRITERIA | VALID
TABLE | REASON | VALID | TABLE | REASON | VALID
TABLE | REQUEST | VALID | TABLE | REQUEST | VALID
TABLE | REQUEST_ITEM | VALID | TABLE | REQUEST_ITEM | VALID
TABLE | REQUEST_ITEM_STATUS | VALID | TABLE | REQUEST_ITEM_STATUS | VALID
TABLE | REQUEST_ITEM_STATUS_HISTORY | VALID | TABLE | REQUEST_ITEM_STATUS_HISTORY | VALID
TABLE | REQUEST_SPCONTACT | VALID | TABLE | REQUEST_SPCONTACT | VALID
TABLE | REQUEST_STATUS | VALID | TABLE | REQUEST_STATUS | VALID
TABLE | REQUEST_STATUS_HISTORY | VALID | TABLE | REQUEST_STATUS_HISTORY | VALID
TABLE | RULEACTION | VALID | TABLE | RULEACTION | VALID
TABLE | RULECONDITION | VALID | TABLE | RULECONDITION | VALID
TABLE | RULEFLITER | VALID | TABLE | RULEFLITER | VALID
TABLE | SDDB_ATTRIBUTE | VALID | TABLE | SDDB_ATTRIBUTE | VALID
TABLE | SELECTED_PRODUCT | VALID | TABLE | SELECTED_PRODUCT | VALID
TABLE | SERVICE | VALID | TABLE | SERVICE | VALID
TABLE | SERVICE_AREA_ASSOCIATION | VALID | TABLE | SERVICE_AREA_ASSOCIATION | VALID
TABLE | SERVICE_IDENTIFIER | VALID | TABLE | SERVICE_IDENTIFIER | VALID
TABLE | SERVICE_NK_NUMBER_INVENTORY | VALID | TABLE | SERVICE_NK_NUMBER_INVENTORY | VALID
TABLE | SERVICE_OFFERING | VALID | TABLE | SERVICE_OFFERING | VALID
TABLE | SERVICE_OFFERING_SETTING | VALID | TABLE | SERVICE_OFFERING_SETTING | VALID
TABLE | SERVICE_PROVIDER | VALID | TABLE | SERVICE_PROVIDER | VALID
TABLE | SERVICE_STATUS | VALID | TABLE | SERVICE_STATUS | VALID
TABLE | SERVICE_STATUS_HISTORY | VALID | TABLE | SERVICE_STATUS_HISTORY | VALID
TABLE | SERVICEABILITY_RESPONSE | VALID | TABLE | SERVICEABILITY_RESPONSE | VALID
TABLE | SP_BUNDLE | VALID | TABLE | SP_BUNDLE | VALID
TABLE | SP_CIDN | VALID | TABLE | SP_CIDN | VALID
TABLE | SP_CONTACT | VALID | TABLE | SP_CONTACT | VALID
TABLE | SP_GROUP | VALID | TABLE | SP_GROUP | VALID
TABLE | SP_OFFERING | VALID | TABLE | SP_OFFERING | VALID
TABLE | SP_OFFERING_ASSOCIATION | VALID | TABLE | SP_OFFERING_ASSOCIATION | VALID
TABLE | SP_SHORT_NAME | VALID | TABLE | SP_SHORT_NAME | VALID
TABLE | SP_SP_GROUP | VALID | TABLE | SP_SP_GROUP | VALID
TABLE | SP_WORK_TYPE_AUTH | VALID | TABLE | SP_WORK_TYPE_AUTH | VALID
TABLE | SQ_MAPPING | VALID | TABLE | SQ_MAPPING | VALID
TABLE | SYS_TEMP_FBT | VALID | TABLE | SYS_TEMP_FBT | VALID
TABLE | T_ERROR_CODE_MAST | VALID | TABLE | T_ERROR_CODE_MAST | VALID
TABLE | TARIFF | VALID | TABLE | TARIFF | VALID
TABLE | TBL_AUDIT_LOLIG | VALID | TABLE | TBL_AUDIT_LOLIG | VALID
TABLE | TIME_SLOT | VALID | TABLE | TIME_SLOT | VALID
TABLE | TOAD_PLAN_SQL | VALID | TABLE | TOAD_PLAN_SQL | VALID
TABLE | TOAD_PLAN_TABLE | VALID | TABLE | TOAD_PLAN_TABLE | VALID
TABLE | USERS | VALID | TABLE | USERS | VALID
TABLE | WORK_GROUP | VALID | TABLE | WORK_GROUP | VALID
TABLE | WORK_QUEUE | VALID | TABLE | WORK_QUEUE | VALID
TABLE | WORK_TYPE | VALID | TABLE | WORK_TYPE | VALID
TABLE | WORK_TYPE_ALLOWED_OFFERING | VALID | TABLE | WORK_TYPE_ALLOWED_OFFERING | VALID
TABLE | WORK_TYPE_CATEGORY | VALID | TABLE | WORK_TYPE_CATEGORY | VALID
TABLE | WORK_TYPE_OFFERING | VALID | TABLE | WORK_TYPE_OFFERING | VALID
TABLE | WORKQUEUE_DECISION | VALID | TABLE | WORKQUEUE_DECISION | VALID
VIEW | PCMS_CODE_OFFERING_VIEW | VALID | VIEW | PCMS_CODE_OFFERING_VIEW | VALID

## C.4.Appln.Table Constrai Status (hidden)
Application Table Constraint Status Details | [5 empty] | Disabled Constraints | [5 empty] | Application Object Constraint Summary
Before Rename |  |  | After Rename |  |  | Before Change |  | Forecasted |  | After Change |  | Before Rename |  |  | After Rename
CONSTRAINT_TYPE | CONSTRAINT_NAME | STATUS | CONSTRAINT_TYPE | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_TYPE | STATUS | No.Cons | CONSTRAINT_TYPE | STATUS | No.Cons
CK | WORK_QUEUE_DELFLG_CK | ENABLED | CK | WORK_QUEUE_DELFLG_CK | ENABLED | CHANGE_REQUEST_FK | DISABLED | CHANGE_REQUEST_FK | DISABLED | CHANGE_REQUEST_FK | DISABLED | CK | ENABLED | 16 | CK | ENABLED | 16
CK | POP_RULE_CONDITION_CK | ENABLED | CK | POP_RULE_CONDITION_CK | ENABLED | MOP_STATUS_FK | DISABLED | MOP_STATUS_FK | DISABLED | MOP_STATUS_FK | DISABLED | FK | DISABLED | 12 | FK | DISABLED | 12
CK | SYS_C0031655 | ENABLED | CK | SYS_C0031655 | ENABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED | FK | ENABLED | 32 | FK | ENABLED | 32
CK | SYS_C0031656 | ENABLED | CK | SYS_C0031656 | ENABLED | PARENT_MESSAGE_ID_FK | DISABLED | PARENT_MESSAGE_ID_FK | DISABLED | PARENT_MESSAGE_ID_FK | DISABLED | PK | ENABLED | 94 | PK | ENABLED | 94
CK | AUST_STATE_CK | ENABLED | CK | AUST_STATE_CK | ENABLED | PARENT_SERV_OFF_FK | DISABLED | PARENT_SERV_OFF_FK | DISABLED | PARENT_SERV_OFF_FK | DISABLED | UK | ENABLED | 2 | UK | ENABLED | 2
CK | WORK_TYPE_CATEGORY_CK | ENABLED | CK | WORK_TYPE_CATEGORY_CK | ENABLED | REASON_CODE_FK | DISABLED | REASON_CODE_FK | DISABLED | REASON_CODE_FK | DISABLED | Total |  | 156 | Total |  | 156
CK | SYS_C0032034 | ENABLED | CK | SYS_C0032034 | ENABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED
CK | POP_RULE_CONDN_RULE_CONDN_CK | ENABLED | CK | POP_RULE_CONDN_RULE_CONDN_CK | ENABLED | RQST_STATUS_STATUSHIST_FK | DISABLED | RQST_STATUS_STATUSHIST_FK | DISABLED | RQST_STATUS_STATUSHIST_FK | DISABLED
CK | WORK_TYPE_CATEGORY_DELFLG_CK | ENABLED | CK | WORK_TYPE_CATEGORY_DELFLG_CK | ENABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED
CK | SYS_C0032036 | ENABLED | CK | SYS_C0032036 | ENABLED | SP_WORK_TYPE_AUTH_FK | DISABLED | SP_WORK_TYPE_AUTH_FK | DISABLED | SP_WORK_TYPE_AUTH_FK | DISABLED
CK | SYS_C0032037 | ENABLED | CK | SYS_C0032037 | ENABLED | SPOFFERINGASSOC_ATT_FK | DISABLED | SPOFFERINGASSOC_ATT_FK | DISABLED | SPOFFERINGASSOC_ATT_FK | DISABLED
CK | POP_RULE_ACTION_CK | ENABLED | CK | POP_RULE_ACTION_CK | ENABLED | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | WORKTYPE_CAT_WORKTYPE_FK | DISABLED
CK | EQUIPMENT_CK | ENABLED | CK | EQUIPMENT_CK | ENABLED
CK | SP_SHORT_NAME_CK | ENABLED | CK | SP_SHORT_NAME_CK | ENABLED
CK | EQUIPMENT_DELVMD_CK | ENABLED | CK | EQUIPMENT_DELVMD_CK | ENABLED
CK | WORK_QUEUE_CK | ENABLED | CK | WORK_QUEUE_CK | ENABLED
FK | FK_QA_WORK_QUEUE_1 | ENABLED | FK | FK_QA_WORK_QUEUE_1 | ENABLED | CK - Check
FK | ASSIGNMENT_HISTORY_FK | ENABLED | FK | ASSIGNMENT_HISTORY_FK | ENABLED | FK - Reference
FK | ACTIVITY_HISTORY_FK | ENABLED | FK | ACTIVITY_HISTORY_FK | ENABLED | PK - Primary Key
FK | AHOLD_HISTORY_FK | ENABLED | FK | AHOLD_HISTORY_FK | ENABLED | UK - Unique Key
FK | OFFER_ATTT_FK | ENABLED | FK | OFFER_ATTT_FK | ENABLED
FK | LOLO_MSQ_ATT_ATTRIBUTE_FK | ENABLED | FK | LOLO_MSQ_ATT_ATTRIBUTE_FK | ENABLED
FK | SPOFFERINGASSOC_ATT_FK | DISABLED | FK | SPOFFERINGASSOC_ATT_FK | DISABLED
FK | POSTCODE_LOCALITY_FK | ENABLED | FK | POSTCODE_LOCALITY_FK | ENABLED
FK | PARENT_MESSAGE_ID_FK | DISABLED | FK | PARENT_MESSAGE_ID_FK | DISABLED
FK | OFFERTYPE_OFFERING_OT_FK | DISABLED | FK | OFFERTYPE_OFFERING_OT_FK | DISABLED
FK | CHANGE_REQUEST_FK | DISABLED | FK | CHANGE_REQUEST_FK | DISABLED
FK | REASON_CODE_FK | DISABLED | FK | REASON_CODE_FK | DISABLED
FK | RQSTITEM_REASON_CODE_FK | ENABLED | FK | RQSTITEM_REASON_CODE_FK | ENABLED
FK | RI_STATUSHIST_RI_STATUS_FK | DISABLED | FK | RI_STATUSHIST_RI_STATUS_FK | DISABLED
FK | REQUEST_ITEM_FK | ENABLED | FK | REQUEST_ITEM_FK | ENABLED
FK | SP_CONACT_ID_FK | ENABLED | FK | SP_CONACT_ID_FK | ENABLED
FK | RQST_STATUS_STATUSHIST_FK | DISABLED | FK | RQST_STATUS_STATUSHIST_FK | DISABLED
FK | FK_REQ_RSTAT_01 | ENABLED | FK | FK_REQ_RSTAT_01 | ENABLED
FK | PARENT_SERV_OFF_FK | DISABLED | FK | PARENT_SERV_OFF_FK | DISABLED
FK | MOP_STATUS_FK | DISABLED | FK | MOP_STATUS_FK | DISABLED
FK | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | FK | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED
FK | SRGROUP_SP_GROUP_FK | ENABLED | FK | SRGROUP_SP_GROUP_FK | ENABLED
FK | WTAO_WTID_FK | ENABLED | FK | WTAO_WTID_FK | ENABLED
FK | SP_WORK_TYPE_AUTH_FK | DISABLED | FK | SP_WORK_TYPE_AUTH_FK | DISABLED
FK | REQUESTITAM_WORKTYPE_FK | ENABLED | FK | REQUESTITAM_WORKTYPE_FK | ENABLED
FK | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | FK | WORKTYPE_CAT_WORKTYPE_FK | DISABLED
FK | USER_SPD_FK | ENABLED | FK | USER_SPD_FK | ENABLED
FK | REQUEST_FK | ENABLED | FK | REQUEST_FK | ENABLED
FK | QUEUE_ASSIGNMENT_FK | ENABLED | FK | QUEUE_ASSIGNMENT_FK | ENABLED
FK | USERS_FK | ENABLED | FK | USERS_FK | ENABLED
FK | FNN_REL_RSP_REQSTITAM_FK | ENABLED | FK | FNN_REL_RSP_REQSTITAM_FK | ENABLED
FK | FNN_VLD_RSP_REQSTITAM_FK | ENABLED | FK | FNN_VLD_RSP_REQSTITAM_FK | ENABLED
FK | RQST_RQSTITEM_FK | ENABLED | FK | RQST_RQSTITEM_FK | ENABLED
FK | PCO_PRDID_FK | ENABLED | FK | PCO_PRDID_FK | ENABLED
FK | OFFERING_PCMS_CODE_FK | ENABLED | FK | OFFERING_PCMS_CODE_FK | ENABLED
FK | PCO_OFFID_FK | ENABLED | FK | PCO_OFFID_FK | ENABLED
FK | WTAO_OFFID_FK | ENABLED | FK | WTAO_OFFID_FK | ENABLED
FK | EQUIPMENT_FK | ENABLED | FK | EQUIPMENT_FK | ENABLED
FK | CHARAC_PARAM_ASSOC_ID_FK | ENABLED | FK | CHARAC_PARAM_ASSOC_ID_FK | ENABLED
FK | CHARAC_PARAM_ID_FK | ENABLED | FK | CHARAC_PARAM_ID_FK | ENABLED
FK | CHARAC_ASSOC_ID_FK | ENABLED | FK | CHARAC_ASSOC_ID_FK | ENABLED
FK | CHARACTERISTIC_FK_01 | ENABLED | FK | CHARACTERISTIC_FK_01 | ENABLED
FK | RQSTITAM_BUNDLE_FK | ENABLED | FK | RQSTITAM_BUNDLE_FK | ENABLED
FK | CHARACTERISTIC_FK | ENABLED | FK | CHARACTERISTIC_FK | ENABLED
PK | EAST_AXIS_STRT_TYPE_SUFFIX_PK | ENABLED | PK | EAST_AXIS_STRT_TYPE_SUFFIX_PK | ENABLED
PK | LOLO_MSQ_SRV_MAP_PK | ENABLED | PK | LOLO_MSQ_SRV_MAP_PK | ENABLED
PK | INSTANT_HOTLINE_PK | ENABLED | PK | INSTANT_HOTLINE_PK | ENABLED
PK | DIRECTORY_DETAILS_PK | ENABLED | PK | DIRECTORY_DETAILS_PK | ENABLED
PK | CHARAC_PARAM_ASSOCIATION_PK | ENABLED | PK | CHARAC_PARAM_ASSOCIATION_PK | ENABLED
PK | CHARAC_PARAMETER_PK | ENABLED | PK | CHARAC_PARAMETER_PK | ENABLED
PK | CHARACTERISTIC_PK | ENABLED | PK | CHARACTERISTIC_PK | ENABLED
PK | FWOM_TIME_SLOT_PK | ENABLED | PK | FWOM_TIME_SLOT_PK | ENABLED
PK | FULLY_CONFIG_SQ_RESPONSE_PK | ENABLED | PK | FULLY_CONFIG_SQ_RESPONSE_PK | ENABLED
PK | ENTRY_MEDIUM_PK | ENABLED | PK | ENTRY_MEDIUM_PK | ENABLED
PK | EAST_AXIS_STREET_TYPE_PK | ENABLED | PK | EAST_AXIS_STREET_TYPE_PK | ENABLED
PK | EAST_AXIS_ADDRESS_TYPE_PK | ENABLED | PK | EAST_AXIS_ADDRESS_TYPE_PK | ENABLED
PK | EAST_ADDRESS_TYPE_PK | ENABLED | PK | EAST_ADDRESS_TYPE_PK | ENABLED
PK | CUSTOMER_TYPE_PK | ENABLED | PK | CUSTOMER_TYPE_PK | ENABLED
PK | CUSTOMER_COURTESY_TITLE_PK | ENABLED | PK | CUSTOMER_COURTESY_TITLE_PK | ENABLED
PK | ACTIVITY_HISTORY_PK | ENABLED | PK | ACTIVITY_HISTORY_PK | ENABLED
PK | PCMS_CODE_PK | ENABLED | PK | PCMS_CODE_PK | ENABLED
PK | OFFERING_OFFERING_TYPE_PK | ENABLED | PK | OFFERING_OFFERING_TYPE_PK | ENABLED
PK | EQUIPMENT_TYPE_PK | ENABLED | PK | EQUIPMENT_TYPE_PK | ENABLED
PK | EQUIPMENT_PK | ENABLED | PK | EQUIPMENT_PK | ENABLED
PK | EAST_SUB_ADDRESS_TYPE_PK | ENABLED | PK | EAST_SUB_ADDRESS_TYPE_PK | ENABLED
PK | CHANGE_REQUEST_PK | ENABLED | PK | CHANGE_REQUEST_PK | ENABLED
PK | AUST_STATE_PK | ENABLED | PK | AUST_STATE_PK | ENABLED
PK | SP_CIDN_PK | ENABLED | PK | SP_CIDN_PK | ENABLED
PK | SERVICE_PROVIDER_PK | ENABLED | PK | SERVICE_PROVIDER_PK | ENABLED
PK | ASSIGNMENT_HISTORY_PK | ENABLED | PK | ASSIGNMENT_HISTORY_PK | ENABLED
PK | CHARAC_ASSOCIATION_PK | ENABLED | PK | CHARAC_ASSOCIATION_PK | ENABLED
PK | ATTRIBUTE_PK | ENABLED | PK | ATTRIBUTE_PK | ENABLED
PK | WORK_TYPE_ALLOWED_OFFERING_PK | ENABLED | PK | WORK_TYPE_ALLOWED_OFFERING_PK | ENABLED
PK | WORK_TYPE_PK | ENABLED | PK | WORK_TYPE_PK | ENABLED
PK | ACTIVITY_PK | ENABLED | PK | ACTIVITY_PK | ENABLED
PK | AHOLD_HISTORY_PK | ENABLED | PK | AHOLD_HISTORY_PK | ENABLED
PK | WORK_TYPE_CATEGORY_PK | ENABLED | PK | WORK_TYPE_CATEGORY_PK | ENABLED
PK | WORKQUEUE_DECISION_PK | ENABLED | PK | WORKQUEUE_DECISION_PK | ENABLED
PK | TIME_SLOT_PK | ENABLED | PK | TIME_SLOT_PK | ENABLED
PK | CCA_PK | ENABLED | PK | CCA_PK | ENABLED
PK | WORK_QUEUE_PK | ENABLED | PK | WORK_QUEUE_PK | ENABLED
PK | WORK_TYPE_OFFERING_PK | ENABLED | PK | WORK_TYPE_OFFERING_PK | ENABLED
PK | SP_WORK_TYPE_AUTH_PK | ENABLED | PK | SP_WORK_TYPE_AUTH_PK | ENABLED
PK | SPOFFERINGASSOC_PK | ENABLED | PK | SPOFFERINGASSOC_PK | ENABLED
PK | WORK_GROUP_PK | ENABLED | PK | WORK_GROUP_PK | ENABLED
PK | SP_GROUP_PK | ENABLED | PK | SP_GROUP_PK | ENABLED
PK | COMPLEX_REQUEST_ITEM_PK | ENABLED | PK | COMPLEX_REQUEST_ITEM_PK | ENABLED
PK | SERVICE_STATUS_HISTORY_PK | ENABLED | PK | SERVICE_STATUS_HISTORY_PK | ENABLED
PK | TARIFF_PK | ENABLED | PK | TARIFF_PK | ENABLED
PK | USER_PK | ENABLED | PK | USER_PK | ENABLED
PK | SERVICE_OFFERING_PK | ENABLED | PK | SERVICE_OFFERING_PK | ENABLED
PK | SERVICE_IDENTIFIER_PK | ENABLED | PK | SERVICE_IDENTIFIER_PK | ENABLED
PK | SERVICEABILITYRESPONSE_PK | ENABLED | PK | SERVICEABILITYRESPONSE_PK | ENABLED
PK | SELECTED_PRODUCT_PK | ENABLED | PK | SELECTED_PRODUCT_PK | ENABLED
PK | SP_SP_GROUP_PK | ENABLED | PK | SP_SP_GROUP_PK | ENABLED
PK | RULECONDITION_PK | ENABLED | PK | RULECONDITION_PK | ENABLED
PK | RULEACTION_PK | ENABLED | PK | RULEACTION_PK | ENABLED
PK | SP_CONTACT_PK | ENABLED | PK | SP_CONTACT_PK | ENABLED
PK | SP_SHORT_NAME_PK | ENABLED | PK | SP_SHORT_NAME_PK | ENABLED
PK | REQUEST_SPCONTACT_PK | ENABLED | PK | REQUEST_SPCONTACT_PK | ENABLED
PK | REQUEST_STATUS_HISTORY_PK | ENABLED | PK | REQUEST_STATUS_HISTORY_PK | ENABLED
PK | REQUEST_STATUS_PK | ENABLED | PK | REQUEST_STATUS_PK | ENABLED
PK | SERVICE_STATUS_PK | ENABLED | PK | SERVICE_STATUS_PK | ENABLED
PK | REQUEST_PK | ENABLED | PK | REQUEST_PK | ENABLED
PK | SDDB_ATTRIBUTE_PK | ENABLED | PK | SDDB_ATTRIBUTE_PK | ENABLED
PK | REQUEST_ITEM_STATUS_HISTORY_PK | ENABLED | PK | REQUEST_ITEM_STATUS_HISTORY_PK | ENABLED
PK | REQUEST_ITEM_STATUS_PK | ENABLED | PK | REQUEST_ITEM_STATUS_PK | ENABLED
PK | QUEUE_CRITERIA_PK | ENABLED | PK | QUEUE_CRITERIA_PK | ENABLED
PK | QUEUE_ASSIGNMENT_PK | ENABLED | PK | QUEUE_ASSIGNMENT_PK | ENABLED
PK | PRODUCT_CLASS_PK | ENABLED | PK | PRODUCT_CLASS_PK | ENABLED
PK | REQUEST_ITEM_PK | ENABLED | PK | REQUEST_ITEM_PK | ENABLED
PK | POP_RULE_CONDITION_PK | ENABLED | PK | POP_RULE_CONDITION_PK | ENABLED
PK | POP_RULE_BINDING_PK | ENABLED | PK | POP_RULE_BINDING_PK | ENABLED
PK | POP_RULE_ACTION_PK | ENABLED | PK | POP_RULE_ACTION_PK | ENABLED
PK | AMEND_LOCK_PK | ENABLED | PK | AMEND_LOCK_PK | ENABLED
PK | PSTS_SERVICE_PK | ENABLED | PK | PSTS_SERVICE_PK | ENABLED
PK | PROGRAMMING_PK | ENABLED | PK | PROGRAMMING_PK | ENABLED
PK | OFFERING_TYPE_PK | ENABLED | PK | OFFERING_TYPE_PK | ENABLED
PK | REASON_PK | ENABLED | PK | REASON_PK | ENABLED
PK | OFFERING_PK | ENABLED | PK | OFFERING_PK | ENABLED
PK | POSTCODE_LOCALITY_PK | ENABLED | PK | POSTCODE_LOCALITY_PK | ENABLED
PK | OFFERING_ATTRIBUTE_PK | ENABLED | PK | OFFERING_ATTRIBUTE_PK | ENABLED
PK | NOTES_PK | ENABLED | PK | NOTES_PK | ENABLED
PK | MOP_STATUS_PK | ENABLED | PK | MOP_STATUS_PK | ENABLED
PK | MESSAGE_ID_PK | ENABLED | PK | MESSAGE_ID_PK | ENABLED
PK | SERVICE_NK_NUMBER_INVENTORY_PK | ENABLED | PK | SERVICE_NK_NUMBER_INVENTORY_PK | ENABLED
PK | POP_LOCK_PK | ENABLED | PK | POP_LOCK_PK | ENABLED
PK | REASON_CODE_PK | ENABLED | PK | REASON_CODE_PK | ENABLED
PK | LOLO_MSQ_ATT_MAP_PK | ENABLED | PK | LOLO_MSQ_ATT_MAP_PK | ENABLED
PK | GENERAL_REFERENCE_PK | ENABLED | PK | GENERAL_REFERENCE_PK | ENABLED
PK | MOP_ORDER_ITEM_NOTIFICATION_PK | ENABLED | PK | MOP_ORDER_ITEM_NOTIFICATION_PK | ENABLED
PK | MOP_ORDER_PK | ENABLED | PK | MOP_ORDER_PK | ENABLED
PK | FNN_VALIDATION_RESPONSE_PK | ENABLED | PK | FNN_VALIDATION_RESPONSE_PK | ENABLED
PK | FNN_RELOCATION_RESPONSE_PK | ENABLED | PK | FNN_RELOCATION_RESPONSE_PK | ENABLED
PK | ERROR_MAPPING_PK | ENABLED | PK | ERROR_MAPPING_PK | ENABLED
PK | BUNDLE_PRODUCT_CLASS_PK | ENABLED | PK | BUNDLE_PRODUCT_CLASS_PK | ENABLED
PK | PLAN_PK | ENABLED | PK | PLAN_PK | ENABLED
PK | BPM_USER_PK | ENABLED | PK | BPM_USER_PK | ENABLED
UK | RULEFLITER_UK1 | ENABLED | UK | RULEFLITER_UK1 | ENABLED
UK | SPG_UK1 | ENABLED | UK | SPG_UK1 | ENABLED

## C.5.PM Bench Mark Report (hidden)
Application SQL Performacne Bench Mark
SQL ID | SQL Text | Execution Timings
|  | Before Reorg | Before Partition | After partition | Before Re-org with Partition | After Reorg
SQL_1 | select /*+ index (req ECS_USER) */ count(*) from request req where req.ecs_user_id ='E1810628869S92' and req.request_revision_id in (select request_revision_id from Request_Status_History where status_timestamp in (select max(status_timestamp) from Request_Status_History rsh where req.request_revision_id = rsh.request_revision_id ) and request_status_code='RQC' ); | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
SQL_2 | SELECT crd_revision_id, assigned, crd_id, from_time, to_time, revision, request_revision_id, appmt_revision_id, crd_type FROM crd WHERE appmt_revision_id = 56747187 | 0:01 | 0:01 | 0:00 | 0:00 | 0:00
SQL_3 | select change_request_id, sp_contact_name, sp_contact_nbr, change_type, reason_code, initiating_user_id, request_revision_id, cust_req_date_time, change_notes, cust_discon_date_time, version from change_request where cust_req_date_time between trunc(sysdate-1) and trunc(sysdate); | 0:01 | 0:01 | 0:00 | 0:00 | 0:00
SQL_4 | select count(*) from activity_history where created_date between trunc(sysdate-1) and trunc(sysdate); | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
SQL_5 | select * from Request_Status_History where request_Status_History_Id in (select max(request_Sta tus_History_Id ) from Request_Status_History where request_Id ='951638' ) | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
SQL_6 | select notes_id, type, description, request_revision_id, request_item_revision_id, username, created_date from notes where created_date between trunc(sysdate-1) and trunc(sysdate); | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
SQL_7 | SELECT request_revision_id, request_id, revision, ecs_user_id, notes, cidn, medium_of_entry, sp_id, received_timestamp, sp_reference_no, active_revision, sp_contact_id, customer_name, customer_number, DECODE (action, '1', NULL, action) action, channel_type, attribute1, attribute2 FROM request WHERE received_timestamp BETWEEN '06-JUN-13 01.18.18.863000000 PM' AND '09-JUN-13 09.00.32.656000000 AM' and rownum<=200; | 0:02 | 0:02 | 0:00 | 0:00 | 0:00
SQL_8 | select mop_order_notification_id, ksu_code, ksu_status, ksu_notes, ksu_sub_status, order_item_revision_id, created_timestamp from mop_order_item_notification where created_timestamp between trunc(sysdate-1) and trunc(sysdate); | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
SQL_9 | SELECT fnn_validation_response_id, fnn_status, service_status, ERROR_CODE, error_description, request_item_revision_id FROM fnn_validation_response WHERE request_item_revision_id in (select request_item_revision_id from request_item where request_revision_id in (select request_revision_id from request where request_id in (select request_id from request_status_history where request_status_code='RQC') )) | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
SQL_10 | select request_status_history_id, status_timestamp, request_status_code, request_id, request_revision_id from request_status_history where status_timestamp between trunc(sysdate-1) and trunc(sysdate) and rownum<=500; | 0:03 | 0:03 | 0:00 | 0:00 | 0:00

## D.1.LOB Content Table (hidden)
ACTIVITY_HISTORY TABLE BEFORE AND AFTER CHANGE
| Before Change | Forecasted | After Change
DDL | CREATE TABLE NBNLOLO.MESSAGE ( MESSAGE_ID NUMBER(10), TRANSACTION VARCHAR2(20 BYTE), TARGET_APPLICATION VARCHAR2(20 BYTE), CONTENT CLOB, MESSAGE_TYPE VARCHAR2(10 BYTE), PARENT_MESSAGE_ID NUMBER(10), REQUEST_ID NUMBER(10) ) TABLESPACE LOLO_DATA_UL03 PCTUSED 0 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT ) LOGGING NOCOMPRESS LOB (CONTENT) STORE AS ( TABLESPACE LOLO_DATA_UL03 ENABLE STORAGE IN ROW CHUNK 16384 RETENTION NOCACHE INDEX ( TABLESPACE LOLO_DATA_UL03 STORAGE ( INITIAL 64M NEXT 1 MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT )) STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT ) ) NOCACHE NOPARALLEL MONITORING; CREATE UNIQUE INDEX NBNLOLO.MESSAGE_ID_PK ON NBNLOLO.MESSAGE (MESSAGE_ID) LOGGING TABLESPACE LOLO_IDX_UL01 PCTFREE 10 INITRANS 2 MAXTRANS 255 STORAGE ( INITIAL 32M NEXT 32M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT ) NOPARALLEL; ALTER TABLE NBNLOLO.MESSAGE ADD ( CONSTRAINT MESSAGE_ID_PK PRIMARY KEY (MESSAGE_ID) USING INDEX TABLESPACE LOLO_IDX_UL01 PCTFREE 10 INITRANS 2 MAXTRANS 255 STORAGE ( INITIAL 32M NEXT 32M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 )); ALTER TABLE NBNLOLO.MESSAGE ADD ( CONSTRAINT PARENT_MESSAGE_ID_FK FOREIGN KEY (PARENT_MESSAGE_ID) REFERENCES NBNLOLO.MESSAGE (MESSAGE_ID) DISABLE); | CREATE TABLE NBNLOLO.MESSAGE ( MESSAGE_ID NUMBER(10), TRANSACTION VARCHAR2(20 BYTE), TARGET_APPLICATION VARCHAR2(20 BYTE), CONTENT CLOB, MESSAGE_TYPE VARCHAR2(10 BYTE), PARENT_MESSAGE_ID NUMBER(10), REQUEST_ID NUMBER(10) ) TABLESPACE LOLO_DATA_UL03 PCTUSED 0 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT ) LOGGING NOCOMPRESS LOB (CONTENT) STORE AS MSG_CONTENT_CLOB_SGMNT ( TABLESPACE LOLO_DATA_LOB ENABLE STORAGE IN ROW CHUNK 16384 RETENTION NOCACHE INDEX ( TABLESPACE LOLO_DATA_LOB STORAGE ( INITIAL 64M NEXT 1 MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT )) STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT ) ) NOCACHE NOPARALLEL MONITORING; CREATE UNIQUE INDEX NBNLOLO.MESSAGE_ID_PK ON NBNLOLO.MESSAGE (MESSAGE_ID) LOGGING TABLESPACE LOLO_IDX_UL01 PCTFREE 10 INITRANS 2 MAXTRANS 255 STORAGE ( INITIAL 32M NEXT 32M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT ) NOPARALLEL; ALTER TABLE NBNLOLO.MESSAGE ADD ( CONSTRAINT MESSAGE_ID_PK PRIMARY KEY (MESSAGE_ID) USING INDEX TABLESPACE LOLO_IDX_UL01 PCTFREE 10 INITRANS 2 MAXTRANS 255 STORAGE ( INITIAL 32M NEXT 32M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 )); ALTER TABLE NBNLOLO.MESSAGE ADD ( CONSTRAINT PARENT_MESSAGE_ID_FK FOREIGN KEY (PARENT_MESSAGE_ID) REFERENCES NBNLOLO.MESSAGE (MESSAGE_ID) DISABLE); | CREATE TABLE NBNLOLO.MESSAGE ( MESSAGE_ID NUMBER(10), TRANSACTION VARCHAR2(20 BYTE), TARGET_APPLICATION VARCHAR2(20 BYTE), CONTENT CLOB, MESSAGE_TYPE VARCHAR2(10 BYTE), PARENT_MESSAGE_ID NUMBER(10), REQUEST_ID NUMBER(10) ) TABLESPACE LOLO_DATA_LOB PCTUSED 0 PCTFREE 10 INITRANS 1 MAXTRANS 255 STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT ) LOGGING NOCOMPRESS LOB (CONTENT) STORE AS MSG_CONTENT_CLOB_SGMNT ( TABLESPACE LOLO_DATA_LOB ENABLE STORAGE IN ROW CHUNK 16384 RETENTION NOCACHE INDEX ( TABLESPACE LOLO_DATA_LOB STORAGE ( INITIAL 32M NEXT 1 MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT )) STORAGE ( INITIAL 64M NEXT 64M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT ) ) NOCACHE NOPARALLEL MONITORING; CREATE UNIQUE INDEX NBNLOLO.MESSAGE_ID_PK ON NBNLOLO.MESSAGE (MESSAGE_ID) LOGGING TABLESPACE LOLO_IDX_UL01 PCTFREE 10 INITRANS 2 MAXTRANS 255 STORAGE ( INITIAL 32M NEXT 32M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 BUFFER_POOL DEFAULT ) NOPARALLEL; ALTER TABLE NBNLOLO.MESSAGE ADD ( CONSTRAINT MESSAGE_ID_PK PRIMARY KEY (MESSAGE_ID) USING INDEX TABLESPACE LOLO_IDX_UL01 PCTFREE 10 INITRANS 2 MAXTRANS 255 STORAGE ( INITIAL 32M NEXT 32M MINEXTENTS 1 MAXEXTENTS UNLIMITED PCTINCREASE 0 )); ALTER TABLE NBNLOLO.MESSAGE ADD ( CONSTRAINT PARENT_MESSAGE_ID_FK FOREIGN KEY (PARENT_MESSAGE_ID) REFERENCES NBNLOLO.MESSAGE (MESSAGE_ID) DISABLE);
INDEXES | MESSAGE_ID_PK | MESSAGE_ID_PK
CONSTRAINTS | PARENT_MESSAGE_ID_FK | PARENT_MESSAGE_ID_FK | PARENT_MESSAGE_ID_FK
ROWCOUNT | 4020242 | 0
PARENT TABLE | Seff Reference | Seff Reference | Seff Reference
CHILD TABLE | Nill | Nill | Nill

## D.2. ApplnSchema Object Status (hidden)
Application Schema Object Status | [5 empty] | Application Schema Object Status Summary
Before Change |  |  | After Change |  |  | Before Change |  |  | After Change
OBJECT_TYPE | OBJECT_NAME | STATUS | OBJECT_TYPE | OBJECT_NAME | STATUS | OBJECT_TYPE | STATUS | NO OBJS | OBJECT_TYPE | STATUS | NO OBJS
DATABASE_LINK | CAT | VALID | DATABASE_LINK | CAT | VALID | DATABASE_LINK | VALID | 3 | DATABASE_LINK | VALID | 3
DATABASE_LINK | LOLO | VALID | DATABASE_LINK | LOLO | VALID | FUNCTION | VALID | 5 | FUNCTION | VALID | 5
DATABASE_LINK | MYLOLOCAT | VALID | DATABASE_LINK | MYLOLOCAT | VALID | INDEX | VALID | 142 | INDEX | VALID | 144
FUNCTION | FN_APP_DATE | VALID | FUNCTION | FN_APP_DATE | VALID | LOB | VALID | 3 | LOB | VALID | 4
FUNCTION | GET_APP_REV_ID | VALID | FUNCTION | GET_APP_REV_ID | VALID | SEQUENCE | VALID | 9 | SEQUENCE | VALID | 9
FUNCTION | GET_FNN | VALID | FUNCTION | GET_FNN | VALID | SYNONYM | VALID | 13 | SYNONYM | VALID | 13
FUNCTION | GET_ORDER_NO | VALID | FUNCTION | GET_ORDER_NO | VALID | TABLE | VALID | 121 | TABLE | VALID | 122
FUNCTION | SQUIRREL_GET_ERROR_OFFSET | VALID | FUNCTION | SQUIRREL_GET_ERROR_OFFSET | VALID | VIEW | VALID | 1 | VIEW | VALID | 1
INDEX | ACTIVITY_HISTORY_PK | VALID | INDEX | ACTIVITY_HISTORY_PK | VALID | Total |  | 297 | Total |  | 301
INDEX | ACTIVITY_HISTORY_PK_OLD | VALID | INDEX | ACTIVITY_HISTORY_PK_OLD | VALID |  | Diff | 4
INDEX | ACTIVITY_ID_IDX | VALID | INDEX | ACTIVITY_ID_IDX | VALID
INDEX | ACTIVITY_ID_IDX_OLD | VALID | INDEX | ACTIVITY_ID_IDX_OLD | VALID | Note : Differece is due to MESSGE_OLD table and its indexes
INDEX | ACTIVITY_PK | VALID | INDEX | ACTIVITY_PK | VALID
INDEX | AH_UPDATED_DATE_IDX | VALID | INDEX | AH_UPDATED_DATE_IDX | VALID
INDEX | AH_UPDATED_DATE_IDX_OLD | VALID | INDEX | AH_UPDATED_DATE_IDX_OLD | VALID
INDEX | AMEND_LOCK_PK | VALID | INDEX | AMEND_LOCK_PK | VALID
INDEX | APPOINTMENT_REQREVNID_IDX | VALID | INDEX | APPOINTMENT_REQREVNID_IDX | VALID
INDEX | ASSIGNED_USER_IDX | VALID | INDEX | ASSIGNED_USER_IDX | VALID
INDEX | ASSIGNMENT_HISTORY_PK | VALID | INDEX | ASSIGNMENT_HISTORY_PK | VALID
INDEX | ATTRIBUTE_PK | VALID | INDEX | ATTRIBUTE_PK | VALID
INDEX | AUST_STATE_PK | VALID | INDEX | AUST_STATE_PK | VALID
INDEX | BPM_USER_PK | VALID | INDEX | BPM_USER_PK | VALID
INDEX | BUNDLE_PRODUCT_CLASS_PK | VALID | INDEX | BUNDLE_PRODUCT_CLASS_PK | VALID
INDEX | CCA_PK | VALID | INDEX | CCA_PK | VALID
INDEX | CHANGE_REQUEST_PK | VALID | INDEX | CHANGE_REQUEST_PK | VALID
INDEX | CHARAC_ASSOCIATION_PK | VALID | INDEX | CHARAC_ASSOCIATION_PK | VALID
INDEX | CHARAC_PARAM_ASSOCIATION_PK | VALID | INDEX | CHARAC_PARAM_ASSOCIATION_PK | VALID
INDEX | CHARAC_PARAMETER_PK | VALID | INDEX | CHARAC_PARAMETER_PK | VALID
INDEX | CHARACTERISTIC_PK | VALID | INDEX | CHARACTERISTIC_PK | VALID
INDEX | COMPLEX_REQUEST_ITEM_PK | VALID | INDEX | COMPLEX_REQUEST_ITEM_PK | VALID
INDEX | CRD_APPMT_REVNID_IDX | VALID | INDEX | CRD_APPMT_REVNID_IDX | VALID
INDEX | CRD_PK | VALID | INDEX | CRD_PK | VALID
INDEX | CREATED_DATE_IDX | VALID | INDEX | CREATED_DATE_IDX | VALID
INDEX | CREATED_DATE_IDX_OLD | VALID | INDEX | CREATED_DATE_IDX_OLD | VALID
INDEX | CUSTOMER_COURTESY_TITLE_PK | VALID | INDEX | CUSTOMER_COURTESY_TITLE_PK | VALID
INDEX | CUSTOMER_TYPE_PK | VALID | INDEX | CUSTOMER_TYPE_PK | VALID
INDEX | DIRECTORY_DETAILS_PK | VALID | INDEX | DIRECTORY_DETAILS_PK | VALID
INDEX | EAST_ADDRESS_TYPE_PK | VALID | INDEX | EAST_ADDRESS_TYPE_PK | VALID
INDEX | EAST_AXIS_ADDRESS_TYPE_PK | VALID | INDEX | EAST_AXIS_ADDRESS_TYPE_PK | VALID
INDEX | EAST_AXIS_STREET_TYPE_PK | VALID | INDEX | EAST_AXIS_STREET_TYPE_PK | VALID
INDEX | EAST_AXIS_STRT_TYPE_SUFFIX_PK | VALID | INDEX | EAST_AXIS_STRT_TYPE_SUFFIX_PK | VALID
INDEX | EAST_SUB_ADDRESS_TYPE_PK | VALID | INDEX | EAST_SUB_ADDRESS_TYPE_PK | VALID
INDEX | ECS_USER | VALID | INDEX | ECS_USER | VALID
INDEX | ECS_USER_IDX | VALID | INDEX | ECS_USER_IDX | VALID
INDEX | ENTRY_MEDIUM_PK | VALID | INDEX | ENTRY_MEDIUM_PK | VALID
INDEX | EQUIPMENT_PK | VALID | INDEX | EQUIPMENT_PK | VALID
INDEX | EQUIPMENT_TYPE_PK | VALID | INDEX | EQUIPMENT_TYPE_PK | VALID
INDEX | ERROR_MAPPING_PK | VALID | INDEX | ERROR_MAPPING_PK | VALID
INDEX | FK_ASSH_REQ_01 | VALID | INDEX | FK_ASSH_REQ_01 | VALID
INDEX | FK_ASSH_USERS_01 | VALID | INDEX | FK_ASSH_USERS_01 | VALID
INDEX | FK_ASSH_WQ_01 | VALID | INDEX | FK_ASSH_WQ_01 | VALID
INDEX | FK_CRIT_REQ_01 | VALID | INDEX | FK_CRIT_REQ_01 | VALID
INDEX | FK_EQUIP_ETYP_01 | VALID | INDEX | FK_EQUIP_ETYP_01 | VALID
INDEX | FK_EQUIP_RITM_01 | VALID | INDEX | FK_EQUIP_RITM_01 | VALID
INDEX | FK_QA_WG_01 | VALID | INDEX | FK_QA_WG_01 | VALID
INDEX | FK_QA_WQ_01 | VALID | INDEX | FK_QA_WQ_01 | VALID
INDEX | FK_WG_WG_01 | VALID | INDEX | FK_WG_WG_01 | VALID
INDEX | FNN_RELOCATION_RESPONSE_PK | VALID | INDEX | FNN_RELOCATION_RESPONSE_PK | VALID
INDEX | FNN_VALDN_RESP_REVID_IDX | VALID | INDEX | FNN_VALDN_RESP_REVID_IDX | VALID
INDEX | FNN_VALIDATION_RESPONSE_PK | VALID | INDEX | FNN_VALIDATION_RESPONSE_PK | VALID
INDEX | FULLY_CONFIG_SQ_RESPONSE_PK | VALID | INDEX | FULLY_CONFIG_SQ_RESPONSE_PK | VALID
INDEX | FWOM_TIME_SLOT_PK | VALID | INDEX | FWOM_TIME_SLOT_PK | VALID
INDEX | GENERAL_REFERENCE_PK | VALID | INDEX | GENERAL_REFERENCE_PK | VALID
INDEX | INSTANT_HOTLINE_PK | VALID | INDEX | INSTANT_HOTLINE_PK | VALID
INDEX | LOLO_MSQ_ATT_MAP_PK | VALID | INDEX | LOLO_MSQ_ATT_MAP_PK | VALID
INDEX | LOLO_MSQ_SRV_MAP_PK | VALID | INDEX | LOLO_MSQ_SRV_MAP_PK | VALID
INDEX | MESSAGE_ID_PK | VALID | INDEX | MESSAGE_ID_PK | VALID
INDEX | MOP_ORDER_ITEM_NOTIFICATION_PK | VALID | INDEX | MESSAGE_PK_20131230 | VALID
INDEX | MOP_ORDER_PK | VALID | INDEX | MOP_ORDER_ITEM_NOTIFICATION_PK | VALID
INDEX | MOP_STATUS_PK | VALID | INDEX | MOP_ORDER_PK | VALID
INDEX | NK_FNN | VALID | INDEX | MOP_STATUS_PK | VALID
INDEX | NOTES_PK | VALID | INDEX | NK_FNN | VALID
INDEX | OFFERING_ATTRIBUTE_PK | VALID | INDEX | NOTES_PK | VALID
INDEX | OFFERING_OFFERING_TYPE_PK | VALID | INDEX | OFFERING_ATTRIBUTE_PK | VALID
INDEX | OFFERING_PK | VALID | INDEX | OFFERING_OFFERING_TYPE_PK | VALID
INDEX | OFFERING_TYPE_PK | VALID | INDEX | OFFERING_PK | VALID
INDEX | PCMS_CODE_PK | VALID | INDEX | OFFERING_TYPE_PK | VALID
INDEX | PLAN_PK | VALID | INDEX | PCMS_CODE_PK | VALID
INDEX | POP_LOCK_PK | VALID | INDEX | PLAN_PK | VALID
INDEX | POP_RULE_ACTION_PK | VALID | INDEX | POP_LOCK_PK | VALID
INDEX | POP_RULE_BINDING_PK | VALID | INDEX | POP_RULE_ACTION_PK | VALID
INDEX | POP_RULE_CONDITION_PK | VALID | INDEX | POP_RULE_BINDING_PK | VALID
INDEX | POSTCODE_LOCALITY_PK | VALID | INDEX | POP_RULE_CONDITION_PK | VALID
INDEX | PRODUCT_CLASS_PK | VALID | INDEX | POSTCODE_LOCALITY_PK | VALID
INDEX | PROGRAMMING_PK | VALID | INDEX | PRODUCT_CLASS_PK | VALID
INDEX | PSTS_SERVICE_PK | VALID | INDEX | PROGRAMMING_PK | VALID
INDEX | QUEUE_ASSIGNMENT_PK | VALID | INDEX | PSTS_SERVICE_PK | VALID
INDEX | QUEUE_CRITERIA_PK | VALID | INDEX | QUEUE_ASSIGNMENT_PK | VALID
INDEX | REASON_CODE_PK | VALID | INDEX | QUEUE_CRITERIA_PK | VALID
INDEX | REASON_PK | VALID | INDEX | REASON_CODE_PK | VALID
INDEX | REQ_ID_IDX | VALID | INDEX | REASON_PK | VALID
INDEX | REQ_ITEM_HISTORY_IDX | VALID | INDEX | REQ_ID_IDX | VALID
INDEX | REQ_ITEM_STATUS_IDX | VALID | INDEX | REQ_ITEM_HISTORY_IDX | VALID
INDEX | REQ_REVISION_IDX | VALID | INDEX | REQ_ITEM_STATUS_IDX | VALID
INDEX | REQ_STATUS_CODE_IDX | VALID | INDEX | REQ_REVISION_IDX | VALID
INDEX | REQ_STATUS_DESC_IDX | VALID | INDEX | REQ_STATUS_CODE_IDX | VALID
INDEX | REQ_STATUS_IDX | VALID | INDEX | REQ_STATUS_DESC_IDX | VALID
INDEX | REQUEST_ID_PK | VALID | INDEX | REQ_STATUS_IDX | VALID
INDEX | REQUEST_ITEM_PK | VALID | INDEX | REQUEST_ID_PK | VALID
INDEX | REQUEST_ITEM_REVISION_ID_IDX | VALID | INDEX | REQUEST_ITEM_PK | VALID
INDEX | REQUEST_ITEM_STATUS_HISTORY_PK | VALID | INDEX | REQUEST_ITEM_REVISION_ID_IDX | VALID
INDEX | REQUEST_ITEM_STATUS_PK | VALID | INDEX | REQUEST_ITEM_STATUS_HISTORY_PK | VALID
INDEX | REQUEST_PK | VALID | INDEX | REQUEST_ITEM_STATUS_PK | VALID
INDEX | REQUEST_REV_IDX | VALID | INDEX | REQUEST_PK | VALID
INDEX | REQUEST_REV_IDX_OLD | VALID | INDEX | REQUEST_REV_IDX | VALID
INDEX | REQUEST_REVISDTSTAMP_IDX | VALID | INDEX | REQUEST_REV_IDX_OLD | VALID
INDEX | REQUEST_REVISION_ID_AH_IDX | VALID | INDEX | REQUEST_REVISDTSTAMP_IDX | VALID
INDEX | REQUEST_REVISION_ID_AH_IDX_OLD | VALID | INDEX | REQUEST_REVISION_ID_AH_IDX | VALID
INDEX | REQUEST_REVISION_ID_IDX | VALID | INDEX | REQUEST_REVISION_ID_AH_IDX_OLD | VALID
INDEX | REQUEST_SPCONTACT_PK | VALID | INDEX | REQUEST_REVISION_ID_IDX | VALID
INDEX | REQUEST_STATUS_HISTORY_PK | VALID | INDEX | REQUEST_SPCONTACT_PK | VALID
INDEX | REQUEST_STATUS_PK | VALID | INDEX | REQUEST_STATUS_HISTORY_PK | VALID
INDEX | REVISION_IDX | VALID | INDEX | REQUEST_STATUS_PK | VALID
INDEX | RULEACTION_PK | VALID | INDEX | REVISION_IDX | VALID
INDEX | RULECONDITION_PK | VALID | INDEX | RULEACTION_PK | VALID
INDEX | RULEFLITER_UK1 | VALID | INDEX | RULECONDITION_PK | VALID
INDEX | SDDB_ATTRIBUTE_PK | VALID | INDEX | RULEFLITER_UK1 | VALID
INDEX | SELECTED_PRODUCT_PK | VALID | INDEX | SDDB_ATTRIBUTE_PK | VALID
INDEX | SERVICE_IDENTIFIER_PK | VALID | INDEX | SELECTED_PRODUCT_PK | VALID
INDEX | SERVICE_NK_NUMBER_INVENTORY_PK | VALID | INDEX | SERVICE_IDENTIFIER_PK | VALID
INDEX | SERVICE_OFFERING_PK | VALID | INDEX | SERVICE_NK_NUMBER_INVENTORY_PK | VALID
INDEX | SERVICE_PROVIDER_PK | VALID | INDEX | SERVICE_OFFERING_PK | VALID
INDEX | SERVICE_STATUS_HISTORY_PK | VALID | INDEX | SERVICE_PROVIDER_PK | VALID
INDEX | SERVICE_STATUS_PK | VALID | INDEX | SERVICE_STATUS_HISTORY_PK | VALID
INDEX | SERVICEABILITYRESPONSE_PK | VALID | INDEX | SERVICE_STATUS_PK | VALID
INDEX | SP_CIDN_PK | VALID | INDEX | SERVICEABILITYRESPONSE_PK | VALID
INDEX | SP_CONTACT_PK | VALID | INDEX | SP_CIDN_PK | VALID
INDEX | SP_GROUP_PK | VALID | INDEX | SP_CONTACT_PK | VALID
INDEX | SP_INDEX | VALID | INDEX | SP_GROUP_PK | VALID
INDEX | SP_SHORT_NAME_PK | VALID | INDEX | SP_INDEX | VALID
INDEX | SP_SP_GROUP_PK | VALID | INDEX | SP_SHORT_NAME_PK | VALID
INDEX | SP_VIEWABLE_FLAG_IDX | VALID | INDEX | SP_SP_GROUP_PK | VALID
INDEX | SP_VIEWABLE_FLAG_IDX_OLD | VALID | INDEX | SP_VIEWABLE_FLAG_IDX | VALID
INDEX | SP_WORK_TYPE_AUTH_PK | VALID | INDEX | SP_VIEWABLE_FLAG_IDX_OLD | VALID
INDEX | SPOFFERINGASSOC_PK | VALID | INDEX | SP_WORK_TYPE_AUTH_PK | VALID
INDEX | SYS_IL0000062608C00004$$ | VALID | INDEX | SPG_UK1 | VALID
INDEX | SYS_IL0000062611C00006$$ | VALID | INDEX | SPOFFERINGASSOC_PK | VALID
INDEX | SYS_IL0000062649C00036$$ | VALID | INDEX | SYS_IL0000062608C00004$$ | VALID
INDEX | TARIFF_PK | VALID | INDEX | SYS_IL0000062611C00006$$ | VALID
INDEX | TIME_SLOT_PK | VALID | INDEX | SYS_IL0000062649C00036$$ | VALID
INDEX | TPSQL_IDX | VALID | INDEX | SYS_IL0000093502C00004$$ | VALID
INDEX | UK_SPG_01 | VALID | INDEX | TARIFF_PK | VALID
INDEX | USER_PK | VALID | INDEX | TIME_SLOT_PK | VALID
INDEX | WORK_GROUP_PK | VALID | INDEX | TPSQL_IDX | VALID
INDEX | WORK_QUEUE_PK | VALID | INDEX | USER_PK | VALID
INDEX | WORK_TYPE_ALLOWED_OFFERING_PK | VALID | INDEX | WORK_GROUP_PK | VALID
INDEX | WORK_TYPE_CATEGORY_PK | VALID | INDEX | WORK_QUEUE_PK | VALID
INDEX | WORK_TYPE_OFFERING_PK | VALID | INDEX | WORK_TYPE_ALLOWED_OFFERING_PK | VALID
INDEX | WORK_TYPE_PK | VALID | INDEX | WORK_TYPE_CATEGORY_PK | VALID
INDEX | WORKQUEUE_DECISION_PK | VALID | INDEX | WORK_TYPE_OFFERING_PK | VALID
LOB | SYS_LOB0000062608C00004$$ | VALID | INDEX | WORK_TYPE_PK | VALID
LOB | SYS_LOB0000062611C00006$$ | VALID | INDEX | WORKQUEUE_DECISION_PK | VALID
LOB | SYS_LOB0000062649C00036$$ | VALID | LOB | MSG_CONTENT_CLOB_SGMNT | VALID
SEQUENCE | LOLIG_SEQUENCE | VALID | LOB | SYS_LOB0000062608C00004$$ | VALID
SEQUENCE | ORDER_SEQ | VALID | LOB | SYS_LOB0000062611C00006$$ | VALID
SEQUENCE | ORDERID_SEQ | VALID | LOB | SYS_LOB0000062649C00036$$ | VALID
SEQUENCE | ORDERITEM_SEQ | VALID | SEQUENCE | LOLIG_SEQUENCE | VALID
SEQUENCE | ORDERITEMID_SEQ | VALID | SEQUENCE | ORDER_SEQ | VALID
SEQUENCE | REQUEST_SEQ | VALID | SEQUENCE | ORDERID_SEQ | VALID
SEQUENCE | REQUESTID_SEQ | VALID | SEQUENCE | ORDERITEM_SEQ | VALID
SEQUENCE | REQUESTITEM_SEQ | VALID | SEQUENCE | ORDERITEMID_SEQ | VALID
SEQUENCE | REQUESTITEMID_SEQ | VALID | SEQUENCE | REQUEST_SEQ | VALID
SYNONYM | ATTRIBUTE_1 | VALID | SEQUENCE | REQUESTID_SEQ | VALID
SYNONYM | ATTRIBUTE_VALUE_1 | VALID | SEQUENCE | REQUESTITEM_SEQ | VALID
SYNONYM | AUST_STATE_1 | VALID | SEQUENCE | REQUESTITEMID_SEQ | VALID
SYNONYM | OFFERING_ATTRIBUTE_1 | VALID | SYNONYM | ATTRIBUTE_1 | VALID
SYNONYM | OFFERING_OFFERING_TYPE_1 | VALID | SYNONYM | ATTRIBUTE_VALUE_1 | VALID
SYNONYM | OFFERING_TYPE_1 | VALID | SYNONYM | AUST_STATE_1 | VALID
SYNONYM | REQUEST_ITEM_STATUS_HISTORY_1 | VALID | SYNONYM | OFFERING_ATTRIBUTE_1 | VALID
SYNONYM | REQUEST_STATUS_1 | VALID | SYNONYM | OFFERING_OFFERING_TYPE_1 | VALID
SYNONYM | REQUEST_STATUS_HISTORY_1 | VALID | SYNONYM | OFFERING_TYPE_1 | VALID
SYNONYM | SERVICE_OFFERING_1 | VALID | SYNONYM | REQUEST_ITEM_STATUS_HISTORY_1 | VALID
SYNONYM | SERVICE_OFFERING_SETTING_1 | VALID | SYNONYM | REQUEST_STATUS_1 | VALID
SYNONYM | WORK_TYPE_1 | VALID | SYNONYM | REQUEST_STATUS_HISTORY_1 | VALID
SYNONYM | WORK_TYPE_CATEGORY_1 | VALID | SYNONYM | SERVICE_OFFERING_1 | VALID
TABLE | ACTIVITY | VALID | SYNONYM | SERVICE_OFFERING_SETTING_1 | VALID
TABLE | ACTIVITY_HISTORY | VALID | SYNONYM | WORK_TYPE_1 | VALID
TABLE | ACTIVITY_HISTORY_OLD | VALID | SYNONYM | WORK_TYPE_CATEGORY_1 | VALID
TABLE | ADDRESS | VALID | TABLE | ACTIVITY | VALID
TABLE | AMEND_LOCK | VALID | TABLE | ACTIVITY_HISTORY | VALID
TABLE | APPOINTMENT | VALID | TABLE | ACTIVITY_HISTORY_OLD | VALID
TABLE | ASSIGNMENT_HISTORY | VALID | TABLE | ADDRESS | VALID
TABLE | ATTRIBUTE | VALID | TABLE | AMEND_LOCK | VALID
TABLE | ATTRIBUTE_VALUE | VALID | TABLE | APPOINTMENT | VALID
TABLE | AUST_STATE | VALID | TABLE | ASSIGNMENT_HISTORY | VALID
TABLE | BPM_USERS | VALID | TABLE | ATTRIBUTE | VALID
TABLE | BUNDLE | VALID | TABLE | ATTRIBUTE_VALUE | VALID
TABLE | BUNDLE_NETWORK_TYPE | VALID | TABLE | AUST_STATE | VALID
TABLE | BUNDLE_PRODUCT_CLASS | VALID | TABLE | BPM_USERS | VALID
TABLE | CCA | VALID | TABLE | BUNDLE | VALID
TABLE | CHAINED_ROWS | VALID | TABLE | BUNDLE_NETWORK_TYPE | VALID
TABLE | CHANGE_REQUEST | VALID | TABLE | BUNDLE_PRODUCT_CLASS | VALID
TABLE | CHANNEL | VALID | TABLE | CCA | VALID
TABLE | CHARAC_ASSOCIATION | VALID | TABLE | CHAINED_ROWS | VALID
TABLE | CHARAC_PARAM_ASSOCIATION | VALID | TABLE | CHANGE_REQUEST | VALID
TABLE | CHARAC_PARAM_VALUE | VALID | TABLE | CHANNEL | VALID
TABLE | CHARAC_PARAMETER | VALID | TABLE | CHARAC_ASSOCIATION | VALID
TABLE | CHARACTERISTIC | VALID | TABLE | CHARAC_PARAM_ASSOCIATION | VALID
TABLE | COMPLEX_REQUEST_ITEM | VALID | TABLE | CHARAC_PARAM_VALUE | VALID
TABLE | CRD | VALID | TABLE | CHARAC_PARAMETER | VALID
TABLE | CUSTOMER | VALID | TABLE | CHARACTERISTIC | VALID
TABLE | CUSTOMER_COURTESY_TITLE | VALID | TABLE | COMPLEX_REQUEST_ITEM | VALID
TABLE | CUSTOMER_TYPE | VALID | TABLE | CRD | VALID
TABLE | DIRECTORY_DETAILS | VALID | TABLE | CUSTOMER | VALID
TABLE | EAST_ADDRESS_TYPE | VALID | TABLE | CUSTOMER_COURTESY_TITLE | VALID
TABLE | EAST_AXIS_ADDRESS_TYPE | VALID | TABLE | CUSTOMER_TYPE | VALID
TABLE | EAST_AXIS_STREET_TYPE | VALID | TABLE | DIRECTORY_DETAILS | VALID
TABLE | EAST_AXIS_STREET_TYPE_SUFFIX | VALID | TABLE | EAST_ADDRESS_TYPE | VALID
TABLE | EAST_SUB_ADDRESS_TYPE | VALID | TABLE | EAST_AXIS_ADDRESS_TYPE | VALID
TABLE | ENTRY_MEDIUM | VALID | TABLE | EAST_AXIS_STREET_TYPE | VALID
TABLE | EQUIPMENT | VALID | TABLE | EAST_AXIS_STREET_TYPE_SUFFIX | VALID
TABLE | EQUIPMENT_TYPE | VALID | TABLE | EAST_SUB_ADDRESS_TYPE | VALID
TABLE | ERROR_MAPPING | VALID | TABLE | ENTRY_MEDIUM | VALID
TABLE | FNN_RELOCATION_RESPONSE | VALID | TABLE | EQUIPMENT | VALID
TABLE | FNN_VALIDATION_RESPONSE | VALID | TABLE | EQUIPMENT_TYPE | VALID
TABLE | FULLY_CONFIG_SQ_RESPONSE | VALID | TABLE | ERROR_MAPPING | VALID
TABLE | FWOM_TIME_SLOT | VALID | TABLE | FNN_RELOCATION_RESPONSE | VALID
TABLE | GENERAL_REFERENCE | VALID | TABLE | FNN_VALIDATION_RESPONSE | VALID
TABLE | INSTANT_HOTLINE | VALID | TABLE | FULLY_CONFIG_SQ_RESPONSE | VALID
TABLE | LOLO_FWOM_REASON_MAP | VALID | TABLE | FWOM_TIME_SLOT | VALID
TABLE | LOLO_MSQ_ATT_MAP | VALID | TABLE | GENERAL_REFERENCE | VALID
TABLE | LOLO_MSQ_SRV_MAP | VALID | TABLE | INSTANT_HOTLINE | VALID
TABLE | MESSAGE | VALID | TABLE | LOLO_FWOM_REASON_MAP | VALID
TABLE | MOP_ORDER | VALID | TABLE | LOLO_MSQ_ATT_MAP | VALID
TABLE | MOP_ORDER_ITEM | VALID | TABLE | LOLO_MSQ_SRV_MAP | VALID
TABLE | MOP_ORDER_ITEM_NOTIFICATION | VALID | TABLE | MESSAGE | VALID
TABLE | MOP_SERVICE_INVENTORY | VALID | TABLE | MESSAGE_20131230 | VALID
TABLE | MOP_STATUS | VALID | TABLE | MOP_ORDER | VALID
TABLE | NOTES | VALID | TABLE | MOP_ORDER_ITEM | VALID
TABLE | OFFERING | VALID | TABLE | MOP_ORDER_ITEM_NOTIFICATION | VALID
TABLE | OFFERING_ATTRIBUTE | VALID | TABLE | MOP_SERVICE_INVENTORY | VALID
TABLE | OFFERING_BUNDLE_ASSOCIATION | VALID | TABLE | MOP_STATUS | VALID
TABLE | OFFERING_CATEGORY | VALID | TABLE | NOTES | VALID
TABLE | OFFERING_OFFERING_TYPE | VALID | TABLE | OFFERING | VALID
TABLE | OFFERING_TYPE | VALID | TABLE | OFFERING_ATTRIBUTE | VALID
TABLE | PCMS_CODE | VALID | TABLE | OFFERING_BUNDLE_ASSOCIATION | VALID
TABLE | POP_LOCK | VALID | TABLE | OFFERING_CATEGORY | VALID
TABLE | POP_RULE_ACTION | VALID | TABLE | OFFERING_OFFERING_TYPE | VALID
TABLE | POP_RULE_BINDING | VALID | TABLE | OFFERING_TYPE | VALID
TABLE | POP_RULE_CONDITION | VALID | TABLE | PCMS_CODE | VALID
TABLE | PORT_CHURN_INFO | VALID | TABLE | POP_LOCK | VALID
TABLE | POSTCODE_LOCALITY | VALID | TABLE | POP_RULE_ACTION | VALID
TABLE | PRODUCT_CLASS | VALID | TABLE | POP_RULE_BINDING | VALID
TABLE | PRODUCT_CLASS_OFFERING | VALID | TABLE | POP_RULE_CONDITION | VALID
TABLE | PROGRAMMING | VALID | TABLE | PORT_CHURN_INFO | VALID
TABLE | PSTS_SERVICE | VALID | TABLE | POSTCODE_LOCALITY | VALID
TABLE | QUEUE_ASSIGNMENT | VALID | TABLE | PRODUCT_CLASS | VALID
TABLE | QUEUE_CRITERIA | VALID | TABLE | PRODUCT_CLASS_OFFERING | VALID
TABLE | REASON | VALID | TABLE | PROGRAMMING | VALID
TABLE | REQUEST | VALID | TABLE | PSTS_SERVICE | VALID
TABLE | REQUEST_ITEM | VALID | TABLE | QUEUE_ASSIGNMENT | VALID
TABLE | REQUEST_ITEM_STATUS | VALID | TABLE | QUEUE_CRITERIA | VALID
TABLE | REQUEST_ITEM_STATUS_HISTORY | VALID | TABLE | REASON | VALID
TABLE | REQUEST_SPCONTACT | VALID | TABLE | REQUEST | VALID
TABLE | REQUEST_STATUS | VALID | TABLE | REQUEST_ITEM | VALID
TABLE | REQUEST_STATUS_HISTORY | VALID | TABLE | REQUEST_ITEM_STATUS | VALID
TABLE | RULEACTION | VALID | TABLE | REQUEST_ITEM_STATUS_HISTORY | VALID
TABLE | RULECONDITION | VALID | TABLE | REQUEST_SPCONTACT | VALID
TABLE | RULEFLITER | VALID | TABLE | REQUEST_STATUS | VALID
TABLE | SDDB_ATTRIBUTE | VALID | TABLE | REQUEST_STATUS_HISTORY | VALID
TABLE | SELECTED_PRODUCT | VALID | TABLE | RULEACTION | VALID
TABLE | SERVICE | VALID | TABLE | RULECONDITION | VALID
TABLE | SERVICE_AREA_ASSOCIATION | VALID | TABLE | RULEFLITER | VALID
TABLE | SERVICE_IDENTIFIER | VALID | TABLE | SDDB_ATTRIBUTE | VALID
TABLE | SERVICE_NK_NUMBER_INVENTORY | VALID | TABLE | SELECTED_PRODUCT | VALID
TABLE | SERVICE_OFFERING | VALID | TABLE | SERVICE | VALID
TABLE | SERVICE_OFFERING_SETTING | VALID | TABLE | SERVICE_AREA_ASSOCIATION | VALID
TABLE | SERVICE_PROVIDER | VALID | TABLE | SERVICE_IDENTIFIER | VALID
TABLE | SERVICE_STATUS | VALID | TABLE | SERVICE_NK_NUMBER_INVENTORY | VALID
TABLE | SERVICE_STATUS_HISTORY | VALID | TABLE | SERVICE_OFFERING | VALID
TABLE | SERVICEABILITY_RESPONSE | VALID | TABLE | SERVICE_OFFERING_SETTING | VALID
TABLE | SP_BUNDLE | VALID | TABLE | SERVICE_PROVIDER | VALID
TABLE | SP_CIDN | VALID | TABLE | SERVICE_STATUS | VALID
TABLE | SP_CONTACT | VALID | TABLE | SERVICE_STATUS_HISTORY | VALID
TABLE | SP_GROUP | VALID | TABLE | SERVICEABILITY_RESPONSE | VALID
TABLE | SP_OFFERING | VALID | TABLE | SP_BUNDLE | VALID
TABLE | SP_OFFERING_ASSOCIATION | VALID | TABLE | SP_CIDN | VALID
TABLE | SP_SHORT_NAME | VALID | TABLE | SP_CONTACT | VALID
TABLE | SP_SP_GROUP | VALID | TABLE | SP_GROUP | VALID
TABLE | SP_WORK_TYPE_AUTH | VALID | TABLE | SP_OFFERING | VALID
TABLE | SQ_MAPPING | VALID | TABLE | SP_OFFERING_ASSOCIATION | VALID
TABLE | SYS_TEMP_FBT | VALID | TABLE | SP_SHORT_NAME | VALID
TABLE | T_ERROR_CODE_MAST | VALID | TABLE | SP_SP_GROUP | VALID
TABLE | TARIFF | VALID | TABLE | SP_WORK_TYPE_AUTH | VALID
TABLE | TBL_AUDIT_LOLIG | VALID | TABLE | SQ_MAPPING | VALID
TABLE | TIME_SLOT | VALID | TABLE | SYS_TEMP_FBT | VALID
TABLE | TOAD_PLAN_SQL | VALID | TABLE | T_ERROR_CODE_MAST | VALID
TABLE | TOAD_PLAN_TABLE | VALID | TABLE | TARIFF | VALID
TABLE | USERS | VALID | TABLE | TBL_AUDIT_LOLIG | VALID
TABLE | WORK_GROUP | VALID | TABLE | TIME_SLOT | VALID
TABLE | WORK_QUEUE | VALID | TABLE | TOAD_PLAN_SQL | VALID
TABLE | WORK_TYPE | VALID | TABLE | TOAD_PLAN_TABLE | VALID
TABLE | WORK_TYPE_ALLOWED_OFFERING | VALID | TABLE | USERS | VALID
TABLE | WORK_TYPE_CATEGORY | VALID | TABLE | WORK_GROUP | VALID
TABLE | WORK_TYPE_OFFERING | VALID | TABLE | WORK_QUEUE | VALID
TABLE | WORKQUEUE_DECISION | VALID | TABLE | WORK_TYPE | VALID
VIEW | PCMS_CODE_OFFERING_VIEW | VALID | TABLE | WORK_TYPE_ALLOWED_OFFERING | VALID
|  |  | TABLE | WORK_TYPE_CATEGORY | VALID
|  |  | TABLE | WORK_TYPE_OFFERING | VALID
|  |  | TABLE | WORKQUEUE_DECISION | VALID
|  |  | VIEW | PCMS_CODE_OFFERING_VIEW | VALID

## D.3.Appln.Table Constrai Status (hidden)
Application Table Constraint Status Details | [5 empty] | Disabled Constraints | [5 empty] | Application Object Constraint Summary
Before Rename |  |  | After Rename |  |  | Before Change |  | Forecasted |  | After Change |  | Before Rename |  |  | After Rename
CONSTRAINT_TYPE | CONSTRAINT_NAME | STATUS | CONSTRAINT_TYPE | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_NAME | STATUS | CONSTRAINT_TYPE | STATUS | No.Cons | CONSTRAINT_TYPE | STATUS | No.Cons
CK | WORK_QUEUE_DELFLG_CK | ENABLED | CK | EQUIPMENT_DELVMD_CK | ENABLED | CHANGE_REQUEST_FK | DISABLED | CHANGE_REQUEST_FK | DISABLED | CHANGE_REQUEST_FK | DISABLED | CK | ENABLED | 16 | CK | ENABLED | 16
CK | POP_RULE_CONDITION_CK | ENABLED | CK | POP_RULE_CONDITION_CK | ENABLED | MOP_STATUS_FK | DISABLED | MOP_STATUS_FK | DISABLED | MOP_STATUS_FK | DISABLED | FK | DISABLED | 12 | FK | DISABLED | 13
CK | SYS_C0031655 | ENABLED | CK | EQUIPMENT_CK | ENABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED | OFFERTYPE_OFFERING_OT_FK | DISABLED | FK | ENABLED | 32 | FK | ENABLED | 32
CK | SYS_C0031656 | ENABLED | CK | POP_RULE_ACTION_CK | ENABLED | PARENT_MESSAGE_ID_FK | DISABLED | PARENT_MESSAGE_ID_FK | DISABLED | PARENT_MESSAGE_ID_FK | DISABLED | PK | ENABLED | 94 | PK | ENABLED | 95
CK | AUST_STATE_CK | ENABLED | CK | SYS_C0032037 | ENABLED | PARENT_SERV_OFF_FK | DISABLED | PARENT_MESSAGE_ID_FK_20131230 | DISABLED | PARENT_MESSAGE_ID_FK_20131230 | DISABLED | UK | ENABLED | 2 | UK | ENABLED | 2
CK | WORK_TYPE_CATEGORY_CK | ENABLED | CK | SYS_C0032036 | ENABLED | REASON_CODE_FK | DISABLED | PARENT_SERV_OFF_FK | DISABLED | PARENT_SERV_OFF_FK | DISABLED | Total |  | 156 | Total |  | 158
CK | SYS_C0032034 | ENABLED | CK | WORK_TYPE_CATEGORY_DELFLG_CK | ENABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED | REASON_CODE_FK | DISABLED | REASON_CODE_FK | DISABLED |  | Diff | 158
CK | POP_RULE_CONDN_RULE_CONDN_CK | ENABLED | CK | POP_RULE_CONDN_RULE_CONDN_CK | ENABLED | RQST_STATUS_STATUSHIST_FK | DISABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED | RI_STATUSHIST_RI_STATUS_FK | DISABLED
CK | WORK_TYPE_CATEGORY_DELFLG_CK | ENABLED | CK | SYS_C0032034 | ENABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | RQST_STATUS_STATUSHIST_FK | DISABLED | RQST_STATUS_STATUSHIST_FK | DISABLED
CK | SYS_C0032036 | ENABLED | CK | WORK_TYPE_CATEGORY_CK | ENABLED | SP_WORK_TYPE_AUTH_FK | DISABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED
CK | SYS_C0032037 | ENABLED | CK | AUST_STATE_CK | ENABLED | SPOFFERINGASSOC_ATT_FK | DISABLED | SP_WORK_TYPE_AUTH_FK | DISABLED | SP_WORK_TYPE_AUTH_FK | DISABLED
CK | POP_RULE_ACTION_CK | ENABLED | CK | SYS_C0031656 | ENABLED | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | SPOFFERINGASSOC_ATT_FK | DISABLED | SPOFFERINGASSOC_ATT_FK | DISABLED
CK | EQUIPMENT_CK | ENABLED | CK | SYS_C0031655 | ENABLED |  |  | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | WORKTYPE_CAT_WORKTYPE_FK | DISABLED
CK | SP_SHORT_NAME_CK | ENABLED | CK | WORK_QUEUE_CK | ENABLED
CK | EQUIPMENT_DELVMD_CK | ENABLED | CK | WORK_QUEUE_DELFLG_CK | ENABLED |  |  | Difference is due to Old MESSGE table with two constraints
CK | WORK_QUEUE_CK | ENABLED | CK | SP_SHORT_NAME_CK | ENABLED
FK | FK_QA_WORK_QUEUE_1 | ENABLED | FK | RQSTITAM_BUNDLE_FK | ENABLED | CK - Check
FK | ASSIGNMENT_HISTORY_FK | ENABLED | FK | CHARACTERISTIC_FK | ENABLED | FK - Reference
FK | ACTIVITY_HISTORY_FK | ENABLED | FK | CHARACTERISTIC_FK_01 | ENABLED | PK - Primary Key
FK | AHOLD_HISTORY_FK | ENABLED | FK | CHARAC_ASSOC_ID_FK | ENABLED | UK - Unique Key
FK | OFFER_ATTT_FK | ENABLED | FK | CHARAC_PARAM_ID_FK | ENABLED
FK | LOLO_MSQ_ATT_ATTRIBUTE_FK | ENABLED | FK | CHARAC_PARAM_ASSOC_ID_FK | ENABLED
FK | SPOFFERINGASSOC_ATT_FK | DISABLED | FK | EQUIPMENT_FK | ENABLED
FK | POSTCODE_LOCALITY_FK | ENABLED | FK | WTAO_OFFID_FK | ENABLED
FK | PARENT_MESSAGE_ID_FK | DISABLED | FK | PCO_OFFID_FK | ENABLED
FK | OFFERTYPE_OFFERING_OT_FK | DISABLED | FK | OFFERING_PCMS_CODE_FK | ENABLED
FK | CHANGE_REQUEST_FK | DISABLED | FK | PCO_PRDID_FK | ENABLED
FK | REASON_CODE_FK | DISABLED | FK | RQST_RQSTITEM_FK | ENABLED
FK | RQSTITEM_REASON_CODE_FK | ENABLED | FK | FNN_VLD_RSP_REQSTITAM_FK | ENABLED
FK | RI_STATUSHIST_RI_STATUS_FK | DISABLED | FK | FNN_REL_RSP_REQSTITAM_FK | ENABLED
FK | REQUEST_ITEM_FK | ENABLED | FK | USERS_FK | ENABLED
FK | SP_CONACT_ID_FK | ENABLED | FK | QUEUE_ASSIGNMENT_FK | ENABLED
FK | RQST_STATUS_STATUSHIST_FK | DISABLED | FK | REQUEST_FK | ENABLED
FK | FK_REQ_RSTAT_01 | ENABLED | FK | FK_QA_WORK_QUEUE_1 | ENABLED
FK | PARENT_SERV_OFF_FK | DISABLED | FK | ASSIGNMENT_HISTORY_FK | ENABLED
FK | MOP_STATUS_FK | DISABLED | FK | ACTIVITY_HISTORY_FK | ENABLED
FK | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED | FK | AHOLD_HISTORY_FK | ENABLED
FK | SRGROUP_SP_GROUP_FK | ENABLED | FK | OFFER_ATTT_FK | ENABLED
FK | WTAO_WTID_FK | ENABLED | FK | LOLO_MSQ_ATT_ATTRIBUTE_FK | ENABLED
FK | SP_WORK_TYPE_AUTH_FK | DISABLED | FK | SPOFFERINGASSOC_ATT_FK | DISABLED
FK | REQUESTITAM_WORKTYPE_FK | ENABLED | FK | POSTCODE_LOCALITY_FK | ENABLED
FK | WORKTYPE_CAT_WORKTYPE_FK | DISABLED | FK | PARENT_MESSAGE_ID_FK_20131230 | DISABLED
FK | USER_SPD_FK | ENABLED | FK | OFFERTYPE_OFFERING_OT_FK | DISABLED
FK | REQUEST_FK | ENABLED | FK | CHANGE_REQUEST_FK | DISABLED
FK | QUEUE_ASSIGNMENT_FK | ENABLED | FK | REASON_CODE_FK | DISABLED
FK | USERS_FK | ENABLED | FK | RQSTITEM_REASON_CODE_FK | ENABLED
FK | FNN_REL_RSP_REQSTITAM_FK | ENABLED | FK | RI_STATUSHIST_RI_STATUS_FK | DISABLED
FK | FNN_VLD_RSP_REQSTITAM_FK | ENABLED | FK | REQUEST_ITEM_FK | ENABLED
FK | RQST_RQSTITEM_FK | ENABLED | FK | SP_CONACT_ID_FK | ENABLED
FK | PCO_PRDID_FK | ENABLED | FK | RQST_STATUS_STATUSHIST_FK | DISABLED
FK | OFFERING_PCMS_CODE_FK | ENABLED | FK | FK_REQ_RSTAT_01 | ENABLED
FK | PCO_OFFID_FK | ENABLED | FK | PARENT_SERV_OFF_FK | DISABLED
FK | WTAO_OFFID_FK | ENABLED | FK | MOP_STATUS_FK | DISABLED
FK | EQUIPMENT_FK | ENABLED | FK | SERVSTATUS_SERVSTATUS_HIST_FK | DISABLED
FK | CHARAC_PARAM_ASSOC_ID_FK | ENABLED | FK | SRGROUP_SP_GROUP_FK | ENABLED
FK | CHARAC_PARAM_ID_FK | ENABLED | FK | WTAO_WTID_FK | ENABLED
FK | CHARAC_ASSOC_ID_FK | ENABLED | FK | SP_WORK_TYPE_AUTH_FK | DISABLED
FK | CHARACTERISTIC_FK_01 | ENABLED | FK | REQUESTITAM_WORKTYPE_FK | ENABLED
FK | RQSTITAM_BUNDLE_FK | ENABLED | FK | WORKTYPE_CAT_WORKTYPE_FK | DISABLED
FK | CHARACTERISTIC_FK | ENABLED | FK | USER_SPD_FK | ENABLED
PK | EAST_AXIS_STRT_TYPE_SUFFIX_PK | ENABLED | FK | PARENT_MESSAGE_ID_FK | DISABLED
PK | LOLO_MSQ_SRV_MAP_PK | ENABLED | PK | REQUEST_ITEM_STATUS_PK | ENABLED
PK | INSTANT_HOTLINE_PK | ENABLED | PK | QUEUE_CRITERIA_PK | ENABLED
PK | DIRECTORY_DETAILS_PK | ENABLED | PK | QUEUE_ASSIGNMENT_PK | ENABLED
PK | CHARAC_PARAM_ASSOCIATION_PK | ENABLED | PK | PRODUCT_CLASS_PK | ENABLED
PK | CHARAC_PARAMETER_PK | ENABLED | PK | REQUEST_ITEM_PK | ENABLED
PK | CHARACTERISTIC_PK | ENABLED | PK | POP_RULE_CONDITION_PK | ENABLED
PK | FWOM_TIME_SLOT_PK | ENABLED | PK | POP_RULE_BINDING_PK | ENABLED
PK | FULLY_CONFIG_SQ_RESPONSE_PK | ENABLED | PK | POP_RULE_ACTION_PK | ENABLED
PK | ENTRY_MEDIUM_PK | ENABLED | PK | AMEND_LOCK_PK | ENABLED
PK | EAST_AXIS_STREET_TYPE_PK | ENABLED | PK | PSTS_SERVICE_PK | ENABLED
PK | EAST_AXIS_ADDRESS_TYPE_PK | ENABLED | PK | PROGRAMMING_PK | ENABLED
PK | EAST_ADDRESS_TYPE_PK | ENABLED | PK | OFFERING_TYPE_PK | ENABLED
PK | CUSTOMER_TYPE_PK | ENABLED | PK | REASON_PK | ENABLED
PK | CUSTOMER_COURTESY_TITLE_PK | ENABLED | PK | OFFERING_PK | ENABLED
PK | ACTIVITY_HISTORY_PK | ENABLED | PK | POSTCODE_LOCALITY_PK | ENABLED
PK | PCMS_CODE_PK | ENABLED | PK | OFFERING_ATTRIBUTE_PK | ENABLED
PK | OFFERING_OFFERING_TYPE_PK | ENABLED | PK | NOTES_PK | ENABLED
PK | EQUIPMENT_TYPE_PK | ENABLED | PK | MOP_STATUS_PK | ENABLED
PK | EQUIPMENT_PK | ENABLED | PK | SERVICE_NK_NUMBER_INVENTORY_PK | ENABLED
PK | EAST_SUB_ADDRESS_TYPE_PK | ENABLED | PK | POP_LOCK_PK | ENABLED
PK | CHANGE_REQUEST_PK | ENABLED | PK | REASON_CODE_PK | ENABLED
PK | AUST_STATE_PK | ENABLED | PK | LOLO_MSQ_ATT_MAP_PK | ENABLED
PK | SP_CIDN_PK | ENABLED | PK | GENERAL_REFERENCE_PK | ENABLED
PK | SERVICE_PROVIDER_PK | ENABLED | PK | MOP_ORDER_ITEM_NOTIFICATION_PK | ENABLED
PK | ASSIGNMENT_HISTORY_PK | ENABLED | PK | MOP_ORDER_PK | ENABLED
PK | CHARAC_ASSOCIATION_PK | ENABLED | PK | FNN_VALIDATION_RESPONSE_PK | ENABLED
PK | ATTRIBUTE_PK | ENABLED | PK | FNN_RELOCATION_RESPONSE_PK | ENABLED
PK | WORK_TYPE_ALLOWED_OFFERING_PK | ENABLED | PK | ERROR_MAPPING_PK | ENABLED
PK | WORK_TYPE_PK | ENABLED | PK | BUNDLE_PRODUCT_CLASS_PK | ENABLED
PK | ACTIVITY_PK | ENABLED | PK | PLAN_PK | ENABLED
PK | AHOLD_HISTORY_PK | ENABLED | PK | BPM_USER_PK | ENABLED
PK | WORK_TYPE_CATEGORY_PK | ENABLED | PK | MESSGE_PK_20131230 | ENABLED
PK | WORKQUEUE_DECISION_PK | ENABLED | PK | EAST_AXIS_STRT_TYPE_SUFFIX_PK | ENABLED
PK | TIME_SLOT_PK | ENABLED | PK | LOLO_MSQ_SRV_MAP_PK | ENABLED
PK | CCA_PK | ENABLED | PK | INSTANT_HOTLINE_PK | ENABLED
PK | WORK_QUEUE_PK | ENABLED | PK | DIRECTORY_DETAILS_PK | ENABLED
PK | WORK_TYPE_OFFERING_PK | ENABLED | PK | CHARAC_PARAM_ASSOCIATION_PK | ENABLED
PK | SP_WORK_TYPE_AUTH_PK | ENABLED | PK | CHARAC_PARAMETER_PK | ENABLED
PK | SPOFFERINGASSOC_PK | ENABLED | PK | CHARACTERISTIC_PK | ENABLED
PK | WORK_GROUP_PK | ENABLED | PK | FWOM_TIME_SLOT_PK | ENABLED
PK | SP_GROUP_PK | ENABLED | PK | FULLY_CONFIG_SQ_RESPONSE_PK | ENABLED
PK | COMPLEX_REQUEST_ITEM_PK | ENABLED | PK | ENTRY_MEDIUM_PK | ENABLED
PK | SERVICE_STATUS_HISTORY_PK | ENABLED | PK | EAST_AXIS_STREET_TYPE_PK | ENABLED
PK | TARIFF_PK | ENABLED | PK | EAST_AXIS_ADDRESS_TYPE_PK | ENABLED
PK | USER_PK | ENABLED | PK | EAST_ADDRESS_TYPE_PK | ENABLED
PK | SERVICE_OFFERING_PK | ENABLED | PK | CUSTOMER_TYPE_PK | ENABLED
PK | SERVICE_IDENTIFIER_PK | ENABLED | PK | CUSTOMER_COURTESY_TITLE_PK | ENABLED
PK | SERVICEABILITYRESPONSE_PK | ENABLED | PK | ACTIVITY_HISTORY_PK | ENABLED
PK | SELECTED_PRODUCT_PK | ENABLED | PK | PCMS_CODE_PK | ENABLED
PK | SP_SP_GROUP_PK | ENABLED | PK | OFFERING_OFFERING_TYPE_PK | ENABLED
PK | RULECONDITION_PK | ENABLED | PK | EQUIPMENT_TYPE_PK | ENABLED
PK | RULEACTION_PK | ENABLED | PK | EQUIPMENT_PK | ENABLED
PK | SP_CONTACT_PK | ENABLED | PK | EAST_SUB_ADDRESS_TYPE_PK | ENABLED
PK | SP_SHORT_NAME_PK | ENABLED | PK | CHANGE_REQUEST_PK | ENABLED
PK | REQUEST_SPCONTACT_PK | ENABLED | PK | AUST_STATE_PK | ENABLED
PK | REQUEST_STATUS_HISTORY_PK | ENABLED | PK | SP_CIDN_PK | ENABLED
PK | REQUEST_STATUS_PK | ENABLED | PK | MESSAGE_ID_PK | ENABLED
PK | SERVICE_STATUS_PK | ENABLED | PK | SERVICE_PROVIDER_PK | ENABLED
PK | REQUEST_PK | ENABLED | PK | ASSIGNMENT_HISTORY_PK | ENABLED
PK | SDDB_ATTRIBUTE_PK | ENABLED | PK | CHARAC_ASSOCIATION_PK | ENABLED
PK | REQUEST_ITEM_STATUS_HISTORY_PK | ENABLED | PK | ATTRIBUTE_PK | ENABLED
PK | REQUEST_ITEM_STATUS_PK | ENABLED | PK | WORK_TYPE_ALLOWED_OFFERING_PK | ENABLED
PK | QUEUE_CRITERIA_PK | ENABLED | PK | WORK_TYPE_PK | ENABLED
PK | QUEUE_ASSIGNMENT_PK | ENABLED | PK | ACTIVITY_PK | ENABLED
PK | PRODUCT_CLASS_PK | ENABLED | PK | AHOLD_HISTORY_PK | ENABLED
PK | REQUEST_ITEM_PK | ENABLED | PK | WORK_TYPE_CATEGORY_PK | ENABLED
PK | POP_RULE_CONDITION_PK | ENABLED | PK | WORKQUEUE_DECISION_PK | ENABLED
PK | POP_RULE_BINDING_PK | ENABLED | PK | TIME_SLOT_PK | ENABLED
PK | POP_RULE_ACTION_PK | ENABLED | PK | CCA_PK | ENABLED
PK | AMEND_LOCK_PK | ENABLED | PK | WORK_QUEUE_PK | ENABLED
PK | PSTS_SERVICE_PK | ENABLED | PK | WORK_TYPE_OFFERING_PK | ENABLED
PK | PROGRAMMING_PK | ENABLED | PK | SP_WORK_TYPE_AUTH_PK | ENABLED
PK | OFFERING_TYPE_PK | ENABLED | PK | SPOFFERINGASSOC_PK | ENABLED
PK | REASON_PK | ENABLED | PK | WORK_GROUP_PK | ENABLED
PK | OFFERING_PK | ENABLED | PK | SP_GROUP_PK | ENABLED
PK | POSTCODE_LOCALITY_PK | ENABLED | PK | COMPLEX_REQUEST_ITEM_PK | ENABLED
PK | OFFERING_ATTRIBUTE_PK | ENABLED | PK | SERVICE_STATUS_HISTORY_PK | ENABLED
PK | NOTES_PK | ENABLED | PK | TARIFF_PK | ENABLED
PK | MOP_STATUS_PK | ENABLED | PK | USER_PK | ENABLED
PK | MESSAGE_ID_PK | ENABLED | PK | SERVICE_OFFERING_PK | ENABLED
PK | SERVICE_NK_NUMBER_INVENTORY_PK | ENABLED | PK | SERVICE_IDENTIFIER_PK | ENABLED
PK | POP_LOCK_PK | ENABLED | PK | SERVICEABILITYRESPONSE_PK | ENABLED
PK | REASON_CODE_PK | ENABLED | PK | SELECTED_PRODUCT_PK | ENABLED
PK | LOLO_MSQ_ATT_MAP_PK | ENABLED | PK | SP_SP_GROUP_PK | ENABLED
PK | GENERAL_REFERENCE_PK | ENABLED | PK | RULECONDITION_PK | ENABLED
PK | MOP_ORDER_ITEM_NOTIFICATION_PK | ENABLED | PK | RULEACTION_PK | ENABLED
PK | MOP_ORDER_PK | ENABLED | PK | SP_CONTACT_PK | ENABLED
PK | FNN_VALIDATION_RESPONSE_PK | ENABLED | PK | SP_SHORT_NAME_PK | ENABLED
PK | FNN_RELOCATION_RESPONSE_PK | ENABLED | PK | REQUEST_SPCONTACT_PK | ENABLED
PK | ERROR_MAPPING_PK | ENABLED | PK | REQUEST_STATUS_HISTORY_PK | ENABLED
PK | BUNDLE_PRODUCT_CLASS_PK | ENABLED | PK | REQUEST_STATUS_PK | ENABLED
PK | PLAN_PK | ENABLED | PK | SERVICE_STATUS_PK | ENABLED
PK | BPM_USER_PK | ENABLED | PK | REQUEST_PK | ENABLED
UK | RULEFLITER_UK1 | ENABLED | PK | SDDB_ATTRIBUTE_PK | ENABLED
UK | SPG_UK1 | ENABLED | PK | REQUEST_ITEM_STATUS_HISTORY_PK | ENABLED
|  |  | UK | RULEFLITER_UK1 | ENABLED
|  |  | UK | SPG_UK1 | ENABLED